## **2026-2027 QAP Approximate Development Timeline**

*Updated 4/15/25*

DCA is in its first round of a two-year QAP development timeline. Below is an updated approximate timeline of intended steps in the process of QAP engagement, development, and publishing. DCA welcomes partners to submit questions or concerns on this timeline to the [QAP Public Input Survey](https://dcaqap.formstack.com/forms/2023_htc_program_public_input_copy_copy) and to [melissa.florkowski@dca.ga.gov.](mailto:melissa.florkowski@dca.ga.gov)

The [QAP Public Input Survey](https://dcaqap.formstack.com/forms/2023_htc_program_public_input_copy_copy) is open year-round, but stakeholders are always encouraged to submit input as early as possible.

|  |  |  |
| --- | --- | --- |
| **Year** | **Approximate Timeframe** | **Stage** |
| 2024 | April – November | Open-ended engagement, one-on-one meetings on 2026-2027 QAP priorities |
| 2024 | October | Establish list of major policy priorities for 2026-2027 QAP |
| 2024 | October – December | Listening sessions on policy priorities |
| 2025 | January | Publish draft policy proposals for policy priorities |
| 2025 | January – February | Public comment period for policy proposals |
| 2025 | Mid-May | Publish Draft 1 of 2026-2027 QAP |
| 2025 | June | Public comment period for Draft 1 |
| 2025 | July | Publish Draft 2 of 2026-2027 QAP |
| 2025 | August | Public comment period for Draft 2 |
| 2025 | September | Publish final draft of 2026-2027 QAP |
| 2025 | October – November | Final approval from DCA Housing Committee and Board |