## Directions
2014 DESIGN & CONSTRUCTION REVIEW PROCESS
For NOFA Properties
Last updated: 04/18/14
OVERVIEW
In order to ensure compliance with Georgia DCA’s Architectural Standards for safe, decent, affordable housing, DCA monitors the design and construction of all projects awarded tax credits. As such, the project team is required to submit documents to DCA throughout the design and construction process for review.
It is the strict policy of DCA that all applicants will be held to all representations made in the OAH 2014 Core Application Form and all supporting documentation for the duration of the greater of either the Credit Compliance Period or term of the HOME loan. Any material project changes after submission of Application to DCA must be approved in writing by DCA prior to the change. Failure to obtain the appropriate approvals can result in unfavorable compliance scoring or the recapture of credits.
All design/construction submittals must be accompanied by the 2014 NOFA Design & Construction Transmittal (Transmittal Form). The Transmittal Form provides program-specific deadline dates and document requirements. Documents may be submitted earlier than the deadlines. Do not submit documents piecemeal or by email. DCA will not begin its review until all documents required for a particular stage have been submitted. Each separate staged submissions should include one organized binder (hard copy) and one organized flash drive (electronic copy). Do not combine the staged submissions (maintain separate transmittal/binder/flash drives per submission). All hard copies (including Project Team transmittals/cover letters) must be duplicated on the flash drive. See additional directions below.
All extension requests must be submitted in writing to:
Michael Collins, Architectural Services Dept.
michael.collins@dca.ga.gov
(404) 679-4898
EXIBIT "F" SUBMISSION
The following must be submitted in accordance with Exhibit "F":
1. 2014 NOFA Design & Construction Transmittal
2. ALTA/ACSM Land Title Survey (boundary and topographical survey)
3. Geotechnical Report (new construction only)
DCA REVIEW SUBMISSION
The following must be submitted on or before May before 1, 2014:
1. 2014 NOFA Design & Construction Transmittal
2. "Review Set" of drawings & specifications (see "Directions" for definition of "Review Set")
3. DCA Construction Document Log ("Review Set")
4. DCA Schedule of Values ("Review Set")
5. DCA Amenities & Design Options Re-certification
6. Evidence of Compliance with 2009 IECC
7. Federal Work Authorization (E-Verify) Affidavits (see DCA form)
8. Contractor Qualification package (see page 47 of 58 of the 2014 Threshold QAP)
9. DRAFT Owner/Contractor Agreement (current A101 Stipulated Sum or A102 Cost of Work Plus Fee With a Guaranteed Maximum Price forms)
10. DRAFT Construction schedule
11. Executed Owner/Architect Agreement
12. Executed contract with qualified accessibility consultant (DCA pre-qualified consultant)
13. Accessibility consultant's plan review comments
14. Narrative's that addresses progress of green building certification (when applicable)
15. Other:
PRIOR TO CONSTRUCTION LOAN CLOSING
The following must be submitted prior to the construction loan closing:
1. 2014 NOFA Design & Construction Transmittal
2. "Contract Set" of drawings & specifications (see "Directions" for definition of "Contract Set")
3. DCA Construction Document Log ("Contract Set")
4. DCA Schedule of Values ("Contract Set")
5. Addendum incorporating/outlining revisions from DCA "Review Set" into the DCA "Contract Set"
6. Executed Owner/Contractor Agreement
7. Other:
PRIOR TO CONSTRUCTION COMMENCEMENT
The following must be submitted prior to construction commencement:
1. 2014 NOFA Design & Construction Transmittal
2. Notice to Proceed
3. Finalized construction schedule
4. Building Permits
REQUIREMENTS FOR SUBMISSIONS
Binder
One binder containing all necessary forms and supporting documentation according to the Transmittal form and separated by numbered tab dividers in the order determined by the Transmittal form. The binder must be clearly labeled with the DCA project number and name on the front cover and spine area.
Drawings
The drawings must be printed in 12x18 half-size, scalable format. The entire plan set must be bound together and included separately from the binder.
Electronic Submission
One VIRUS-FREE USB flash drive in a small, protective re-sealable container (3-ring) with a built-in fastener - e.g., Velcro, zipper, Ziploc, string or metal clasp - containing exact electronic copies of all of the same items described above, arranged in the same order. The submission should be organized by folders and subfolders that follow the transmittal outline format (similar to the binder). The drawings submission should have subfolders for each discipline (Architectural, Structure, Landscaping, Electrical, etc.). **DO NOT ATTEMPT TO EMAIL THESE FILES**
Additional Info
1. Where a section contains multiple documents or pages, a folder must be created into which all files are loaded.
2. If a section will be empty, include NA at the end of the section name.
3. Double-check the flash drive. Verify that it contains all required files and that it operates properly.
4. Electronic submissions of DCA forms must be in Excel format.
5. Electronic drawing files must be labeled, at minimum, with the drawing page number which corresponds to the Drawing Log.
6. Drawings must be in PDF format and organized in subfolders by discipline
7. One project staged submission per flash drive (and binder/transmittal). The flash drive must be of a sufficient size to contain all files that will be submitted as well as added to by DCA.
8. Both the small, protective re-sealable container (three ring) and the external casing of the flash drive itself must be labeled with the DCA project name and number.
9. Do not submit Word docs (convert to PDF)
10. Maintain short file extension names and don't use special characters (#, $, &,,,)
Mailing Instructions
Georgia Department of Community Affairs
Office of Housing and Finance– Architectural Services Dept.
Attn: Architectural Administration
60 Executive Park South NE
Atlanta, Georgia 30329-2231
ADDITIONAL POLICIES
Definitions
DCA Review Set: The set of Construction Documents (CDs) that will be submitted to the local building authority for review in order to obtain the permit for construction. These Construction Documents would be expected to be at least 90‐95% complete.
DCA Contract Set (100% CDs): The set of Construction Documents (CDs) would be expected to have incorporated the local building authority comments from the permitting process, syndicator and/or lender review, DCA review, accessibility consultant review, and all other consultant's design comments (green building, historic preservation, etc.) and are an exhibit to the executed Owner/Contractor agreement.
Identities of Interest
If an identity of interest exists between any Project Participant and the contractor, than a preconstruction third‐party cost review must be conducted. For HOME projects, the third‐party cost review will be ordered by DCA upon submittal of the DCA Schedule of Values.

## NOFA Transmittal
|  |  | GEORGIA DEPARTMENT OF COMMUNITY AFFAIRS |  |  |  |  | NOFA
Office of Housing Finance and Development Division
Architectural Services Department
60 Executive Park South, NE, Atlanta, GA 30329-2231
2014 "NOFA" DESIGN & CONSTRUCTION TRANSMITTAL (form date: 05.26.14)
OWNER/DEVELOPER CONTACT FOR DESIGN/CONSTRUCTION REVIEW | [8 empty] | DATE:
Name | [8 empty] | DCA PROJECT #:
Company | [7 empty] | PROJECT
Email | [7 empty] | NAME:
Phone
PROJECT DESCRIPTION
| A. | Unit Descriptions |  | # of units | E. | Square Footage
|  | New Construction |  |  |  | Total Net Residential Unit Square Footage
|  | Adaptive Reuse |  |  |  | Total Gross Building Conditioned Square Footage
|  | Rehab |  |  |  | Total Gross Building Covered Square Footage
Historic Rehab
| B. | Total Residential Units |  |  | F. | Buildings
|  | Common Space Units |  |  |  | Number of Residential Buildings
|  | Total Units |  | 0 |  | Number of Non-Residential Buildings
[6 empty] | Total Number of Buildings |  |  |  |  | 0
| C. | Unit mix
|  | describe # of bedrooms & baths in each unit |  |  | G. | Tenancy: | Family or Senior
[5 empty] | H. | Accessibility
[6 empty] | Mobility Impaired Units |  |  |  | at least 5% of total units
| D. | Acreage |  |  |  | list unit #s for mobility units
|  | Gross Acreage |  |  |  | Sight / Hearing Impaired Unit |  |  |  | at least 2% of total units
|  | Developed acreage |  |  |  | list unit #s for site/hearing impaired units
PLACE AN 'X' IN THE BOX NEXT TO EACH DOCUMENT SUBMITTED
*** DO NOT COMBINE THE STAGED SUBMISSION PACKAGES (maintain separate binders/flash drives per submission) ***
EXIBIT "F" SUBMISSION (due in accordance with Exhibit "F")
ALTA/ACSM Land Title Survey (boundary and topographical survey)
Geotechnical Report (new construction only)
Other:
DCA REVIEW SUBMISSION (due on or before May before 1, 2014)
"Review Set" of drawings & specifications (see "Directions" for definition of "Review Set")
DCA Construction Document Log ("Review Set")
DCA Schedule of Values ("Review Set")
DCA Amenities & Design Options Re-certification
Evidence of Compliance with 2009 IECC
Federal Work Authorization (E-Verify) Affidavits (see DCA form)
Contractor Qualification package (see page 47 of 58 of the 2014 Threshold QAP)
DRAFT Owner/Contractor Agreement (current A101 Stipulated Sum or A102 Cost of Work Plus Fee With a Guaranteed Maximum Price forms)
DRAFT Construction schedule
Executed Owner/Architect Agreement
Executed contract with qualified accessibility consultant (DCA pre-qualified consultant)
Accessibility consultant's plan review comments
Grn Bldg Consultant Agreement "Executed" (when applicable)
Narrative's that addresses progress of green building certification (when applicable)
Other:
LOAN CLOSING SUBMISSION (due prior to HOME loan closing)
"Contract Set" of drawings & specifications (see "Directions" for definition of "Contract Set")
DCA Construction Document Log ("Contract Set")
DCA Schedule of Values ("Contract Set")
Addendum incorporating/outlining revisions from DCA "Review Set" into the DCA "Contract Set"
Executed Owner/Contractor Agreement
Other:
COMMENCEMENT SUBMISSION (due prior to construction commencement)
Notice to Proceed
Finalized construction schedule
Permits (Land Development, Building,,,)
Other:
OTHER SUBMISSIONS
Other:
Other:
Forms available at: http://www.dca.ga.gov/housing/housingdevelopment/programs/architecturaldesignandconstruction.asp