## Instructions
Georgia Department of Community Affairs
Office of Housing Finance and Development
Architectural Services Dept.
2014 DCA DESIGN & CONSTRUCTION SUBMISSION INSTRUCTIONS
(Form date: 1.14.15)
Overview
In order to ensure compliance with Georgia DCA’s Architectural Standards for safe, decent, affordable housing, DCA monitors the design and construction of all projects awarded tax credits and/or HOME funds. As such, the project team is required to submit documents to DCA throughout the design and construction process for review, which is accomplished through the Design & Construction (D&C) defined staged submission process.
Each D&C submission is comprised of an organized binder and flash drive which both contain the documents required for that submission. When required, the hard copies of the drawings (plans) and project manual (specs) are included separate from the binder. The program specific D&C transmittals are included in this Excel workbook for each required D&C submission. Additional information is provided in the Architectural Manual and the DCA award notices.
Note: Do NOT combine multiple staged D&C submissions into one binder and one flash drive (maintain separate binders/flash drives for each staged submission package).
Due Dates
Each program specific D&C Transmittal form provides the due dates for each required program submission Note: It is the responsibility of the Developer to request any necessary extensions.
Complete submission packages may be submitted earlier than the due dates but documents should not be submitted piecemeal or from multiple sources (i.e. the plans and specs should NOT be submitted separately by the design firm). DCA will not begin its review until all documents required for a particular submission have been received.
Extension Requests
For unforeseen circumstances, the project team may submit a formal extension request to DCA for consideration. All extension requests must be submitted in writing to:
Marie Palena, Affordable Housing Project Manager marie.palena@dca.ga.gov (404).679.4852)
Note: Any DCA approved submission extension request does NOT extend any other deadlines, in particular, the 10% test.
Design & Construction Transmittal forms
Each D&C staged submission must be accompanied by the proper program specific 2014 D&C Transmittal form located on separate tabs in this Excel workbook.
There is one transmittal form for projects that have received HOME commitments, and two each transmittal forms for projects that have received 4% or 9% tax credit allocation only. In addition to providing submission due dates, the D&C transmittal forms also provide an outline of the documents required for each staged submission
DCA Design & Construction Forms
The D&C forms that are required as part of the staged submissions are listed below and are available on the Architectural Design and Construction website page at the following link:
http://www.dca.ga.gov/housing/housingdevelopment/programs/architecturaldesignandconstruction.asp
• DCA Design & Construction Transmittal form (Excel)
• DCA Schedule of Values form (Excel)
• DCA Amenities & Design Options Re‐certification form (Excel)
• DCA Construction Document Log (Excel)
• E‐verify affidavits (owner, developer & contractor) (Excel)
Note: The completed electronic copies must be provided in DCA's original file type format (i.e. Excel file in lieu of converting to PDF).
Paper Submission Requirements
Submit one hard cover binder that contains all of the necessary forms and supporting documentation as identified in the related D&C Transmittal form.
The binder must be clearly labeled with the DCA project number, project name and submission type located on both the front cover and spine areas. Use double sided printing where feasible and do not use oversized binders so as to conserve DCA archive space. The binder should have plastic insert sleeves on the cover and spine areas.
The binder should include a Table of Contents and each section should be separated by numbered dividers/tabs and include section index pages that list each item in the section. The sections layout order of the binder should follow the outline of the applicable D&C Transmittal form submission type, with the transmittal form being the first section.
All drawing sheets (plans) must be printed in DCA's standard archive size of 12x18 (scalable format preferred). There should be one complete bound plan set with one common cover sheet that identifies ALL of the project drawings Note: Civil drawings should NOT be included separate from the main plan set.
The Project Manual (specs) should be soft bound with double sided printing.
The DCA project number and project name should be prominently displayed on the cover of both the Drawings and Project Manual (specs) and should identify that it is either the “DCA Review Set” or the “DCA Contract Set”.
The binder should include tabbed sections for both the drawings and project manual but only contain pages that notes that the two documents are attached as separate packages. Note: Do NOT include plans and specs in the binder.
The last section on the D&C Transmittal form titled "Other" should be used for additional documents submitted by the project team such as cover letters/internal transmittal forms.
Electronic Submission Requirements
For each required DCA submission provide one "virus-free" USB flash drive that contains enough storage space so that DCA may add additional documents to the drive as needed. The flash drive should contain an external identifying label/tag and "leash". A clear plastic “zip lock” type folder insert should be included inside the binder front area to contain the flash drive. Note: Do NOT email these files.
The folder layout order on the flash drive should follow the outline of the applicable D&C Transmittal form submission type, with the D&C Transmittal form being the first folder. For the drawings, use additional subfolders for each discipline (i.e.. Architectural, Structure, Electrical,,,) and note the sheet number on the file extension. The project manual is typically provided as a single PDF file but may be sub dived as long as it is organized.
The last section on the D&C Transmittal form titled "Other" should be used for additional documents submitted by the project team such as cover letters/internal transmittal forms.
The file extension names should be short as possible and NOT contain special characters (i.e.. $, &, #, %, *, / , \, etc.). All DCA forms should be submitted using the original file format (i.e. don't convert an Excel file type to a PDF).
Additional Submission Instructions
• Double‐check the flash drive folders for “junk files” that have been added by software or other non Windows operating systems and remove as needed.
• PDF files should have the ability to be searched or edited where feasible
• Electronic drawing file extensions must be labeled at minimum with the drawing page number which corresponds to the DCA Construction Document Log.
• Only one project submission should be included per flash drive and binder (do NOT combine submissions)
• Copies of all submitted paper documents should be included in the flash drive, including any delivery cover letters.
Definitions
• DCA Review Set:
The set of Construction Documents (CDs) that will be submitted to the local building authority for review in order to obtain the permit for construction. These CDs would be expected to be at least 90% complete.
• DCA Contract Set:
The set of Construction Documents (CDs) that are incorporated into the executed Owner/Contractor Agreement. These CDs would be expected to be 100% complete and should have incorporated the local building authority comments from the permitting process as well as comments from the syndicator/lender review, DCA review, accessibility consultant review, and all other consultant's design review comments (green building, historic preservation, etc.).
Note: If special circumstances arise where NOT all of the review comments/revisions are incorporated into the Contract Set at the time of the execution of the Owner/Contractor Agreement and will be incorporated into the Construction Documents at a later date (i.e. Change Order), then the Architect should provide a document identifying the missing elements.
• DCA Contract Set Addendum:
The Architect's contract document that identifies the revisions/additions that have occurred between the originally submitted DCA Review Set and the final DCA Contract Set (i.e.. design changes/completion, third party and municipality comments, etc.).
Identities of Interest
For HOME projects, the third‐party cost review will be engaged by DCA upon submittal and approval of the DCA Schedule of Values.
Mailing Instructions
Please deliver all submissions to:
Georgia Department of Community Affairs Architectural Services Department Attn: Administration 60 Executive Park South NE Atlanta, Georgia 30329‐2231

## 2014 HOME
|  |  |  | GEORGIA DEPARTMENT OF COMMUNITY AFFAIRS |  |  |  |  | HOME
Office of Housing Finance and Development
Architectural Services Department
60 Executive Park South, NE, Atlanta, GA 30329-2231
2014 DESIGN & CONSTRUCTION TRANSMITTAL (form date: 1.14.15)
OWNER/DEVELOPER CONTACT FOR DESIGN/CONSTRUCTION REVIEW | [9 empty] | DATE:
Name | [9 empty] | DCA PROJECT #:
Company | [8 empty] | PROJECT
Email | [8 empty] | NAME:
Phone
PROJECT DESCRIPTION
| A. | Unit Descriptions |  |  | # of units | E. | Square Footage
|  | New Construction |  |  |  |  | Total Net Residential Unit Square Footage
|  | Adaptive Reuse |  |  |  |  | Total Gross Building Conditioned Square Footage
|  | Rehab |  |  |  |  | Total Gross Building Covered Square Footage
Historic Rehab
[6 empty] | F. | Buildings
| B. | Total Residential Units |  |  |  |  | Number of Residential Buildings
|  | Common Space Units |  |  |  |  | Number of Non-Residential Buildings
|  | Total Units |  |  | 0 |  | Total Number of Buildings |  |  |  |  | 0
| C. | Unit mix (total units) |  |  |  | G. | Tenancy: | (family or senior)
describe # of bedrooms & baths in each unit type & total of units
[6 empty] | H. | Accessibility
[7 empty] | Mobility Impaired Units |  |  |  | at least 5% of total units
list unit #s for mobility units
| D. | Acreage |  |  |  |  | Mobility Impaired Units (roll-in showers) |  |  |  | 40% of the mobility units
list unit #s for mobility units (roll-in showers)
|  | Gross Acreage |  |  |  |  | Sight / Hearing Impaired Units |  |  |  | at least 2% of total units
|  | Developed acreage |  |  |  |  | list unit #s for site/hearing impaired units
*** DO NOT COMBINE THE STAGED SUBMISSION PACKAGES (maintain separate binders/flash drives per submission) ***
PLACE AN 'X' IN THE BOX NEXT TO EACH DOCUMENT SUBMITTED
60 DAY SUBMISSION (due 60 days after announcement of awards - January 19, 2015)
ALTA/ACSM Land Title Survey
Geotechnical Report (new construction only)
Accessibility consultant Agreement
Other:
DCA REVIEW SUBMISSION (due no later than May 1, 2015)
DCA "Review Set" of drawings (plans) (see "Directions" for definition of "Review Set")
DCA "Review Set" of Project Manual (specs)
DCA Construction Document Log (drawing log) (see DCA form)
DCA Schedule of Values (see DCA form)
Federal Work Authorization Affidavits (E-Verify)
Contractor Approval Package (see 2014 QAP Threshold)
DCA Amenities & Design Options Re-certification (see DCA form)
Narrative that identifies each Carryover Allocation "conditions of funding" and provides a status update of each condition
(ex.: wetlands delineations, noise mitigation plans, etc.) (restate each C.o.F in the narrative)
Executed contract with qualified accessibility consultant
DRAFT Owner/Contractor Agreement (current A101 Stipulated Sum or A102 Cost of Work Plus Fee With a Guaranteed Maximum Price forms)
DRAFT Construction schedule
Executed Owner/Architect Agreement
Green Building Consultant Agreement (contracts and MOUs)
DCA Architectural Waiver Approval(s)
Other:
LOAN CLOSING SUBMISSION (due prior to HOME loan closing)
DCA "Contract Set" of drawings (plans) (see "Directions" for definition of "Contract Set")
DCA "Contract Set" of Project Manual (specs)
Updated DCA Construction Document Log (contract set)
Addendum incorporating/outlining revisions from DCA Review Set into the DCA Contract Set
Executed Owner/Contractor Agreement
Updated DCA Schedule of Values (contract set)
Other:
COMMENCEMENT SUBMISSION (due prior to construction commencement)
Notice to Proceed
Finalized construction schedule
Permits (Land Development, Building, etc.)
Accessibility Consultant Plan Review Comments and Clearance letter
Other:
OTHER SUBMISSIONS
Other:
Other:
Note on A34: 2011 QAP-CORE: Completion of Work Scope (9% TC): Owners of projects receiving Credits in the 2011 round for the "rehabilitation" of an existing property must perform 100% of the work scope in accordance with the original "physical needs assessment" submitted with the Application no later than December 31, 2013. Owners of properties receiving Credits for "new construction" in the 2011 round must perform "100% of the work scope" as set forth in the DCA approved construction drawings and specifications no later than December 31, 2013. DCA Final Inspection Submission: Package should be submitted to the attention of the DCA Construction Administration when Contractor is requesting release of retainage (final pay request).

## 2014 9% PreCon
|  |  |  | GEORGIA DEPARTMENT OF COMMUNITY AFFAIRS |  |  |  |  | 9% TAX CREDIT ONLY
Office of Housing Finance and Development
Architectural Services Department
60 Executive Park South, NE, Atlanta, GA 30329-2231
2014 DESIGN & CONSTRUCTION - PRE CONSTRUCTION TRANSMITTAL (form date: 1.14.15)
OWNER/DEVELOPER CONTACT FOR DESIGN/CONSTRUCTION REVIEW | [9 empty] | DATE:
Name | [9 empty] | DCA PROJECT #:
Company | [8 empty] | PROJECT
Email | [8 empty] | NAME:
Phone
PROJECT DESCRIPTION
| A. | Unit Descriptions |  |  | # of units | E. | Square Footage
|  | New Construction |  |  |  |  | Total Net Residential Unit Square Footage
|  | Adaptive Reuse |  |  |  |  | Total Gross Building Conditioned Square Footage
|  | Rehab |  |  |  |  | Total Gross Building Covered Square Footage
Historic Rehab
[6 empty] | F. | Buildings
| B. | Total Residential Units |  |  |  |  | Number of Residential Buildings
|  | Common Space Units |  |  |  |  | Number of Non-Residential Buildings
|  | Total Units |  |  | 0 |  | Total Number of Buildings |  |  |  |  | 0
| C. | Unit mix |  |  |  | G. | Tenancy: | (family or senior)
describe # of bedrooms & baths in each unit type & total of units
[6 empty] | H. | Accessibility
[7 empty] | Mobility Impaired Units |  |  |  | at least 5% of total units
list unit #s for mobility units
| D. | Acreage |  |  |  |  | Mobility Impaired Units (roll-in showers) |  |  |  | 40% of the mobility units
|  | Gross Acreage |  |  |  |  | list unit #s for mobility units (roll-in showers)
|  | Developed acreage |  |  |  |  | Sight / Hearing Impaired Units |  |  |  | at least 2% of total units
list unit #s for site/hearing impaired units
*** DO NOT COMBINE THE STAGED SUBMISSION PACKAGES (maintain separate binders/flash drives per submission) ***
PLACE AN 'X' IN THE BOX NEXT TO EACH DOCUMENT SUBMITTED
60 DAY SUBMISSION (due 60 days after announcement of awards - January 19, 2015)
Boundary and Topographical Survey
Geotechnical Report (new construction only)
Accessibility consultant Agreement
Other:
DCA REVIEW SUBMISSION (due no later than May 1, 2015 or 60 days before construction loan closing; whichever is earliest)
DCA "Review Set" of drawings (plans) (see "Directions" for definition of "Review Set")
DCA "Review Set" of Project Manual (specs)
DCA Construction Document Log (drawing log) (see DCA form)
DCA Schedule of Values based upon the DCA Review Set (see DCA form)
Federal Work Authorization Affidavits (E-Verify)
DCA Amenities & Design Options Re-certification (see DCA form)
Narrative that identifies each Carryover Allocation "conditions of funding" and provides a status update of each condition
(ex.: wetlands delineations, noise mitigation plans, etc.) (restate each C.o.F in the narrative)
DRAFT Owner/Contractor Agreement (current A101 Stipulated Sum or A102 Cost of Work Plus Fee With a Guaranteed Maximum Price forms)
DRAFT Construction schedule
DCA Architectural Waiver Approval(s)
Green Building Consultant Agreement (contracts and MOUs)
Other:
LOAN CLOSING / COMMENCEMENT SUBMISSION (due prior to construction loan closing)
DCA "Contract Set" of drawings and specifications
Updated DCA Construction Document Log (contract set)
Addendum incorporating/outlining revisions from DCA Review Set into the DCA Contract Set
Executed Owner/Contractor Agreement
Updated DCA Schedule of Values (contract set)
Notice to Proceed
Finalized construction schedule
Permits (Land Development, Building, etc.)
Other:
Note on A34: 2011 QAP-CORE: Completion of Work Scope (9% TC): Owners of projects receiving Credits in the 2011 round for the "rehabilitation" of an existing property must perform 100% of the work scope in accordance with the original "physical needs assessment" submitted with the Application no later than December 31, 2013. Owners of properties receiving Credits for "new construction" in the 2011 round must perform "100% of the work scope" as set forth in the DCA approved construction drawings and specifications no later than December 31, 2013. DCA Final Inspection Submission: Package should be submitted to the attention of the DCA Construction Administration when Contractor is requesting release of retainage (final pay request).

## 2014 9% ConstAdmin
|  |  |  | GEORGIA DEPARTMENT OF COMMUNITY AFFAIRS |  |  |  | 9% TAX CREDIT ONLY
Office of Housing Finance and Development
Architectural Services Department
60 Executive Park South, NE, Atlanta, GA 30329-2231
2014 DESIGN & CONSTRUCTION - CONSTRUCTION ADMINISTRATION TRANSMITTAL (form date: 1.14.15)
OWNER/DEVELOPER CONTACT CONSTRUCTION ADMINISTRATION | [8 empty] | DATE:
Name | [8 empty] | DCA PROJECT #:
Company | [7 empty] | PROJECT
Email | [7 empty] | NAME:
Phone
PROJECT SCHEDULE | [6 empty] | UNIT INFO
| A. Notice to Proceed |  |  |  | C. First Residential Bldg "Placed In Service" |  |  | A. Number of Units
|  | Date: |  |  |  | Estimated Date: |  |  | New Construction:
[6 empty] | Actual Date: |  |  | Rehab Construction:
| B. Commencement |  |  |  | D. Substantial Completion (AIA Certif. of Sub. Compl.) |  |  |  | Total Units: | 0
|  | Date: |  |  |  | Estimated Date:
Actual Date:
*** DO NOT COMBINE THE STAGED SUBMISSION PACKAGES (maintain separate binders/flash drives per submission) ***
PLACE AN 'X' IN THE BOX NEXT TO EACH DOCUMENT SUBMITTED
DCA FINAL INSPECTION SUBMISSION (due when final retainage release pay app is issued)
Request For Final Construction Compliance Form
Final Inspection Fee ($3,000)
Certificates of Occupancy (COs)
DCA Placed In Service form
AIA G704 Certificate of Substantial Completion
Final Contractor Application & Certificate for Payment(s) (100% release of retainage)
Satisfactory completion of final accessibility inspection with confirmation of resolution of any outstanding issues stemming from the inspection
--include all site inspection reports performed by accessibility consultant (minimum three per QAP)
--include a letter from the Consultant or Architect stating all reported accessibility concerns have been resolved
DCA Amenities and Design Options Re-Certification
DCA Architectural Waivers/Project Concept Change approval forms
Other:
ARCHITECTURAL 8609 CLEARANCE SUBMISSION (due prior to final allocation of resources)
Green Building certifications (where applicable)
Verification from a qualified HERS rater that dwelling unit air infiltration rate meets or exceeds the QAP requirements
Radon Testing that demonstrates levels below the EPA recommended limits
--include a radon report from radon professional
--include a radon tests
Verification of compliance with each DCA Carryover Allocation "Condition of Funding" (Architectural Dept)
--provide a narrative that describes means of compliance with each Conditions of Funding (restate each C.o.F in the narrative)
--provide supporting docs/evidence as needed
Contractor Cost Certification (when there is an Identity of Interest between any Project Participant and the General Contractor)
a: Auditor opinion letter:
b: Certification of Independent Certified Public Accountant EXHIBIT B:
c: General Contractor Certification EXHIBIT C:
d: Multifamily Loan Contractors’ Cost Certification of Actual Project Costs EXHIBIT D:
e: Contractor’s Cost Certification EXHIBIT E:
i: Line item analysis and explanation EXHIBIT F:
ii: Complete change order log:
iii: A copy of all signed change orders:
iv: Complete subcontractor log:
Other:
OTHER SUBMISSIONS
Other:
Other:
Note on A21: 2011 QAP-CORE: Completion of Work Scope (9% TC): Owners of projects receiving Credits in the 2011 round for the "rehabilitation" of an existing property must perform 100% of the work scope in accordance with the original "physical needs assessment" submitted with the Application no later than December 31, 2013. Owners of properties receiving Credits for "new construction" in the 2011 round must perform "100% of the work scope" as set forth in the DCA approved construction drawings and specifications no later than December 31, 2013. DCA Final Inspection Submission: Package should be submitted to the attention of the DCA Construction Administration when Contractor is requesting release of retainage (final pay request).
Note on A25: DCA Final Inspection Submission: The submittal package should be submitted to the attention of the DCA Construction Administration when Contractor is requesting release of retainage (final pay request). 2012 Qualified Allocation Plan - Core - SECTION 10. POST AWARD DEADLINES: F. Completion of Work Scope. Owners of projects receiving Credits in the 2012 round for the rehabilitation of an existing property must perform 100% of the work scope in accordance with the original physical needs assessment submitted with the Application no later than December 31, 2014. Owners of properties receiving Credits for new construction in the 2012 round must perform 100% of the work scope as set forth in the DCA approved construction drawings and specifications no later than December 31, 2014. Certificates of Occupancy for the residential buildings must be issued by the local
Note on B27: F. Completion of Work Scope. Owners of projects receiving Credits or Letters of Determination in accordance with this QAP for the new construction and/or rehabilitation of an existing property must perform 100% of the DCA approved work scope no later than December 31, 2016. Certificates of Occupancy for the residential buildings must be issued by the local jurisdiction before end of business December 31, 2016. Temporary Certificates of Occupancy that prohibit occupancy will not be accepted to meet this requirement. DCA will inspect projects requesting IRS Form(s) 8609 to ensure that all work has been completed prior to issuing Form(s) 8609. If a lesser percentage is completed, DCA reserves the right to recapture all Credits allocated or disallow any credits. DCA may approve modifications to the proposed work scope upon written request.
Note on B28: 2014 QAP - EXHIBIT A - DCA APPLICATION AND PRE - AWARD DEADLINES & FEE SCHEDULE - Final Inspection Fee: Final Inspection Fee (for all LIHTC properties, both 4% and 9%, excluding those projects involving HOME funds) Fees: $3,000 per project 9% Deadline: Due within 30 days of final draw but no later than 30 days prior to the placed in service date or a late fee of $25 per day will be assessed 4% Deadline: Due within 30 days of final draw but no later than 30 days prior to the placed in service date or a late fee of $25 per day will be assessed Notes: Include original check as well as a copy of the check.
Note on B29: 2014 QAP - Architectural Manual - Architectural Standards: II. DESIGN SUBMITTALS AND CONSTRUCTION MONITORING - B. Building Permits: Building permits are required for all work to be funded under DCA programs. Proof of inspections and approvals by local officials, including Certificates of Occupancy, are required for final allocation of Low Income Housing Tax Credits (LIHTC). See Architectural Submittal Instructions and contact DCA LIHTC and HOME underwriters for specific information. 2014 QAP - EXHIBIT A - DCA POST AWARD DEADLINES AND FEE SCHEDULE - Certificates of Occupancy/Placement–In-Service: 9% Deadline: Issued by local jurisdiction/all buildings placed in service before end of business December 31, 2016 2014 QAP - CORE - F. Completion of Work Scope: Certificates of Occupancy for the residential buildings must be issued by the local jurisdiction before end of business December 31, 2016. Temporary Certificates of Occupancy that prohibit occupancy or condition occupancy will not be accepted to meet this requirement.
Note on B30: 2014 QAP - CORE - SECTION 14. POST AWARD DEADLINES - G. Placement-In-Service: Owners of projects receiving Credits in the 2013 round must place all buildings in the project in service by December 31, 2016. 9% Deadline Within 30 days of the 1st building placed in service
Note on B31: AIA G704 Certificate of Substantial Completion: Submit a copy of this AIA document and include a copy of any list of remaining "punch out items" that were referenced as part of the document.
Note on B32: Final Contractor Application & Certificate for Payment(s) (100% release of retainage): Submit a copy of this AIA document (and HUD pay app if applicable). Document should note all added Change Orders.
Note on B33: 2014 QAP - Threshold - XVIII. ACCESSIBILITY STANDARDS - C: Each project selected for allocation is required to retain a DCA qualified consultant to monitor the project for accessibility compliance. The consultants must perform a pre-construction plan review and inspect the project at least 3 times during construction to monitor grading operations, framing, and final compliance. DCA must be copied on all reviews/reports. This has been revised to a pre-construction plan review and inspect the project at least 2 times during construction to monitor grading operations / framing, and final compliance. The consultant must provide final clearance for the project.
Note on B36: DCA Amenities and Design Options Re-Certification: This form was originally submitted with the DCA pre-construction review documents. The document should be updated if needed (Project Concept Changes,,,) and resubmitted as part of the project closeout process.
Note on A40: DCA 8609 Clearance Submission: Package should be submitted to the attention of the DCA Construction Administration prior to the Owner's request for the 8609. 2012 Qualified Allocation Plan - Core - SECTION 10. POST AWARD DEADLINES: F. Completion of Work Scope. Owners of projects receiving Credits in the 2012 round for the rehabilitation of an existing property must perform 100% of the work scope in accordance with the original physical needs assessment submitted with the Application no later than December 31, 2014. Owners of properties receiving Credits for new construction in the 2012 round must perform 100% of the work scope as set forth in the DCA approved construction drawings and specifications no later than December 31, 2014. Certificates of Occupancy for the residential buildings must be issued by the local
Note on B42: 2014 QAP – Scoring - VI. SUSTAINABLE DEVELOPMENTS: Certification of the project’s compliance with a sustainable program that is utilized to claim points must be submitted at either the LIHTC final certification or HOME Loan final construction draw, whichever comes last. Failure to demonstrate a good faith effort to complete the certification may result in a finding of non-compliance and limited participation in further rounds. DCA will review proposed scoring sheets to determine that the Applicant has made a good faith effort to obtain the certification.
Note on B43: 2014 QAP - Threshold - XVII. BUILDING SUSTAINABILITY - B. Measured duct and building envelope leakage: Verification by certified HERS rater of a HVAC system duct leakage rate and dwelling unit air infiltration rate that meets or exceeds the Energy Star Qualified Homes, Version 3 National Program Requirements for the appropriate project specific climate zone (the duct leakage rate for all climate zones in Georgia is < 4 cfm/100 square feet; dwelling unit air infiltration rate to outdoors for climate zone 2 is an ACH 50 of 6 and for climate zones 3 and 4 is an ACH 50 of 5). Verification testing must follow the Energy Star testing protocol. If the project is not seeking a green building certification, test reports verifying compliance must be submitted at either the LIHTC final certification or HOME Loan final construction draw, whichever comes first. Projects that plan to utilize Packaged Terminal Air Conditioners (PTAC’s) or ductless mini-splits for all units are exempt from the duct leakage requirement.
Note on B44: Architectural Manual - Architectural Submittal Instructions - F. Documents due before final allocation of resources: 6. Radon testing that demonstrates levels below the EPA recommended limits 2014 QAP - Environmental Manual - B. Non-Scope Issues for Phase I Reports - 7. Radon Gas: a. If the Applicant’s project involves the renovation or use of an existing structure, a radon test must be performed to determine radon gas levels, unless an EPA approved short-term radon test has been performed in the lowest public areas of the building(s) within the last six months which demonstrated radon levels at or below 4 pci/l or 0.02 WL. A copy of the Radon Report should be attached to the Phase I Report. Any readings that exceed the EPA limits must mitigate radon levels are part of the work scope in accordance with ASTM E2121 - 08 Standard Practice for Installing Radon Mitigation Systems in Existing Low-Rise Residential Buildings. b. If the Applicant’s project involves new construction, the building(s) must be constructed in accordance with current EPA requirements for radon resistant construction techniques, including, but not limited to, ASTM E1465 - 08 Standard Practice for Radon Control Options for the Design and Construction of New Low-Rise Residential Buildings and the buildings must be tested for radon upon completion of construction. The Phase I Report must include statements to this effect in Section 5.4.21. c. The minimum requirement for testing locations is one test per every 2000 square feet of ground-contact units. However, radon concentrations can be highly localized and best practice for radon testing should involve a certified radon tester (http://www.radongas.org/ or http://www.nrsb.org/). In addition, it is recommended that at least one test be located in each building on each floor above the ground-contact level, covering a minimum of 10% of the units on all floors above the ground floor3
Note on B47: Conditions of Funding Compliance Narrative: Provide a narrative that includes evidence of compliance with each GHFA Carryover Allocation Conditions of Funding. Restate each "condition of funding" verbatim from the Carryover Allocation letter before each response describing method of compliance. Provide supporting docs/evidence as needed.
Note on B50: 2014 QAP - Exhibit A to Appendix I. - A. DCA Underwriting Policies - 11. Identity of Interest - Contractor: If there is an Identity of Interest between any participant in the Ownership entity and the contractor or the Developer and the contractor, a third party front-end analysis of the construction costs must be conducted. This has been deleted from the carryover and is no longer required for tax credit only projects. For HOME projects, the third-party review will be commissioned by DCA during the DCA underwriting period. For tax credit only projects, the qualifications of the proposed third-party reviewer must be submitted to DCA and approved before the review is conducted. Additionally, industry standards for such Owner-provided construction services shall be used to determine reasonableness for the services. DCA will require that a contractor cost certification be submitted where there is an identity of interest between any Project Participant and the General Contractor. The cost certification shall be prepared in accordance with the standards set forth for a HOME contractor cost certification. Subcontractor / Materialmen. Any Identity of Interest between any Project Participant or General Contractor and any subcontractors, other provider of service, materials, or supplies must be disclosed. Additional scrutiny will be given to subcontractor/materialmen costs where there is an identity of interest.

## 2014 4% PreCon
|  |  | GEORGIA DEPARTMENT OF COMMUNITY AFFAIRS |  |  |  |  | 4% TAX CREDIT & BOND
Office of Housing Finance and Development Division
Architectural Services Department
60 Executive Park South, NE, Atlanta, GA 30329-2231
2014 DESIGN & CONSTRUCTION - PRE CONSTRUCTION TRANSMITTAL (form date: 1.14.15)
OWNER/DEVELOPER CONTACT FOR DESIGN/CONSTRUCTION REVIEW | [8 empty] | DATE:
Name | [8 empty] | DCA PROJECT #:
Company | [7 empty] | PROJECT
Email | [7 empty] | NAME:
Phone
PROJECT DESCRIPTION
| A. | Unit Descriptions |  | # of units | E. | Square Footage
|  | New Construction |  |  |  | Total Net Residential Unit Square Footage
|  | Adaptive Reuse |  |  |  | Total Gross Building Conditioned Square Footage
|  | Rehab |  |  |  | Total Gross Building Covered Square Footage
Historic Rehab
| B. | Total Residential Units |  |  | F. | Buildings
|  | Common Space Units |  |  |  | Number of Residential Buildings
|  | Total Units |  | 0 |  | Number of Non-Residential Buildings
[6 empty] | Total Number of Buildings |  |  |  |  | 0
| C. | Unit mix
|  | describe # of bedrooms & baths in each unit |  |  | G. | Tenancy: | Family or Senior
[5 empty] | H. | Accessibility
[6 empty] | Mobility Impaired Units |  |  |  | at least 5% of total units
| D. | Acreage |  |  |  | list unit #s for mobility units
|  | Gross Acreage |  |  |  | Sight / Hearing Impaired Unit |  |  |  | at least 2% of total units
|  | Developed acreage |  |  |  | list unit #s for site/hearing impaired units
*** DO NOT COMBINE THE STAGED SUBMISSION PACKAGES (maintain separate binders/flash drives per submission) ***
PLACE AN 'X' IN THE BOX NEXT TO EACH DOCUMENT SUBMITTED
30 DAYS PRIOR SUBMISSION (due no later than 30 days prior to application submission)
Architectural Waivers & Amenities/Design Options Pre-Approval Requests
Other:
DCA REVIEW SUBMISSION (due with application submission- new const.; due after DCA review of work scope for rehabs)
DCA "Review Set" of drawings (plans) (see "Directions" for definition of "Review Set")
DCA "Review Set" of Project Manual (specs)
DCA Construction Document Log ("Review Set")
Accessibility Consultant Agreement (executed)
Boundary and Topographical Survey
Geotechnical Report (new construction only)
DCA Schedule of Values ("Review Set")
Federal Work Authorization (E-Verify) Affidavits (see DCA form)
Green Building Consultant Agreement (contracts and MOUs)
Other:
LOAN CLOSING / COMMENCEMENT SUBMISSION (due prior to construction loan closing)
DCA "Contract Set" of drawings and specifications
Updated DCA Construction Document Log (contract set)
Addendum incorporating/outlining revisions from DCA Review Set into the DCA Contract Set
Executed Owner/Contractor Agreement
Updated DCA Schedule of Values (contract set)
Notice to Proceed
Finalized construction schedule
Permits (Land Development, Building, etc.)
Other:

## 2014 4% ConstAdmin
|  |  |  | GEORGIA DEPARTMENT OF COMMUNITY AFFAIRS |  |  |  | 4% TAX CREDIT ONLY
Office of Housing Finance and Development
Architectural Services Department
60 Executive Park South, NE, Atlanta, GA 30329-2231
2014 DESIGN & CONSTRUCTION - CONSTRUCTION ADMINISTRATION TRANSMITTAL (form date: 1.14.15)
OWNER/DEVELOPER CONTACT CONSTRUCTION ADMINISTRATION | [8 empty] | DATE:
Name | [8 empty] | DCA PROJECT #:
Company | [7 empty] | PROJECT
Email | [7 empty] | NAME:
Phone
PROJECT SCHEDULE | [6 empty] | UNIT INFO
| A. Notice to Proceed |  |  |  | C. First Residential Bldg "Placed In Service" |  |  | A. Number of Units
|  | Date: |  |  |  | Estimated Date: |  |  | New Construction:
[6 empty] | Actual Date: |  |  | Rehab Construction:
| B. Commencement |  |  |  | D. Substantial Completion (AIA Certif. of Sub. Compl.) |  |  |  | Total Units: | 0
|  | Date: |  |  |  | Estimated Date:
Actual Date:
*** DO NOT COMBINE THE STAGED SUBMISSION PACKAGES (maintain separate binders/flash drives per submission) ***
PLACE AN 'X' IN THE BOX NEXT TO EACH DOCUMENT SUBMITTED
DCA FINAL INSPECTION SUBMISSION (due when final retainage release pay app is issued)
Request For Final Construction Compliance Form
Final Inspection Fee ($3,000)
Certificates of Occupancy (COs)
DCA Architectural Waivers/Project Concept Changes
DCA Placed In Service form
AIA G704 Certificate of Substantial Completion
Final Contractor Application & Certificate for Payment(s) (100% release of retainage)
Satisfactory completion of final accessibility inspection with confirmation of resolution of any outstanding issues stemming from the inspection
--include all site inspection reports performed by accessibility consultant (minimum three per QAP)
--include a letter from the Consultant or Architect stating all reported accessibility concerns have been resolved
DCA Amenities and Design Options Re-Certification
Other:
ARCHITECTURAL 8609 CLEARANCE SUBMISSION (due prior to final allocation of resources)
Green Building certifications (when applicable)
Verification from a qualified HERS rater that dwelling unit air infiltration rate meets or exceeds the QAP requirements (when project is "not seeking" a grn bldg cert.) certification
Radon Testing that demonstrates levels below the EPA recommended limits
--include a radon report from radon professional
--include a radon tests
Verification of compliance with each DCA Letter of Determination "Condition of Funding" (Architectural Dept)
--provide a narrative that describes means of compliance with each Conditions of Funding (restate each C.o.F in the narrative)
--provide supporting docs/evidence as needed
Contractor Cost Certification (when there is an Identity of Interest between any Project Participant and the General Contractor)
a: Auditor opinion letter:
b: Certification of Independent Certified Public Accountant EXHIBIT B:
c: General Contractor Certification EXHIBIT C:
d: Multifamily Loan Contractors’ Cost Certification of Actual Project Costs EXHIBIT D:
e: Contractor’s Cost Certification EXHIBIT E:
i: Line item analysis and explanation EXHIBIT F:
ii: Complete change order log:
iii: A copy of all signed change orders:
iv: Complete subcontractor log:
Other:
OTHER SUBMISSIONS
Other:
Other:
Note on A25: DCA Final Inspection Submission: The submittal package should be submitted to the attention of the DCA Construction Administration when Contractor is requesting release of retainage (final pay request). 2014 QAP THRESHOLD-XVII. SECTION 14. POST AWARD DEADLINES: F. Completion of Work Scope: Owners of projects receiving Credits or Letters of Determination in accordance with this QAP for the new construction and/or rehabilitation of an existing property must perform 100% of the DCA approved work scope no later than December 31, 2016. Certificates of Occupancy for the residential buildings must be issued by the local jurisdiction before end of business December 31, 2016. Temporary Certificates of Occupancy that prohibit occupancy will not be accepted to meet this requirement. DCA will inspect projects requesting IRS Form(s) 8609 to ensure that all work has been completed prior to issuing Form(s) 8609. If a lesser percentage is completed, DCA reserves the right to recapture all Credits allocated or disallow any credits. DCA may approve modifications to the proposed work scope upon written request.
Note on B27: 2014 QAP-CORE: SECTION 14. POST AWARD DEADLINES F. Completion of Work Scope.* Owners of projects receiving Credits or Letters of Determination in accordance with this QAP for the new construction and/or rehabilitation of an existing property must perform 100% of the DCA approved work scope no later than December 31, 2016. Certificates of Occupancy for the residential buildings must be issued by the local jurisdiction before end of business December 31, 2016. Temporary Certificates of Occupancy that prohibit occupancy will not be accepted to meet this requirement. DCA will inspect projects requesting IRS Form(s) 8609 to ensure that all work has been completed prior to issuing Form(s) 8609. If a lesser percentage is completed, DCA reserves the right to recapture all Credits allocated or disallow any credits. DCA may approve modifications to the proposed work scope upon written request.
Note on B28: 2014 State of Georgia Qualified Allocation Plan-EXHIBIT A Final Inspection Fee (for all LIHTC properties, both 4% and 9%, excluding those projects involving HOME funds): $3,000 per 9% Deadline Due within 30 days of final draw but no later than 30 days prior to the placed in service date or a late fee of $25 per day will be assessed 4% Deadline Due within 30 days of final draw but no later than 30 days prior to the placed in service date or a late fee of $25 per day will be assessed NOTE: Include a copy of the check
Note on B29: 2014 Architectural Manual - Architectural Submittal Instructions - G. Documents due before final allocation of resources: Certificates of Occupancy allowing immediate use of buildings and units prior to or on the application deadline. To meet IRS and DCA requirements, and in jurisdictions not issuing Certificates of Occupancy, the Owner shall obtain from the authority having jurisdiction a letter affirming that the property meets all code requirements; 2014 QAP-CORE: SECTION 14. POST AWARD DEADLINES - F. Completion of Work Scope. Certificates of Occupancy for the residential buildings must be issued by the local jurisdiction before end of business December 31, 2016. Temporary Certificates of Occupancy that prohibit occupancy will not be accepted to meet this requirement.
Note on B31: 2014 QAP-CORE: SECTION 14. POST AWARD DEADLINES - G. Placement-In-Service. Owners of projects receiving Credits or Letter of Determination in accordance with this QAP must place all buildings in the project in service by December 31, 2016. DCA may pre-approve in writing, on a case by case basis, limited extension requests for 4% credit projects or projects receiving credits from the 2015 credit ceiling. 2014 Qualified Allocation Plan - Core EXHIBIT A DCA Placed In Service Form Fees NONE 9% Deadline Within 30 days of the 1st building placed in service 4% Deadline Within 30 days of the 1st building placed in service
Note on B32: AIA G704 Certificate of Substantial Completion: Submit a copy of this AIA document and include a copy of any list of remaining "punch out items" that were referenced as part of the document.
Note on B33: Final Contractor Application & Certificate for Payment(s): Application(s) should show 100% release of retainage and should list each Change Order
Note on B34: 2014 QAP-Threshold-XVIII. ACCESSIBILITY STANDARDS : C. Each project selected for allocation is required to retain a "DCA Qualified" consultant to monitor the project for accessibility compliance. The consultants must perform a pre-construction plan review and inspect the project at least 3 times during construction to monitor grading operations, framing, and final compliance. DCA must be copied on all reviews/reports. The qualified consultant shall not have an identity of interest with any entity on the Part II Development Team tab in the core application. This has been revised to a pre-construction plan review and inspect the project at least 2 times during construction to monitor grading operations / framing, and final compliance. The consultant must provide final clearance for the project.
Note on B37: DCA Amenities and Design Options Re-Certification: This form should be completed to reflect the Threshold items which the team noted in their application. The document should also reflect any project changes that may have occurred since the award (Project Concept Changes, etc.).
Note on A40: DCA 8609 Clearance Submission: The submission package should be submitted to the attention of the DCA Construction Administration prior to the Owner's request for the 8609. 2014 QAP THRESHOLD-XVII. SECTION 14. POST AWARD DEADLINES: F. Completion of Work Scope: Owners of projects receiving Credits or Letters of Determination in accordance with this QAP for the new construction and/or rehabilitation of an existing property must perform 100% of the DCA approved work scope no later than December 31, 2016. Certificates of Occupancy for the residential buildings must be issued by the local jurisdiction before end of business December 31, 2016. Temporary Certificates of Occupancy that prohibit occupancy will not be accepted to meet this requirement. DCA will inspect projects requesting IRS Form(s) 8609 to ensure that all work has been completed prior to issuing Form(s) 8609. If a lesser percentage is completed, DCA reserves the right to recapture all Credits allocated or disallow any credits. DCA may approve modifications to the proposed work scope upon written request.
Note on B42: 2014 QAP THRESHOLD - XVII. BUILDING SUSTAINABILITY: All completed properties must achieve a minimum standard for energy efficiency and sustainable building practices. At minimum, all units at all projects must comply with the following. (Historic properties may apply for an exemption when compliance means loss of historic character-defining features and finishes). 2014 QAP - Scoring - VI. SUSTAINABLE DEVELOPMENTS: Certification of the project’s compliance with a sustainable program that is utilized to claim points must be submitted at either the LIHTC final certification or HOME Loan final construction draw, whichever comes last. Failure to demonstrate a good faith effort to complete the certification may result in a finding of non-compliance and limited participation in further rounds. DCA will review proposed scoring sheets to determine that the Applicant has made a good faith effort to obtain the certification.
Note on B43: 2014 QAP THRESHOLD-XVII. BUILDING SUSTAINABILITY: All completed properties must achieve a minimum standard for energy efficiency and sustainable building practices. At minimum, all units at all projects must comply with the following. (Historic properties may apply for an exemption when compliance means loss of historic character-defining features and finishes). B. Measured duct and building envelope leakage. Verification by certified HERS rater of a HVAC system duct leakage rate and dwelling unit air infiltration rate that meets or exceeds the Energy Star Qualified Homes, Version 3 National Program Requirements for the appropriate project specific climate zone (the duct leakage rate for all climate zones in Georgia is < 4 cfm/100 square feet; dwelling unit air infiltration rate to outdoors for climate zone 2 is an ACH 50 of 6 and for climate zones 3 and 4 is an ACH 50 of 5). Verification testing must follow the Energy Star testing protocol. If the project is not seeking a green building certification, test reports verifying compliance must be submitted at either the LIHTC final certification or HOME Loan final construction draw, whichever comes first. Projects that plan to utilize Packaged Terminal Air Conditioners (PTAC’s) or ductless mini-splits for all units are exempt from the duct leakage requirement.
Note on B44: 2014 Architectural Manual - G. Documents due before final allocation of resources: 6. Radon testing that demonstrates levels below the EPA recommended limits 2014 Environmental Manual: B. Non-Scope Issues for Phase I Reports - 7. Radon Gas: a. If the Applicant’s project involves the renovation or use of an existing structure, a radon test must be performed to determine radon gas levels, unless an EPA approved short-term radon test has been performed in the lowest public areas of the building(s) within the last six months which demonstrated radon levels at or below 4 pci/l or 0.02 WL. A copy of the Radon Report should be attached to the Phase I Report. Any readings that exceed the EPA limits must mitigate radon levels are part of the work scope in accordance with ASTM E2121 - 13 Standard Practice for Installing Radon Mitigation Systems in Existing Low-Rise Residential Buildings. b. If the Applicant’s project involves new construction, the building(s) must be constructed in accordance with current EPA requirements for radon resistant construction techniques, including, but not limited to, ASTM E1465 - 08 Standard Practice for Radon Control Options for the Design and Construction of New Low-Rise Residential Buildings and the buildings must be tested for radon upon completion of construction. The Phase I Report must include statements to this effect in Section 5.4.21. c. The minimum requirement for testing locations is one test per every 2000 square feet of ground-contact units. However, radon concentrations can be highly localized and best practice for radon testing should involve a certified radon tester (http://www.radongas.org/ or http://www.nrsb.org/). In addition, it is recommended that at least one test be located in each building on each floor above the ground-contact level, covering a minimum of 10% of the units on all floors above the ground floor.
Note on B47: Conditions of Funding Compliance Narrative: Provide a narrative that includes evidence of compliance with each GADCA "Letter of Determination" Conditions of Funding. Restate each "condition of funding" verbatim from the Letter of Determination letter before each response describing method of compliance. Provide supporting docs/evidence as needed.
Note on B50: 2014 QAP-Core: Exhibit A to Appendix I: DCA UNDERWRITING POLICIES - 11. Identity of Interest. DCA will require that a contractor cost certification be submitted where there is an identity of interest between any "project participant" and the "general contractor". The cost certification shall be prepared in accordance with the standards set forth for a HOME contractor cost certification “Project Participants” mean the Owner, Developer, Management Company, Consultants and Syndicator for a project for which an Application is submitted. Contractor: If there is an Identity of Interest between any participant in the Ownership entity and the contractor or the Developer and the contractor, a third party front-end analysis of the construction costs must be conducted. This has been deleted from the carryover and is no longer required for tax credit only projects. For HOME projects, the third-party review will be commissioned by DCA during the DCA underwriting period. For tax credit only projects, the qualifications of the proposed third-party reviewer must be submitted to DCA and approved before the review is conducted. Additionally, industry standards for such Owner-provided construction services shall be used to determine reasonableness for the services. DCA will require that a contractor cost certification be submitted where there is an identity of interest between any Project Participant and the General Contractor. The cost certification shall be prepared in accordance with the standards set forth for a HOME contractor cost certification. Subcontractor / Materialmen. Any Identity of Interest between any Project Participant or General Contractor and any subcontractors, other provider of service, materials, or supplies must be disclosed. Additional scrutiny will be given to subcontractor/materialmen costs where there is an identity of interest.