## Instructions
Georgia Department of Community Affairs
Office of Housing and Finance
Construction Services Dept.
2016 DCA CONSTRUCTION SERVICES SUBMISSION INSTRUCTIONS
|  | Form Date: | 06.20.2017
Overview
In order to ensure compliance with Georgia DCA’s Architectural Standards for safe, decent, affordable housing, DCA monitors the design and construction of all projects awarded tax credits and/or HOME funds. As such, the project team is required to submit documents to DCA throughout the design and construction process for review, which is accomplished through the Construction Services Department's defined staged submission process.
Each Construction Services (CS) submission comprises of a binder and flash drive which contain both hard and soft copies of the documents required for that submission. The flash drive must contain the appropriate 2016 DCA Construction Services Submittal Folder structure, with the applicable files placed inside of the appropriate subfolders. For the binder, hard copies will be limited to the completed DCA CS transmittal form, project team transmittals/cover letters and as well as original DCA payments/checks when required. When required, the hard copies of the drawings (plans) and project manual (specs) are to be included separate from the binder. The program specific DCA CS transmittals included in this Excel workbook provides the outline as to what is to be included with each required CS submission. Additional information is provided in the Architectural Manual and the DCA award notices. Note: Do NOT combine multiple staged CS submissions into one binder and one flash drive (maintain separate binders/flash drives for each staged submission package).
Due Dates
Each program specific DCA CS Transmittal form provides the due dates for each required program submission Note: It is the responsibility of the Owner/Developer to request any necessary extensions.
Complete submission packages may be submitted earlier than the due dates but documents should not be submitted piecemeal or from multiple sources (i.e. the plans and specs should NOT be submitted separately by the design firm). DCA will not begin its review until all documents required for a particular submission have been received.
Extension Requests
For unforeseen circumstances, the project team may submit a formal extension request to DCA for consideration. All construction related extension requests must be submitted in writing to:
Donna Tyler, Multifamily Construction Service Manager Donna.Tyler@dca.ga.gov (404) 679-3117
Note: Any DCA approved submission extension request does NOT extend any other deadlines, in particular, the 10% test.
DCA Construction Services Transmittal forms
Each CS staged submission must be accompanied by the proper "program specific" 2016 DCA Construction Services Transmittal form which are included in this Excel workbook and listed below:
• 2016 HOME Construction Services Transmittal
• 2016 9% LIHTC Construction Services Transmittal
• 2016 4% LIHTC Construction Services Transmittal
• 2016 HOME NOFA Construction Services Transmittal
In addition to providing submission due dates, the CS transmittal forms also provide an outline of the documents required for each staged submission.
DCA Construction Services Forms
The CS forms and folder structure that are required as part of the staged submissions are listed below and are available on the Construction Services website page at the following link:
http://www.dca.ga.gov/housing/housingdevelopment/programs/architecturaldesignandconstruction.asp
• 2016 DCA Construction Services Transmittal form (Excel)
• 2016 DCA Schedule of Values form (Excel)
• 2016 DCA Amenities & Design Options Re‐Certification form (Excel)
• 2016 DCA Construction Document Log (Excel)
• E‐verify affidavits (owner, developer & contractor) (Excel)
• 2016 DCA Construction Services Submittal Folder (zipped folder)
Note: The completed electronic copies must be provided in DCA's original file type format (i.e. Excel file in lieu of converting to PDF).
Paper Submission Requirements
Submit one hard cover binder ("1/2” wide spine) that contains copies of the completed DCA CS transmittal form and any applicable project team transmittals/cover letters, as well as DCA payments/checks when required (i.e. final inspection fees,,,). The binder must be clearly labeled with the DCA project number, project name and submission type located on both the front cover and spine areas. The binder should have plastic insert sleeves on the cover and spine areas. Note: Do NOT include plans and specs in the binder.
All drawing sheets (plans) must be printed in DCA's standard archive size of 12x18 (scalable format preferred). There should be one complete bound plan set with one common cover sheet that identifies ALL of the project drawings Note: Civil drawings should NOT be included separate from the main plan set.
The Project Manual (specs) should be soft bound with double sided printing.
The DCA project number and project name should be prominently displayed on the cover of both the Drawings and Project Manual (specs) and should identify that it is either the “DCA Review Set” or the “DCA Contract Set”.
Electronic Submission Requirements
For each required CS submission provide one "virus-free" USB flash drive that contains enough storage space so that DCA may add additional documents to the drive as needed. The flash drive should contain an external identifying label/tag and "leash". A clear 2-3 ring plastic “zip lock” type pouch insert should be included inside the binder front area to contain the flash drive. Note: Do NOT email these files.
The flash drive must contain the appropriate 2016 DCA Construction Services Submittal Folder, with the applicable files placed inside of the appropriate subfolders. For the provided drawings folder, add additional subfolders for each discipline (i.e. Architectural, Structure, Electrical,,,) and note the sheet number on each file extension. The project manual is typically provided as a single PDF file but may be subdivided as long as it is organized.
The last section on the DCA CS Transmittal form titled "Other" should be used for additional documents submitted by the project team such as cover letters/internal transmittal forms.
The file extension names should be short as possible and NOT contain special characters (i.e.. $, &, #, %, *, / , \, etc.). All DCA forms should be submitted using the original file format (i.e. don't convert an Excel file type to a PDF).
Additional Submission Instructions
• Double‐check the flash drive folders for “junk files” that have been added by software or other non Windows operating systems and remove as needed.
• PDF files should have the ability to be searched or edited where feasible
• Electronic drawing file extensions must be labeled at minimum with the drawing page number which corresponds to the DCA Construction Document Log.
• Only one project submission should be included per flash drive and binder (do NOT combine submissions)
• Copies of all submitted paper documents should be included in the flash drive, including any delivery cover letters.
Definitions
• DCA Review Set:
The set of Construction Documents (CDs) that will be submitted to the local building authority for review in order to obtain the permit for construction. These CDs would be expected to be at least 90% complete.
• DCA Contract Set:
The set of Construction Documents (CDs) that are incorporated into the executed Owner/Contractor Agreement. These CDs would be expected to be 100% complete and should have incorporated the local building authority comments from the permitting process as well as comments from the syndicator/lender review, DCA review, accessibility consultant review, and all other consultant's design review comments (green building, historic preservation, etc.).
Note: If special circumstances arise where NOT all of the review comments/revisions are incorporated into the Contract Set at the time of the execution of the Owner/Contractor Agreement and will be incorporated into the Construction Documents at a later date (i.e. Change Order), then the Architect should provide a document identifying the missing elements.
• DCA Contract Set Addendum (HOME projects only):
The Architect's contract document that identifies the revisions/additions that have occurred between the originally submitted DCA Review Set and the final DCA Contract Set (i.e.. design changes/completion, third party and municipality comments, etc.).
Identities of Interest
If there is an Identity of Interest between any Project Participant and the Contractor or the Developer and the Contractor, a third party front-end analysis of the construction costs must be conducted.
For HOME projects, the third‐party cost review will be engaged by DCA upon submittal and approval of the DCA Schedule of Values.
For Tax Credit only projects, the qualifications of the proposed third‐party cost reviewer must be submitted to DCA and approved before the review is conducted (see DCA CS Transmittal form for procedures). Once a firm is qualified for one project, it will be qualified for all 2016 round projects. Approval for any prior funding rounds does NOT constitute approval for the 2016 round.
The required qualifications are as follows:
• The consulting firm must have completed three (3) or more Architecture/Engineering Reviews and Cost Estimate Reviews for lenders pursuant to the HUD MAP (multifamily accelerated processing) program for the Atlanta Multifamily Hub since 2008
• Consideration may be given to firms that have similar experience with other HUD Multifamily Hub offices.
• Consideration will also be given to firms that have prepared a review for a project that has HUD funding in conjunction with Low Income Housing Tax Credits.
Requests for consideration must contain, at minimum:
The qualification package must contain, at minimum:
• Resumes of firm team members that will conduct the review;
• Description of relevant past work conducting architecture/engineering reviews and cost estimate reviews for HUD and Low Income Housing Tax Credit projects (project list);
• A (sample) copy of a cost estimate review performed for the HUD MAP program.
Mailing Instructions
Please deliver all submissions to:
Georgia Department of Community Affairs Multifamily Construction Services Department Attn: Administration 60 Executive Park South NE Atlanta, Georgia 30329‐2231

## 2016 9 Pct
GEORGIA DEPARTMENT OF COMMUNITY AFFAIRS | [9 empty] | 9% TAX CREDIT ONLY
Office of Housing Finance & Development
Construction Services Department
60 Executive Park South, NE, Atlanta, GA 30329-2231
2016 DCA CONSTRUCTION SERVICES TRANSMITTAL | [11 empty] | Form Date: | 06.20.2017
|  | DCA PROJECT #: |  | (2016-000) | [6 empty] | DATE:
PROJECT NAME:
DEVELOPER CONTACT | [8 empty] | BUILDING SCHEDULE
| Company: | [7 empty] | Residential Buildings
| Name: | [7 empty] | #Bldgs. | Bldg. Type |  | Conditioned SF | Covered SF
Email:
Phone:
PROJECT TEAM
Architect:
Contractor:
|  |  |  | Identity of Interest?: |  |  |  | Total: | 0 |  |  | 0 | 0
| Accessibility: | [7 empty] | Accessory Buildings (non-residential)
[9 empty] | #Bldgs. | Bldg. Type |  | Conditioned SF | Covered SF
PROPERTY ADDRESS
Street:
| City: |  |  | ZIP:
| County: | [6 empty] | Total: | 0 |  |  | 0 | 0
| Geo Coord: | Latitude: |  | Longitude
|  |  | (00.000000) |  | (00.000000) |  |  |  |  | UNIT SCHEDULE
PROJECT DESCRIPTION | [9 empty] | Residential Units
|  |  | Scattered Site?: | [6 empty] | #Units | #Bedrms. | #Bathrms. | Total Net SF
|  |  | If Yes, How Many Properties?: | [10 empty] | 0
0
|  |  | Tenancy1: | [10 empty] | 0
|  |  | Tenancy2: | [10 empty] | 0
0
|  |  | Constr. Type1: | [10 empty] | 0
|  |  | Constr. Type2: | [5 empty] | Total: | 0 | 0 |  | 0 | 0 | # of bedrms.
Accessibility Units
|  |  | Acreage: | [6 empty] | Total # of Mobility Impaired Units:
# of M.I. Units With "Roll-in Showers":
PROJECT SCHEDULE | [9 empty] | # of Sight / Hearing Impaired Units:
Notice to Proceed
|  |  | Estimated Date: |  |  |  | HARD COSTS
|  |  | Actual Date: |  |  |  | Description |  |  |  | Award | Due Dill. | Final Alloc.
Contractor Hard Costs:
|  |  |  | Placed in Service |  |  | Other Construction Hard Cost:
|  |  | DCA "Expected" PIS Date: |  |  |  | Construction Contingency:
|  |  | Last Residential Bldg. "Actual" PIS Date: | [6 empty] | Total Hard Costs: | 0 | 0 | 0
|  |  |  | Substantial Completion |  |  | Cost Per Unit Net SF: |  |  |  | #DIV/0! | #DIV/0! | #DIV/0!
|  |  | Estimated Date: |  |  |  | Cost Per Unit: |  |  |  | #DIV/0! | #DIV/0! | #DIV/0!
|  |  | Actual Date: |  |  |  | Cost Per Bedrm.: |  |  |  | #DIV/0! | #DIV/0! | #DIV/0!
*** DO NOT COMBINE THE STAGED SUBMISSION PACKAGES (maintain separate binders/flash drives per submission) ***
PLACE AN 'X' IN THE BOX NEXT TO EACH DOCUMENT SUBMITTED
60 DAY SUBMISSION (due no later than 60 days after announcement of awards; or no later than March 1, 2017)
01 | Boundary Survey (including topographical data)
02 | Geotechnical Report (new construction only)
03 | Accessibility Consultant Agreement
04 | Contractor and Subcontractor Accessibility Training Sessions Action Plan (submit a document that states how this will be accomplished)
05 | Green Building Consultant Agreement - "when applicable" (agreement/proposal/MOUs)
06 | Qualifications for 3rd party cost reviewer (ONLY contractor identity of interest)
07 | DCA Amenities & Design Options Re-Certification form
08 | DCA Approved Architectural Waivers/Optional Amenities (including evidence of DCA approval)
09 | Other:
DCA#: |  | 0 |  |  |  | Program: | 9 Percent |  |  |  |  | Page: | 01 of 02
COMMENCEMENT SUBMISSION (due within 30 days of construction commencement; and no later than November 30, 2017)
01 | DCA Construction Document Log (Contract Set) (drawing log)
02 | DCA "Contract Set" of drawings (plans) (see directions for definition of "Contract Set")
03 | DCA "Contract Set" of Project Manual (specs)
04 | DCA Amenities & Design Options Re-Certification form
05 | Accessibility Consultant Plan Review Comments
06 | Accessibility Consultant Clearance Letter (acknowledgement of plan review comment resolutions)
07 | DCA Schedule of Values form (Contract Set)
08 | Front-End Third Party Cost Review for "Identity of Interest" (see QAP for definition of I of I)
09 | Owner/Contractor Agreement - Executed
10 | Narrative that identifies each Carryover Allocation Letter "Assumptions & Conditions" and provides a status update of each condition (Constr Srvcs Dept items)
(ex.: wetlands delineations, noise mitigation plans, etc.) (restate each C.o.F in the narrative)
11 | Notice to Proceed
12 | Construction Schedule - Finalized
13 | Permits (Land Development, Building,,,)
14 | DCA Approved Architectural Waivers/Optional Amenities (including evidence of DCA approval)
15 | DCA Placed in Service form - Draft with estimated dates (DCA Compliance Dept. form)
16 | Other:
DCA FINAL INSPECTION SUBMISSION (due within 30 days of the final retainage draw certified date)
01 | Request For Final Construction Compliance Form
02 | Final Inspection Fee ($3,000)
03 | Certificates of Occupancy (COs)
04 | AIA G704 Certificate of Substantial Completion
05 | Final Contractor Application & Certificate for Payment(s) (100% release of retainage)
06 | Copies of all Change Orders (including support docs included with approved Change Order)
07 | Confirmation of Contractor and Subcontractor Accessibility Training Sessions (minimum two sessions)
08 | Copies of all site inspection reports performed by the Accessibility Consultant (minimum two rpts. per QAP)
09 | Clearance letter from the Accessibility Consultant stating all reported accessibility concerns have been resolved
10 | DCA Amenities & Design Options Re-Certification form
11 | DCA Approved Architectural Waivers/Optional Amenities (including evidence of DCA approval)
12 | DCA Placed in Service form (DCA Compliance Dept. form)
13 | Other:
CONSTRUCTION 8609 CLEARANCE SUBMISSION (due prior to final allocation of resources which is due no later than September 30, 2019)
01 | Green Building certifications (where applicable)
02 | Verification from a HERS rater that dwelling unit air infiltration rate meets or exceeds the QAP
03 | Radon Testing that demonstrates levels below the EPA recommended limits
--include a radon report from radon professional
--include a radon tests
04 | Verification of compliance with each DCA Carryover Allocation "Condition of Funding" (Item# 10, 12 & 13)
--provide a narrative that describes means of compliance with each Conditions of Funding (restate each C.o.F in the narrative)
--provide supporting docs/evidence as needed
05 | Contractor Cost Certification (when there is an Identity of Interest between any Project Participant and the General Contractor)
a: Auditor opinion letter:
b: Certification of Independent Certified Public Accountant EXHIBIT B:
c: General Contractor Certification EXHIBIT C:
d: Multifamily Loan Contractors’ Cost Certification of Actual Project Costs EXHIBIT D:
e: Contractor’s Cost Certification EXHIBIT E:
i: Line item analysis and explanation EXHIBIT F:
ii: Complete change order log:
iii: A copy of all signed change orders:
iv: Complete subcontractor log:
06 | DCA Approved Architectural Waivers/Optional Amenities (including evidence of DCA approval)
07 | DCA Approved Project Concept Changes (including evidence of DCA approval)
08 | Other:
OTHER SUBMISSIONS
01 | Other:
02 | Other:
DCA#: |  | 0 |  |  |  | Program: | 9 Percent |  |  |  |  | Page: | 02 of 02
Note on A12: DEVELOPER CONTACT FOR DCA CONSTRUCTION SERVICES DEPT.
Note on N14: Note: Gross Building "Conditioned" Square Footage
Note on O14: Note: Gross Building "Covered" Square Footage
Note on N23: Note: Gross Building "Conditioned" Square Footage
Note on O23: Note: Gross Building "Covered" Square Footage
Note on O31: 2016 Architectural Standards - V. BUILDING INTERIORS DESIGN STANDARDS - B. Unit Sizes: Net Rentable (Leasable) Square Footage: This is the DCA definition for calculating “Residential Unit Square Footage” as it pertains to the Architectural Manual and other documents in Qualified Allocation Plan (QAP). It is calculated for each individual dwelling type. The unit net rentable area is measured from the inside face of each of the unit’s perimeter walls. • Net area included air-conditioned space only. • Measure from the inside (paint) face of all unit perimeter walls. • Do not include any patio, balcony, or breezeway areas. • Do not include any outside storage closets. • Do not deduct any interior walls. • Include non-revenue units in total net rentable living area (Total Residential Unit Square Footage)
Note on O40: 2016 Qualified Allocation Plan - Threshold XVIII. ACCESSIBILITY STANDARDS B. Regardless of whether a project anticipates using federal HOME funds as a funding source, all proposed projects must include the following DCA requirements: 1. At least 5% of the total units (but no less than one unit) must be equipped for the mobility disabled, including wheelchair restricted residents. Roll-in showers must be incorporated into 40% of the mobility equipped units (but no fewer than one unit); and 2. At least an additional 2% of the total units (but no less than one unit) must be equipped for hearing and sight-impaired residents. The same unit cannot be used to satisfy the 5% and 2% requirement. Preservation of existing affordable housing that cannot be modified to meet accessibility requirements that are not required by law, may request a DCA waiver.
Note on O41: 2016 Qualified Allocation Plan - Threshold XVIII. ACCESSIBILITY STANDARDS B. Regardless of whether a project anticipates using federal HOME funds as a funding source, all proposed projects must include the following DCA requirements: 1. At least 5% of the total units (but no less than one unit) must be equipped for the mobility disabled, including wheelchair restricted residents. Roll-in showers must be incorporated into 40% of the mobility equipped units (but no fewer than one unit); and 2. At least an additional 2% of the total units (but no less than one unit) must be equipped for hearing and sight-impaired residents. The same unit cannot be used to satisfy the 5% and 2% requirement. Preservation of existing affordable housing that cannot be modified to meet accessibility requirements that are not required by law, may request a DCA waiver.
Note on O42: 2016 Qualified Allocation Plan - Threshold XVIII. ACCESSIBILITY STANDARDS B. Regardless of whether a project anticipates using federal HOME funds as a funding source, all proposed projects must include the following DCA requirements: 1. At least 5% of the total units (but no less than one unit) must be equipped for the mobility disabled, including wheelchair restricted residents. Roll-in showers must be incorporated into 40% of the mobility equipped units (but no fewer than one unit); and 2. At least an additional 2% of the total units (but no less than one unit) must be equipped for hearing and sight-impaired residents. The same unit cannot be used to satisfy the 5% and 2% requirement. Preservation of existing affordable housing that cannot be modified to meet accessibility requirements that are not required by law, may request a DCA waiver.
Note on M45: Note: Cost amounts on application
Note on N45: Due Diligence: Cost amounts at time of Construction Loan Closing (Owner/Contractor agreement, etc.) Enter data with Commencement submission.
Note on O45: Final Allocation: Final Construction Hard Cost amounts (Change Orders, etc.) Enter data with Architectural 8609 submission.
Note on E48: Note: The "Expected Placed In Service" date is from the DCA generated "Exhibit A: Building Designation" which is an exhibit to the Carryover Letter for projects receiving tax credits.
Note on F51: Note: The date for the "AIA G704 Certificate of Substantial Completion"
Note on B58: 2016 QAP - Core - SECTION 16 - POST AWARD DEADLINES - A. Construction Documents: 1. Construction Documents: For 9% deals, including those utilizing DCA HOME funds, a boundary survey, topographic survey, and geotechnical soils boring report must be submitted to DCA for review and approval no later than 60 days after announcement of awards. Additional Construction Documents will need to be submitted according to Post Award Deadlines and Fees Schedule.
Note on B62: 2016 QAP - Threshold - XVIII. ACCESSIBILITY STANDARDS : C. Each project selected for allocation is required to retain a "DCA Qualified" consultant to monitor the project for accessibility compliance. The Consultant cannot be a member of the proposed Project Team nor have an Identify of Interest with any member of the proposed Project Team. The DCA qualified consultant must perform the following: (1) a pre-construction plan and specification review to determine that the proposed property will meet all required accessibility requirements. The Consultant report must be included with the Step 2 construction documents submitted to DCA. At a minimum, the report will include the initial comments from the consultant, all documents related to resolution of identified accessibility issues and a certification from the consultant that the plans appear to meet all accessibility requirements. (2) provided at least two training sessions to the General Contractor and Subcontractors regarding accessibility requirements. One training must be on site. (3) an inspection of the construction site after framing is completed to determine that the property is following the approved plans and specifications as to accessibility. DCA must receive a copy of the report issued by the consultant as well as documentation that all issues, if any, have been resolved. (4) a final inspection of the property after completion of construction to determine that the property has been constructed in accordance with all accessibility requirements. DCA must receive a copy of the report issued by the consultant as well as documentation that all issues, if any, have been resolved prior to submission of the project cost certification.
Note on B63: 2016 QAP - Threshold Criteria: XVIII. ACCESSIBILITY STANDARDS: (2) provided at least two training sessions to the General Contractor and Subcontractors regarding accessibility requirements. One training must be on site.
Note on B73: 2016 QAP - Core- EXHIBIT A - DCA POST AWARD DEADLINES AND FEE SCHEDULE Commencement of Construction/Rehabilitation (Tax Credit Only Projects) 4% Deadline: No later than October 31, 2017 (per award letter)
Note on B79: 2016 QAP - Threshold - XVIII. ACCESSIBILITY STANDARDS : The DCA qualified consultant must perform the following: (1) a pre-construction plan and specification review to determine that the proposed property will meet all required accessibility requirements. The Consultant report must be included with the Step 2 construction documents submitted to DCA. At a minimum, the report will include the initial comments from the consultant, all documents related to resolution of identified accessibility issues and a certification from the consultant that the plans appear to meet all accessibility requirements.
Note on B84: Assumptions & Conditions Status Update Narrative: Provide a narrative that identifies each GHFA Letter of Determination "Assumptions & Conditions" of Funding section and provides a status update of each condition. Restate each "Assumptions & Conditions" verbatim from the Letter of Determination before each response. Note: - Only need to respond to items related to the Construction Services Department requirements
Note on B93: DCA Final Inspection Submission: The submittal package should be submitted to the attention of the DCA Construction Administration when Contractor is requesting release of retainage (final pay app request). 2016 QAP -Core- SECTION 16. POST AWARD DEADLINES: G. Completion of Work Scope: Owners of projects receiving Credits or Letters of Determination in accordance with this QAP for the new construction and/or rehabilitation of an existing property must perform 100% of the DCA approved work scope no later than December 31, 2018. Certificates of Occupancy for the residential buildings must be issued by the local jurisdiction before end of business December 31, 2018. Temporary Certificates of Occupancy that prohibit occupancy will not be accepted to meet this requirement. DCA will inspect projects requesting IRS Form(s) 8609 to ensure that all work has been completed prior to issuing Form(s) 8609. If a lesser percentage is completed, DCA reserves the right to recapture all Credits allocated or disallow any credits. DCA may approve modifications to the proposed work scope upon written request.
Note on B95: 2016 QAP - Core - EXHIBIT A - DCA POST AWARD DEADLINES AND FEE SCHEDULE -Completion of Work Scope 4% Deadline: No later than December 31, 2018 G. Completion of Work Scope. Owners of projects receiving Credits or Letters of Determination in accordance with this QAP for the new construction and/or rehabilitation of an existing property must perform 100% of the DCA approved work scope no later than December 31, 2018. Certificates of Occupancy for the residential buildings must be issued by the local jurisdiction before end of business December 31, 2018. Temporary Certificates of Occupancy that prohibit occupancy will not be accepted to meet this requirement. DCA will inspect projects requesting IRS Form(s) 8609 to ensure that all work has been completed prior to issuing Form(s) 8609. If a lesser percentage is completed, DCA reserves the right to recapture all Credits allocated or disallow any credits. DCA may approve modifications to the proposed work scope upon written request.
Note on B96: 2016 State of Georgia Qualified Allocation Plan-EXHIBIT A Final Inspection Fee (for all LIHTC properties, both 4% and 9%, excluding those projects involving HOME funds): $3,000 per 9% Deadline: Due within 30 days of final draw but no later than 30 days prior to the placed in service date or a late fee of $25 per day will be assessed NOTE: Include a copy of the check
Note on B97: 2016 QAP - Architectural Manual - Architectural Standards: II. DESIGN SUBMITTALS AND CONSTRUCTION MONITORING - B. Building Permits: Building permits are required for all work to be funded under DCA programs. Proof of inspections and approvals by local officials, including Certificates of Occupancy, are required for final allocation of Low Income Housing Tax Credits (LIHTC). See Architectural Submission Requirements and contact DCA LIHTC and HOME underwriters for specific information. 2016 QAP - Core - EXHIBIT A - DCA POST AWARD DEADLINES AND FEE SCHEDULE - Certificates of Occupancy/Placement–In-Service: 9% Deadline: Issued by local jurisdiction/all buildings placed in service before end of business December 31, 2018 2016 QAP - Core - SECTION 16. POST AWARD DEADLINES: G. Completion of Work Scope: Certificates of Occupancy for the residential buildings must be issued by the local jurisdiction before end of business December 31, 2018. Temporary Certificates of Occupancy that prohibit occupancy will not be accepted to meet this requirement.
Note on B98: AIA G704 Certificate of Substantial Completion: Submit a copy of this AIA document and include a copy of any list of remaining "punch out items" that were referenced as part of the document.
Note on B99: Final Contractor Application & Certificate for Payment(s) (100% release of retainage): Submit a copy of this AIA document (HUD pay app if applicable). Document should note all added Change Orders.
Note on B101: 2016 QAP - Threshold - XVIII. ACCESSIBILITY STANDARDS : (2) provided at least two training sessions to the General Contractor and Subcontractors regarding accessibility requirements. One training must be on site.
Note on B102: 2016 QAP - Threshold - XVIII. ACCESSIBILITY STANDARDS : (3) an inspection of the construction site after framing is completed to determine that the property is following the approved plans and specifications as to accessibility. DCA must receive a copy of the report issued by the consultant as well as documentation that all issues, if any, have been resolved. (4) a final inspection of the property after completion of construction to determine that the property has been constructed in accordance with all accessibility requirements. DCA must receive a copy of the report issued by the consultant as well as documentation that all issues, if any, have been resolved prior to submission of the project cost certification.
Note on B103: 2016 QAP - Threshold - XVIII. ACCESSIBILITY STANDARDS : C. Each project selected for allocation is required to retain a "DCA Qualified" consultant to monitor the project for accessibility compliance. The Consultant cannot be a member of the proposed Project Team nor have an Identify of Interest with any member of the proposed Project Team. The DCA qualified consultant must perform the following: (1) a pre-construction plan and specification review to determine that the proposed property will meet all required accessibility requirements. The Consultant report must be included with the Step 2 construction documents submitted to DCA. At a minimum, the report will include the initial comments from the consultant, all documents related to resolution of identified accessibility issues and a certification from the consultant that the property meets all required accessibility requirements. (2) an inspection of the construction site after framing is completed to determine that the property is following the approved plans and specifications as to accessibility. DCA must receive a copy of the report issued by the consultant as well as documentation that all issues, if any, have been resolved. (3) a final inspection of the property after completion of construction to determine that the property has been constructed in accordance with all accessibility requirements. DCA must receive a copy of the report issued by the consultant as well as documentation that all issues, if any, have been resolved prior to submission of the project cost certification.
Note on B106: 2016 QAP - Core - SECTION 16 - POST AWARD DEADLINES - H. Placement-In-Service: Owners of projects receiving Credits or Letter of Determination in accordance with this QAP must place all buildings in the development in service by December 31, 2017. DCA may pre-approve in writing, on a case by case basis, limited extension requests for 4% credit projects or projects receiving credits from the 2016 credit ceiling. 2016 QAP - Core - EXHIBIT A - DCA POST AWARD DEADLINES AND FEE SCHEDULE -DCA Placed In Service: 9% Deadline: Within 30 days of the 1st building placed in service
Note on B109: DCA Construction 8609 Clearance Submission: Package should be submitted to the attention of the DCA Construction Administration prior to the Owner's request for the 8609. 2016 QAP- Core- SECTION 16. POST AWARD DEADLINES: G. Completion of Work Scope. Owners of projects receiving Credits or Letters of Determination in accordance with this QAP for the new construction and/or rehabilitation of an existing property must perform 100% of the DCA approved work scope no later than December 31, 2018. Certificates of Occupancy for the residential buildings must be issued by the local jurisdiction before end of business December 31, 2018. Temporary Certificates of Occupancy that prohibit occupancy will not be accepted to meet this requirement. DCA will inspect projects requesting IRS Form(s) 8609 to ensure that all work has been completed prior to issuing Form(s) 8609. If a lesser percentage is completed, DCA reserves the right to recapture all Credits allocated or disallow any credits. DCA may approve modifications to the proposed work scope upon written request. Final Allocation Deadline: 9% Deadline September 30, 2019 (per award letter)
Note on B111: 2016 QAP THRESHOLD - XVII. BUILDING SUSTAINABILITY: All completed properties must achieve a minimum standard for energy efficiency and sustainable building practices. At minimum, all units at all projects must comply with the following. (Historic properties may apply for an exemption when compliance means loss of historic character-defining features and finishes). 2016 QAP - Scoring - VI. SUSTAINABLE DEVELOPMENTS: Certification of the project’s compliance with a sustainable program that is utilized to claim points must be submitted at the time of LIHTC final certification. Failure to complete the certification will result in a finding of noncompliance and limited participation in further rounds. DCA reserves the right to determine that a project has not materially complied with the representations in the Submitted Application and withdraw its allocation if the certification is not obtained.
Note on B112: 2016 QAP - THRESHOLD - XVII. BUILDING SUSTAINABILITY: All completed properties must achieve a minimum standard for energy efficiency and sustainable building practices. At minimum, all units at all projects must comply with the following. (Historic properties may apply for an exemption when compliance means loss of historic character-defining features and finishes). B. Measured duct and building envelope leakage. Verification by certified HERS rater of a HVAC system duct leakage rate and dwelling unit air infiltration rate that meets or exceeds the Energy Star Qualified Homes, Version 3 National Program Requirements for the appropriate project specific climate zone (the duct leakage rate for all climate zones in Georgia is < 4 cfm/100 square feet; dwelling unit air infiltration rate to outdoors for climate zone 2 is an ACH 50 of 6 and for climate zones 3 and 4 is an ACH 50 of 5). Verification testing must follow the Energy Star testing protocol. If the project is not seeking a green building certification, test reports verifying compliance must be submitted at either the LIHTC final certification or HOME Loan final construction draw, whichever comes first. Projects that plan to utilize Packaged Terminal Air Conditioners (PTAC’s) or ductless mini-splits for all units are exempt from the duct leakage requirement.
Note on B113: 2016 Architectural Manual-Architectural Standards O. Radon: All new construction must be built in accordance with current EPA requirements for radon resistant construction techniques, including, but not limited to, ASTM E1465 – 08a Standard Practice for Radon Control Options for the Design and Construction of New Low-Rise Residential Buildings. Both new construction and rehabilitated buildings must be tested prior to tenant occupancy for compliance with EPA’s established limits for radon levels. 2016 Environmental Manual: B. Non-Scope Issues for Phase I Reports - 6. Radon Gas: a. If the Applicant’s project involves the renovation or use of an existing structure, a radon test must be performed to determine radon gas levels, unless an EPA approved short-term radon test has been performed in the lowest public areas of the building(s) within the last six months which demonstrated radon levels at or below 4 pci/l or 0.02 WL. A copy of the Radon Report should be attached to the Phase I Report. Any readings that exceed the EPA limits must mitigate radon levels are part of the work scope in accordance with ASTM E2121 - 13 Standard Practice for Installing Radon Mitigation Systems in Existing Low-Rise Residential Buildings. b. If the Applicant’s project involves new construction, the building(s) must be constructed in accordance with current EPA requirements for radon resistant construction techniques, including, but not limited to, ASTM E1465 - 08 Standard Practice for Radon Control Options for the Design and Construction of New Low-Rise Residential Buildings and the buildings must be tested for radon upon completion of construction. The Phase I Report must include statements to this effect in Section 5.4.21. c. The minimum requirement for testing locations is one test per every 2000 square feet of ground-contact units. However, radon concentrations can be highly localized and best practice for radon testing should involve a certified radon tester (http://www.radongas.org/ or http://www.nrsb.org/). In addition, it is recommended that at least one test be located in each building on each floor above the ground-contact level, covering a minimum of 10% of the units on all floors above the ground floor.
Note on B116: Conditions of Funding Compliance Narrative: Provide a narrative that includes evidence of compliance with each GHFA Letter of Determination "Assumptions & Conditions" of Funding section. Restate each "Assumptions & Conditions" verbatim from the Letter of Determination before each response describing method of compliance. Provide supporting docs/evidence as needed. Note: - Only need to respond to items related to the Construction Services Department requirements
Note on B119: 2016 QAP - Threshold: Exhibit A to Appendix I: DCA UNDERWRITING POLICIES - 10. Identity of Interest. Contractor: If there is an Identity of Interest between any Project Participant and the General Contractor, a third party front-end analysis of the construction costs must be conducted. For HOME projects, the third-party review will be commissioned by DCA during the DCA underwriting period. For tax credit only projects, the qualifications of the proposed third-party reviewer must be submitted to DCA and approved before the review is conducted. Additionally, industry standards for such Owner-provided construction services shall be used to determine reasonableness for the services. DCA will require that a contractor cost certification be submitted where there is an Identity of Interest between any Project Participant and the General Contractor. The cost certification shall be prepared in accordance with the standards set forth for a HOME contractor cost certification. Subcontractor / Materialmen: Any Identity of Interest between any Project Participant or General Contractor and any subcontractors, other provider of service, materials, or supplies must be disclosed. Additional scrutiny will be given to subcontractor/materialmen costs where there is an Identity of Interest. 2016 QAP - Core: SECTION 2. DEFINITIONS: Project Participants: Mean the Owner, Developer, Management Company, Consultants and Syndicator for a project for which an Application is submitted.
Note on B130: Note: Submit copies of DCA approved Project Concept Changes that are related to the Construction Services Dept.

## 2016 4 Pct
GEORGIA DEPARTMENT OF COMMUNITY AFFAIRS | [9 empty] | 4% TAX CREDIT ONLY
Office of Housing Finance & Development
Construction Services Department
60 Executive Park South, NE, Atlanta, GA 30329-2231
2016 DCA CONSTRUCTION SERVICES TRANSMITTAL | [11 empty] | Form Date: | 06.20.2017
|  | DCA PROJECT #: |  | (2016-000) | [6 empty] | DATE:
PROJECT NAME:
DEVELOPER CONTACT | [8 empty] | BUILDING SCHEDULE
| Company: | [7 empty] | Residential Buildings
| Name: | [7 empty] | #Bldgs. | Bldg. Type |  | Conditioned SF | Covered SF
Email:
Phone:
PROJECT TEAM
Architect:
Contractor:
|  |  |  | Identity of Interest?: |  |  |  | Total: | 0 |  |  | 0 | 0
| Accessibility: | [7 empty] | Accessory Buildings (non-residential)
[9 empty] | #Bldgs. | Bldg. Type |  | Conditioned SF | Covered SF
PROPERTY ADDRESS
Street:
| City: |  |  | ZIP:
| County: | [6 empty] | Total: | 0 |  |  | 0 | 0
| Geo Coord: | Latitude: |  | Longitude
|  |  | (00.000000) |  | (00.000000) |  |  |  |  | UNIT SCHEDULE
PROJECT DESCRIPTION | [9 empty] | Residential Units
|  |  | Scattered Site?: | [6 empty] | #Units | #Bedrms. | #Bathrms. | Total Net SF
|  |  | If Yes, How Many Properties?: | [10 empty] | 0
0
|  |  | Tenancy1: | [10 empty] | 0
|  |  | Tenancy2: | [10 empty] | 0
0
|  |  | Constr. Type1: | [10 empty] | 0
|  |  | Constr. Type2: | [5 empty] | Total: | 0 | 0 |  | 0 | 0 | # of bedrms.
Accessibility Units
|  |  | Acreage: | [6 empty] | Total # of Mobility Impaired Units:
# of M.I. Units With "Roll-in Showers":
PROJECT SCHEDULE | [9 empty] | # of Sight / Hearing Impaired Units:
Notice to Proceed
|  |  | Estimated Date: |  |  |  | HARD COSTS
|  |  | Actual Date: |  |  |  | Description |  |  |  | Award | Due Dill. | Final Alloc.
Contractor Hard Costs:
|  |  |  | Placed in Service |  |  | Other Construction Hard Cost:
|  |  | DCA "Expected" PIS Date: |  |  |  | Construction Contingency:
|  |  | Last Residential Bldg. "Actual" PIS Date: | [6 empty] | Total Hard Costs: | 0 | 0 | 0
|  |  |  | Substantial Completion |  |  | Cost Per Unit Net SF: |  |  |  | #DIV/0! | #DIV/0! | #DIV/0!
|  |  | Estimated Date: |  |  |  | Cost Per Unit: |  |  |  | #DIV/0! | #DIV/0! | #DIV/0!
|  |  | Actual Date: |  |  |  | Cost Per Bedrm.: |  |  |  | #DIV/0! | #DIV/0! | #DIV/0!
*** DO NOT COMBINE THE STAGED SUBMISSION PACKAGES (maintain separate binders/flash drives per submission) ***
PLACE AN 'X' IN THE BOX NEXT TO EACH DOCUMENT SUBMITTED
60 DAY SUBMISSION (due no later than 60 days after the Date of Letter of Determination)
01 | Boundary Survey (including topographical data)
02 | Geotechnical Report (new construction only)
03 | Accessibility Consultant Agreement
04 | Contractor and Subcontractor Accessibility Training Sessions Action Plan (submit a document that states how this will be accomplished)
05 | Green Building Consultant Agreement - "when applicable" (agreement/proposal/MOUs)
06 | Qualifications for 3rd party cost reviewer (ONLY contractor identity of interest)
07 | DCA Amenities & Design Options Re-Certification form
08 | DCA Approved Architectural Waivers/Optional Amenities (including evidence of DCA approval)
09 | Other:
Closing of the bond financing within 180 days of the issuance of this Letter of Determination.
DCA#: |  | 0 |  |  |  | Program: | 4 Percent |  |  |  |  | Page: | 01 of 02
| COMMENCEMENT SUBMISSION (due within 30 days of construction commencement) | [12 empty] | COMMENCEMENT SUBMISSION (due within 30 days of construction commencement; and no later than October 31, 2017)
01 | DCA Construction Document Log (Contract Set) (drawing log)
02 | DCA "Contract Set" of drawings (plans) (see directions for definition of "Contract Set")
03 | DCA "Contract Set" of Project Manual (specs)
04 | DCA Amenities & Design Options Re-Certification form
05 | Accessibility Consultant Plan Review Comments
06 | Accessibility Consultant Clearance Letter (acknowledgement of plan review comment resolutions)
07 | DCA Schedule of Values form (Contract Set)
08 | Front-End Third Party Cost Review for "Identity of Interest" (see QAP for definition of I of I)
09 | Owner/Contractor Agreement - Executed
10 | Narrative that identifies each Determination Letter "Assumptions & Conditions" and provides a status update of each condition (Construction Srvcs Dept items)
(ex.: wetlands delineations, noise mitigation plans, etc.) (restate each C.o.F in the narrative)
11 | Notice to Proceed
12 | Construction Schedule - Finalized
13 | Permits (Land Development, Building,,,)
14 | DCA Approved Architectural Waivers/Optional Amenities (including evidence of DCA approval)
15 | DCA Placed in Service form - Draft with estimated dates (DCA Compliance Dept. form)
16 | Other:
DCA FINAL INSPECTION SUBMISSION (due within 30 days of the final retainage draw certified date)
01 | Request For Final Construction Compliance Form
02 | Final Inspection Fee ($3,000)
03 | Certificates of Occupancy (COs)
04 | AIA G704 Certificate of Substantial Completion
05 | Final Contractor Application & Certificate for Payment(s) (100% release of retainage)
06 | Copies of all Change Orders (including support docs included with approved Change Order)
07 | Confirmation of Contractor and Subcontractor Accessibility Training Sessions (minimum two sessions)
08 | Copies of all site inspection reports performed by the Accessibility Consultant (minimum two rpts. per QAP)
09 | Clearance letter from the Accessibility Consultant stating all reported accessibility concerns have been resolved
10 | DCA Amenities & Design Options Re-Certification form
11 | DCA Approved Architectural Waivers/Optional Amenities (including evidence of DCA approval)
12 | DCA Placed in Service form (DCA Compliance Dept. form)
13 | Other:
CONSTRUCTION 8609 CLEARANCE SUBMISSION (due prior to final allocation of resources which is due no later than September 15, 2019)
01 | Green Building certifications (where applicable)
02 | Verification from a HERS rater that dwelling unit air infiltration rate meets or exceeds the QAP
03 | Radon Testing that demonstrates levels below the EPA recommended limits
--include a radon report from radon professional
--include a radon tests
04 | Verification of compliance with each DCA Determination Letter "Condition of Funding" (Item# 10, 12 & 13) | [9 empty] | (Construction Srvcs Dept items)
--provide a narrative that describes means of compliance with each Conditions of Funding (restate each C.o.F in the narrative)
--provide supporting docs/evidence as needed
05 | Contractor Cost Certification (when there is an Identity of Interest between any Project Participant and the General Contractor)
a: Auditor opinion letter:
b: Certification of Independent Certified Public Accountant EXHIBIT B:
c: General Contractor Certification EXHIBIT C:
d: Multifamily Loan Contractors’ Cost Certification of Actual Project Costs EXHIBIT D:
e: Contractor’s Cost Certification EXHIBIT E:
i: Line item analysis and explanation EXHIBIT F:
ii: Complete change order log:
iii: A copy of all signed change orders:
iv: Complete subcontractor log:
06 | DCA Approved Architectural Waivers/Optional Amenities (including evidence of DCA approval)
07 | DCA Approved Project Concept Changes (including evidence of DCA approval)
08 | Other:
OTHER SUBMISSIONS
01 | Other:
02 | Other:
DCA#: |  | 0 |  |  |  | Program: | 4 Percent |  |  |  |  | Page: | 02 of 02
Note on A12: DEVELOPER CONTACT FOR DCA CONSTRUCTION SERVICES DEPT.
Note on N14: Note: Gross Building "Conditioned" Square Footage
Note on O14: Note: Gross Building "Covered" Square Footage
Note on N23: Note: Gross Building "Conditioned" Square Footage
Note on O23: Note: Gross Building "Covered" Square Footage
Note on O31: 2016 Architectural Standards - V. BUILDING INTERIORS DESIGN STANDARDS - B. Unit Sizes: Net Rentable (Leasable) Square Footage: This is the DCA definition for calculating “Residential Unit Square Footage” as it pertains to the Architectural Manual and other documents in Qualified Allocation Plan (QAP). It is calculated for each individual dwelling type. The unit net rentable area is measured from the inside face of each of the unit’s perimeter walls. • Net area included air-conditioned space only. • Measure from the inside (paint) face of all unit perimeter walls. • Do not include any patio, balcony, or breezeway areas. • Do not include any outside storage closets. • Do not deduct any interior walls. • Include non-revenue units in total net rentable living area (Total Residential Unit Square Footage)
Note on O40: 2016 Qualified Allocation Plan - Threshold XVIII. ACCESSIBILITY STANDARDS B. Regardless of whether a project anticipates using federal HOME funds as a funding source, all proposed projects must include the following DCA requirements: 1. At least 5% of the total units (but no less than one unit) must be equipped for the mobility disabled, including wheelchair restricted residents. Roll-in showers must be incorporated into 40% of the mobility equipped units (but no fewer than one unit); and 2. At least an additional 2% of the total units (but no less than one unit) must be equipped for hearing and sight-impaired residents. The same unit cannot be used to satisfy the 5% and 2% requirement. Preservation of existing affordable housing that cannot be modified to meet accessibility requirements that are not required by law, may request a DCA waiver.
Note on O41: 2016 Qualified Allocation Plan - Threshold XVIII. ACCESSIBILITY STANDARDS B. Regardless of whether a project anticipates using federal HOME funds as a funding source, all proposed projects must include the following DCA requirements: 1. At least 5% of the total units (but no less than one unit) must be equipped for the mobility disabled, including wheelchair restricted residents. Roll-in showers must be incorporated into 40% of the mobility equipped units (but no fewer than one unit); and 2. At least an additional 2% of the total units (but no less than one unit) must be equipped for hearing and sight-impaired residents. The same unit cannot be used to satisfy the 5% and 2% requirement. Preservation of existing affordable housing that cannot be modified to meet accessibility requirements that are not required by law, may request a DCA waiver.
Note on O42: 2016 Qualified Allocation Plan - Threshold XVIII. ACCESSIBILITY STANDARDS B. Regardless of whether a project anticipates using federal HOME funds as a funding source, all proposed projects must include the following DCA requirements: 1. At least 5% of the total units (but no less than one unit) must be equipped for the mobility disabled, including wheelchair restricted residents. Roll-in showers must be incorporated into 40% of the mobility equipped units (but no fewer than one unit); and 2. At least an additional 2% of the total units (but no less than one unit) must be equipped for hearing and sight-impaired residents. The same unit cannot be used to satisfy the 5% and 2% requirement. Preservation of existing affordable housing that cannot be modified to meet accessibility requirements that are not required by law, may request a DCA waiver.
Note on M45: Note: Cost amounts on application
Note on N45: Due Diligence: Cost amounts at time of Construction Loan Closing (Owner/Contractor agreement, etc.) Enter data with Commencement submission.
Note on O45: Final Allocation: Final Construction Hard Cost amounts (Change Orders, etc.) Enter data with Architectural 8609 submission.
Note on E48: Note: The "Expected Placed In Service" date is from the DCA generated "Exhibit A: Building Designation" which is an exhibit to the Carryover Letter for projects receiving tax credits.
Note on F51: Note: The date for the "AIA G704 Certificate of Substantial Completion"
Note on B58: 2016 QAP - Core - SECTION 16 - POST AWARD DEADLINES - A. Construction Documents: For 4% deals, Construction Documents as fully outlined in the Architectural Manual must be submitted to DCA for review and approval at time of Application.
Note on B62: 2016 QAP - Threshold - XVIII. ACCESSIBILITY STANDARDS : C. Each project selected for allocation is required to retain a "DCA Qualified" consultant to monitor the project for accessibility compliance. The Consultant cannot be a member of the proposed Project Team nor have an Identify of Interest with any member of the proposed Project Team. The DCA qualified consultant must perform the following: (1) a pre-construction plan and specification review to determine that the proposed property will meet all required accessibility requirements. The Consultant report must be included with the Step 2 construction documents submitted to DCA. At a minimum, the report will include the initial comments from the consultant, all documents related to resolution of identified accessibility issues and a certification from the consultant that the plans appear to meet all accessibility requirements. (2) provided at least two training sessions to the General Contractor and Subcontractors regarding accessibility requirements. One training must be on site. (3) an inspection of the construction site after framing is completed to determine that the property is following the approved plans and specifications as to accessibility. DCA must receive a copy of the report issued by the consultant as well as documentation that all issues, if any, have been resolved. (4) a final inspection of the property after completion of construction to determine that the property has been constructed in accordance with all accessibility requirements. DCA must receive a copy of the report issued by the consultant as well as documentation that all issues, if any, have been resolved prior to submission of the project cost certification.
Note on B63: 2016 QAP - Threshold Criteria: XVIII. ACCESSIBILITY STANDARDS: (2) provided at least two training sessions to the General Contractor and Subcontractors regarding accessibility requirements. One training must be on site.
Note on B73: 2016 QAP - Core- EXHIBIT A - DCA POST AWARD DEADLINES AND FEE SCHEDULE Commencement of Construction/Rehabilitation (Tax Credit Only Projects) 4% Deadline: No later than September 30, 2017
Note on B84: Assumptions & Conditions Status Update Narrative: Provide a narrative that identifies each GHFA Letter of Determination "Assumptions & Conditions" of Funding section and provides a status update of each condition. Restate each "Assumptions & Conditions" verbatim from the Letter of Determination before each response. Note: - Only need to respond to items related to the Construction Services Department requirements
Note on B93: DCA Final Inspection Submission: The submittal package should be submitted to the attention of the DCA Construction Administration when Contractor is requesting release of retainage (final pay app request). 2016 QAP -Core- SECTION 16. POST AWARD DEADLINES: G. Completion of Work Scope: Owners of projects receiving Credits or Letters of Determination in accordance with this QAP for the new construction and/or rehabilitation of an existing property must perform 100% of the DCA approved work scope no later than December 31, 2018. Certificates of Occupancy for the residential buildings must be issued by the local jurisdiction before end of business December 31, 2018. Temporary Certificates of Occupancy that prohibit occupancy will not be accepted to meet this requirement. DCA will inspect projects requesting IRS Form(s) 8609 to ensure that all work has been completed prior to issuing Form(s) 8609. If a lesser percentage is completed, DCA reserves the right to recapture all Credits allocated or disallow any credits. DCA may approve modifications to the proposed work scope upon written request.
Note on B95: 2016 QAP - Core - EXHIBIT A - DCA POST AWARD DEADLINES AND FEE SCHEDULE -Completion of Work Scope 4% Deadline: No later than December 31, 2018 G. Completion of Work Scope. Owners of projects receiving Credits or Letters of Determination in accordance with this QAP for the new construction and/or rehabilitation of an existing property must perform 100% of the DCA approved work scope no later than December 31, 2018. Certificates of Occupancy for the residential buildings must be issued by the local jurisdiction before end of business December 31, 2018. Temporary Certificates of Occupancy that prohibit occupancy will not be accepted to meet this requirement. DCA will inspect projects requesting IRS Form(s) 8609 to ensure that all work has been completed prior to issuing Form(s) 8609. If a lesser percentage is completed, DCA reserves the right to recapture all Credits allocated or disallow any credits. DCA may approve modifications to the proposed work scope upon written request.
Note on B96: 2016 State of Georgia Qualified Allocation Plan-EXHIBIT A Final Inspection Fee (for all LIHTC properties, both 4% and 9%, excluding those projects involving HOME funds): $3,000 per 4% Deadline: Due within 30 days of final draw but no later than 30 days prior to the placed in service date or a late fee of $25 per day will be assessed NOTE: Include a copy of the check
Note on B97: 2016 QAP - Architectural Manual - Architectural Standards: II. DESIGN SUBMITTALS AND CONSTRUCTION MONITORING - B. Building Permits: Building permits are required for all work to be funded under DCA programs. Proof of inspections and approvals by local officials, including Certificates of Occupancy, are required for final allocation of Low Income Housing Tax Credits (LIHTC). See Architectural Submission Requirements and contact DCA LIHTC and HOME underwriters for specific information. 2016 QAP - Core - EXHIBIT A - DCA POST AWARD DEADLINES AND FEE SCHEDULE - Certificates of Occupancy/Placement–In-Service: 4% Deadline: Issued by local jurisdiction/all buildings placed in service before end of business December 31, 2018 2016 QAP - Core - SECTION 16. POST AWARD DEADLINES: G. Completion of Work Scope: Certificates of Occupancy for the residential buildings must be issued by the local jurisdiction before end of business December 31, 2018. Temporary Certificates of Occupancy that prohibit occupancy will not be accepted to meet this requirement.
Note on B98: AIA G704 Certificate of Substantial Completion: Submit a copy of this AIA document and include a copy of any list of remaining "punch out items" that were referenced as part of the document.
Note on B99: Final Contractor Application & Certificate for Payment(s) (100% release of retainage): Submit a copy of this AIA document (HUD pay app if applicable). Document should note all added Change Orders.
Note on B101: 2016 QAP - Threshold - XVIII. ACCESSIBILITY STANDARDS : (2) provided at least two training sessions to the General Contractor and Subcontractors regarding accessibility requirements. One training must be on site.
Note on B102: 2016 QAP - Threshold - XVIII. ACCESSIBILITY STANDARDS : (3) an inspection of the construction site after framing is completed to determine that the property is following the approved plans and specifications as to accessibility. DCA must receive a copy of the report issued by the consultant as well as documentation that all issues, if any, have been resolved. (4) a final inspection of the property after completion of construction to determine that the property has been constructed in accordance with all accessibility requirements. DCA must receive a copy of the report issued by the consultant as well as documentation that all issues, if any, have been resolved prior to submission of the project cost certification.
Note on B103: 2016 QAP - Threshold - XVIII. ACCESSIBILITY STANDARDS : C. Each project selected for allocation is required to retain a "DCA Qualified" consultant to monitor the project for accessibility compliance. The Consultant cannot be a member of the proposed Project Team nor have an Identify of Interest with any member of the proposed Project Team. The DCA qualified consultant must perform the following: (1) a pre-construction plan and specification review to determine that the proposed property will meet all required accessibility requirements. The Consultant report must be included with the Step 2 construction documents submitted to DCA. At a minimum, the report will include the initial comments from the consultant, all documents related to resolution of identified accessibility issues and a certification from the consultant that the property meets all required accessibility requirements. (2) an inspection of the construction site after framing is completed to determine that the property is following the approved plans and specifications as to accessibility. DCA must receive a copy of the report issued by the consultant as well as documentation that all issues, if any, have been resolved. (3) a final inspection of the property after completion of construction to determine that the property has been constructed in accordance with all accessibility requirements. DCA must receive a copy of the report issued by the consultant as well as documentation that all issues, if any, have been resolved prior to submission of the project cost certification.
Note on B106: 2016 QAP - Core - SECTION 16 - POST AWARD DEADLINES - H. Placement-In-Service: Owners of projects receiving Credits or Letter of Determination in accordance with this QAP must place all buildings in the development in service by December 31, 2017. DCA may pre-approve in writing, on a case by case basis, limited extension requests for 4% credit projects or projects receiving credits from the 2016 credit ceiling. 2016 QAP - Core - EXHIBIT A - DCA POST AWARD DEADLINES AND FEE SCHEDULE -DCA Placed In Service: 4% Deadline: Within 30 days of the 1st building placed in service
Note on B109: DCA Construction 8609 Clearance Submission: Package should be submitted to the attention of the DCA Construction Administration prior to the Owner's request for the 8609. 2016 QAP- Core- SECTION 16. POST AWARD DEADLINES: G. Completion of Work Scope. Owners of projects receiving Credits or Letters of Determination in accordance with this QAP for the new construction and/or rehabilitation of an existing property must perform 100% of the DCA approved work scope no later than December 31, 2018. Certificates of Occupancy for the residential buildings must be issued by the local jurisdiction before end of business December 31, 2018. Temporary Certificates of Occupancy that prohibit occupancy will not be accepted to meet this requirement. DCA will inspect projects requesting IRS Form(s) 8609 to ensure that all work has been completed prior to issuing Form(s) 8609. If a lesser percentage is completed, DCA reserves the right to recapture all Credits allocated or disallow any credits. DCA may approve modifications to the proposed work scope upon written request. 2016 QAP - Core - EXHIBIT A - DCA POST AWARD DEADLINES AND FEE SCHEDULE: Final Allocation Deadline: 4% Deadline September 15, 2019
Note on B111: 2016 QAP THRESHOLD - XVII. BUILDING SUSTAINABILITY: All completed properties must achieve a minimum standard for energy efficiency and sustainable building practices. At minimum, all units at all projects must comply with the following. (Historic properties may apply for an exemption when compliance means loss of historic character-defining features and finishes). 2016 QAP - Scoring - VI. SUSTAINABLE DEVELOPMENTS: Certification of the project’s compliance with a sustainable program that is utilized to claim points must be submitted at the time of LIHTC final certification. Failure to complete the certification will result in a finding of noncompliance and limited participation in further rounds. DCA reserves the right to determine that a project has not materially complied with the representations in the Submitted Application and withdraw its allocation if the certification is not obtained.
Note on B112: 2016 QAP - THRESHOLD - XVII. BUILDING SUSTAINABILITY: All completed properties must achieve a minimum standard for energy efficiency and sustainable building practices. At minimum, all units at all projects must comply with the following. (Historic properties may apply for an exemption when compliance means loss of historic character-defining features and finishes). B. Measured duct and building envelope leakage. Verification by certified HERS rater of a HVAC system duct leakage rate and dwelling unit air infiltration rate that meets or exceeds the Energy Star Qualified Homes, Version 3 National Program Requirements for the appropriate project specific climate zone (the duct leakage rate for all climate zones in Georgia is < 4 cfm/100 square feet; dwelling unit air infiltration rate to outdoors for climate zone 2 is an ACH 50 of 6 and for climate zones 3 and 4 is an ACH 50 of 5). Verification testing must follow the Energy Star testing protocol. If the project is not seeking a green building certification, test reports verifying compliance must be submitted at either the LIHTC final certification or HOME Loan final construction draw, whichever comes first. Projects that plan to utilize Packaged Terminal Air Conditioners (PTAC’s) or ductless mini-splits for all units are exempt from the duct leakage requirement.
Note on B113: 2016 Architectural Manual-Architectural Standards O. Radon: All new construction must be built in accordance with current EPA requirements for radon resistant construction techniques, including, but not limited to, ASTM E1465 – 08a Standard Practice for Radon Control Options for the Design and Construction of New Low-Rise Residential Buildings. Both new construction and rehabilitated buildings must be tested prior to tenant occupancy for compliance with EPA’s established limits for radon levels. 2016 Environmental Manual: B. Non-Scope Issues for Phase I Reports - 6. Radon Gas: a. If the Applicant’s project involves the renovation or use of an existing structure, a radon test must be performed to determine radon gas levels, unless an EPA approved short-term radon test has been performed in the lowest public areas of the building(s) within the last six months which demonstrated radon levels at or below 4 pci/l or 0.02 WL. A copy of the Radon Report should be attached to the Phase I Report. Any readings that exceed the EPA limits must mitigate radon levels are part of the work scope in accordance with ASTM E2121 - 13 Standard Practice for Installing Radon Mitigation Systems in Existing Low-Rise Residential Buildings. b. If the Applicant’s project involves new construction, the building(s) must be constructed in accordance with current EPA requirements for radon resistant construction techniques, including, but not limited to, ASTM E1465 - 08 Standard Practice for Radon Control Options for the Design and Construction of New Low-Rise Residential Buildings and the buildings must be tested for radon upon completion of construction. The Phase I Report must include statements to this effect in Section 5.4.21. c. The minimum requirement for testing locations is one test per every 2000 square feet of ground-contact units. However, radon concentrations can be highly localized and best practice for radon testing should involve a certified radon tester (http://www.radongas.org/ or http://www.nrsb.org/). In addition, it is recommended that at least one test be located in each building on each floor above the ground-contact level, covering a minimum of 10% of the units on all floors above the ground floor.
Note on B116: Conditions of Funding Compliance Narrative: Provide a narrative that includes evidence of compliance with each GHFA Letter of Determination "Assumptions & Conditions" of Funding section. Restate each "Assumptions & Conditions" verbatim from the Letter of Determination before each response describing method of compliance. Provide supporting docs/evidence as needed. Note: - Only need to respond to items related to the Construction Services Department requirements
Note on B119: 2016 QAP - Threshold: Exhibit A to Appendix I: DCA UNDERWRITING POLICIES - 10. Identity of Interest. Contractor: If there is an Identity of Interest between any Project Participant and the General Contractor, a third party front-end analysis of the construction costs must be conducted. For HOME projects, the third-party review will be commissioned by DCA during the DCA underwriting period. For tax credit only projects, the qualifications of the proposed third-party reviewer must be submitted to DCA and approved before the review is conducted. Additionally, industry standards for such Owner-provided construction services shall be used to determine reasonableness for the services. DCA will require that a contractor cost certification be submitted where there is an Identity of Interest between any Project Participant and the General Contractor. The cost certification shall be prepared in accordance with the standards set forth for a HOME contractor cost certification. Subcontractor / Materialmen: Any Identity of Interest between any Project Participant or General Contractor and any subcontractors, other provider of service, materials, or supplies must be disclosed. Additional scrutiny will be given to subcontractor/materialmen costs where there is an Identity of Interest. 2016 QAP - Core: SECTION 2. DEFINITIONS: Project Participants: Mean the Owner, Developer, Management Company, Consultants and Syndicator for a project for which an Application is submitted.
Note on B130: Note: Submit copies of DCA approved Project Concept Changes that are related to the Construction Services Dept.

## 2016 HOME
GEORGIA DEPARTMENT OF COMMUNITY AFFAIRS | [9 empty] | 9% HOME ONLY
Office of Housing Finance & Development
Construction Services Department
60 Executive Park South, NE, Atlanta, GA 30329-2231
2016 DCA CONSTRUCTION SERVICES TRANSMITTAL | [11 empty] | Form Date: | 06.20.2017
|  | DCA PROJECT #: |  | (2016-000) | [6 empty] | DATE:
PROJECT NAME:
DEVELOPER CONTACT | [8 empty] | BUILDING SCHEDULE
| Company: | [7 empty] | Residential Buildings
| Name: | [7 empty] | #Bldgs. | Bldg. Type |  | Conditioned SF | Covered SF
Email:
Phone:
PROJECT TEAM
Architect:
Contractor:
|  |  |  | Identity of Interest?: |  |  |  | Total: | 0 |  |  | 0 | 0
| Accessibility: | [7 empty] | Accessory Buildings (non-residential)
[9 empty] | #Bldgs. | Bldg. Type |  | Conditioned SF | Covered SF
PROPERTY ADDRESS
Street:
| City: |  |  | ZIP:
| County: | [6 empty] | Total: | 0 |  |  | 0 | 0
| Geo Coord: | Latitude: |  | Longitude
|  |  | (00.000000) |  | (00.000000) |  |  |  |  | UNIT SCHEDULE
PROJECT DESCRIPTION | [9 empty] | Residential Units
|  |  | Scattered Site?: | [6 empty] | #Units | #Bedrms. | #Bathrms. | Total Net SF
|  |  | If Yes, How Many Properties?: | [10 empty] | 0
0
|  |  | Tenancy1: | [10 empty] | 0
|  |  | Tenancy2: | [10 empty] | 0
0
|  |  | Constr. Type1: | [10 empty] | 0
|  |  | Constr. Type2: | [5 empty] | Total: | 0 | 0 |  | 0 | 0 | # of bedrms.
Accessibility Units
|  |  | Acreage: | [6 empty] | Total # of Mobility Impaired Units:
# of M.I. Units With "Roll-in Showers":
PROJECT SCHEDULE | [9 empty] | # of Sight / Hearing Impaired Units:
Notice to Proceed
|  |  | Estimated Date: |  |  |  | HARD COSTS
|  |  | Actual Date: |  |  |  | Description |  |  |  | Award | Due Dill. | Final Alloc.
Contractor Hard Costs:
|  |  |  | Placed in Service |  |  | Other Construction Hard Cost:
|  |  | DCA "Expected" PIS Date: |  |  |  | Construction Contingency:
|  |  | Last Residential Bldg. "Actual" PIS Date: | [6 empty] | Total Hard Costs: | 0 | 0 | 0
|  |  |  | Substantial Completion |  |  | Cost Per Unit Net SF: |  |  |  | #DIV/0! | #DIV/0! | #DIV/0!
|  |  | Estimated Date: |  |  |  | Cost Per Unit: |  |  |  | #DIV/0! | #DIV/0! | #DIV/0!
|  |  | Actual Date: |  |  |  | Cost Per Bedrm.: |  |  |  | #DIV/0! | #DIV/0! | #DIV/0!
*** DO NOT COMBINE THE STAGED SUBMISSION PACKAGES (maintain separate binders/flash drives per submission) ***
PLACE AN 'X' IN THE BOX NEXT TO EACH DOCUMENT SUBMITTED
60 DAY SUBMISSION (due no later than 60 days after announcement of awards; or no later than March 1, 2017)
01 | ALTA/ACSM Land Title Survey
02 | Geotechnical Report (new construction only)
03 | Accessibility Consultant Agreement
04 | Contractor and Subcontractor Accessibility Training Sessions Action Plan (submit a document that states how this will be accomplished)
05 | Green Building Consultant Agreement - "when applicable" (agreement/proposal/MOUs)
06 | DCA Amenities & Design Options Re-Certification form
07 | DCA Approved Architectural Waivers/Optional Amenities (including evidence of DCA approval)
08 | Other:
DCA#: |  | 0 |  |  |  | Program: | HOME |  |  |  |  | Page: | 01 of 02
*** DO NOT COMBINE THE STAGED SUBMISSION PACKAGES (maintain separate binders/flash drives per submission) ***
PLACE AN 'X' IN THE BOX NEXT TO EACH DOCUMENT SUBMITTED
DCA REVIEW SUBMISSION (due no later than May 1, 2017)
01 | DCA Construction Document Log (Review Set) (drawing log)
02 | DCA "Review Set" of drawings (plans) (see directions for definition of "Review Set")
03 | DCA "Review Set" of Project Manual (specs)
04 | DCA Schedule of Values form (Review Set)
05 | DCA Amenities & Design Options Re-Certification form
06 | Owner/Architect Agreement - Executed
07 | Owner/Contractor Agreement - Draft (current A101 Stipulated Sum or A102 Cost of Work Plus Fee With a Guaranteed Maximum Price forms)
08 | Contractor Approval Package (see page 53 of 59 of the 2016 QAP Threshold)
09 | Construction Schedule - Draft
10 | Narrative that identifies each Carryover Allocation letter "Assumptions & Conditions" and provides a status update of each condition (Constr Srvcs Dept items)
(ex.: wetlands delineations, noise mitigation plans, etc.) (restate each C.o.F in the narrative)
11 | Federal Work Authorization Affidavits (E-Verify)
12 | DCA Approved Architectural Waivers/Optional Amenities (including evidence of DCA approval)
13 | Other:
LOAN CLOSING SUBMISSION (due prior to DCA Loan Closing )
01 | DCA Construction Document Log (Contract Set) (drawing log)
02 | DCA "Contract Set" of drawings (plans) (see directions for definition of "Contract Set")
03 | DCA "Contract Set" of Project Manual (specs)
04 | Addendum incorporating/outlining revisions from DCA Review Set into the DCA Contract Set
05 | DCA Schedule of Values form (Contract Set)
06 | DCA Amenities & Design Options Re-Certification form
07 | Owner/Contractor Agreement - Executed
08 | DCA Approved Architectural Waivers/Optional Amenities (including evidence of DCA approval)
09 | Other:
COMMENCEMENT SUBMISSION (due within 30 days of construction commencement; and no later than 10 months of date of the initial preliminary HOME award)
01 | Notice to Proceed
02 | Construction Schedule - Finalized
03 | Permits (Land Development, Building,,,)
04 | Accessibility Consultant Plan Review Comments
05 | Accessibility Consultant Clearance Letter (acknowledgement of plan review comment resolutions)
06 | DCA Approved Architectural Waivers/Optional Amenities (including evidence of DCA approval)
07 | DCA Placed in Service form - Draft with estimated dates (DCA Compliance Dept. form)
08 | Other:
OTHER SUBMISSIONS
01 | Other:
02 | Other:
DCA#: |  | 0 |  |  |  | Program: | HOME |  |  |  |  | Page: | 02 of 02
Note on A12: DEVELOPER CONTACT FOR DCA CONSTRUCTION SERVICES DEPT.
Note on N14: Note: Gross Building "Conditioned" Square Footage
Note on O14: Note: Gross Building "Covered" Square Footage
Note on N23: Note: Gross Building "Conditioned" Square Footage
Note on O23: Note: Gross Building "Covered" Square Footage
Note on O31: 2016 Architectural Standards - V. BUILDING INTERIORS DESIGN STANDARDS - B. Unit Sizes: Net Rentable (Leasable) Square Footage: This is the DCA definition for calculating “Residential Unit Square Footage” as it pertains to the Architectural Manual and other documents in Qualified Allocation Plan (QAP). It is calculated for each individual dwelling type. The unit net rentable area is measured from the inside face of each of the unit’s perimeter walls. • Net area included air-conditioned space only. • Measure from the inside (paint) face of all unit perimeter walls. • Do not include any patio, balcony, or breezeway areas. • Do not include any outside storage closets. • Do not deduct any interior walls. • Include non-revenue units in total net rentable living area (Total Residential Unit Square Footage)
Note on O40: 2016 Qualified Allocation Plan - Threshold XVIII. ACCESSIBILITY STANDARDS B. Regardless of whether a project anticipates using federal HOME funds as a funding source, all proposed projects must include the following DCA requirements: 1. At least 5% of the total units (but no less than one unit) must be equipped for the mobility disabled, including wheelchair restricted residents. Roll-in showers must be incorporated into 40% of the mobility equipped units (but no fewer than one unit); and 2. At least an additional 2% of the total units (but no less than one unit) must be equipped for hearing and sight-impaired residents. The same unit cannot be used to satisfy the 5% and 2% requirement. Preservation of existing affordable housing that cannot be modified to meet accessibility requirements that are not required by law, may request a DCA waiver.
Note on O41: 2016 Qualified Allocation Plan - Threshold XVIII. ACCESSIBILITY STANDARDS B. Regardless of whether a project anticipates using federal HOME funds as a funding source, all proposed projects must include the following DCA requirements: 1. At least 5% of the total units (but no less than one unit) must be equipped for the mobility disabled, including wheelchair restricted residents. Roll-in showers must be incorporated into 40% of the mobility equipped units (but no fewer than one unit); and 2. At least an additional 2% of the total units (but no less than one unit) must be equipped for hearing and sight-impaired residents. The same unit cannot be used to satisfy the 5% and 2% requirement. Preservation of existing affordable housing that cannot be modified to meet accessibility requirements that are not required by law, may request a DCA waiver.
Note on O42: 2016 Qualified Allocation Plan - Threshold XVIII. ACCESSIBILITY STANDARDS B. Regardless of whether a project anticipates using federal HOME funds as a funding source, all proposed projects must include the following DCA requirements: 1. At least 5% of the total units (but no less than one unit) must be equipped for the mobility disabled, including wheelchair restricted residents. Roll-in showers must be incorporated into 40% of the mobility equipped units (but no fewer than one unit); and 2. At least an additional 2% of the total units (but no less than one unit) must be equipped for hearing and sight-impaired residents. The same unit cannot be used to satisfy the 5% and 2% requirement. Preservation of existing affordable housing that cannot be modified to meet accessibility requirements that are not required by law, may request a DCA waiver.
Note on M45: Note: Cost amounts on application
Note on N45: Due Diligence: Cost amounts at time of Construction Loan Closing (Owner/Contractor agreement, etc.) Enter data with Commencement submission.
Note on O45: Final Allocation: Final Construction Hard Cost amounts (Change Orders, etc.) Enter data with Architectural 8609 submission.
Note on E48: Note: The "Expected Placed In Service" date is from the DCA generated "Exhibit A: Building Designation" which is an exhibit to the Carryover Letter for projects receiving tax credits.
Note on F51: Note: The date for the "AIA G704 Certificate of Substantial Completion"
Note on B58: 2016 QAP - Core - SECTION 16 - POST AWARD DEADLINES - A. Construction Documents: 1. Construction Documents: For 9% deals, including those utilizing DCA HOME funds, a boundary survey, topographic survey, and geotechnical soils boring report must be submitted to DCA for review and approval no later than 60 days after announcement of awards. Additional Construction Documents will need to be submitted according to Post Award Deadlines and Fees Schedule. b) For HOME deals, please comply with the deadlines in the HOME Commitment Letter.
Note on B62: 2016 QAP - Threshold - XVIII. ACCESSIBILITY STANDARDS : C. Each project selected for allocation is required to retain a "DCA Qualified" consultant to monitor the project for accessibility compliance. The Consultant cannot be a member of the proposed Project Team nor have an Identify of Interest with any member of the proposed Project Team. The DCA qualified consultant must perform the following: (1) a pre-construction plan and specification review to determine that the proposed property will meet all required accessibility requirements. The Consultant report must be included with the Step 2 construction documents submitted to DCA. At a minimum, the report will include the initial comments from the consultant, all documents related to resolution of identified accessibility issues and a certification from the consultant that the plans appear to meet all accessibility requirements. (2) provided at least two training sessions to the General Contractor and Subcontractors regarding accessibility requirements. One training must be on site. (3) an inspection of the construction site after framing is completed to determine that the property is following the approved plans and specifications as to accessibility. DCA must receive a copy of the report issued by the consultant as well as documentation that all issues, if any, have been resolved. (4) a final inspection of the property after completion of construction to determine that the property has been constructed in accordance with all accessibility requirements. DCA must receive a copy of the report issued by the consultant as well as documentation that all issues, if any, have been resolved prior to submission of the project cost certification.
Note on B63: 2016 QAP - Threshold Criteria: XVIII. ACCESSIBILITY STANDARDS: (2) provided at least two training sessions to the General Contractor and Subcontractors regarding accessibility requirements. One training must be on site.
Note on B75: 2016 QAP - Core- EXHIBIT A - DCA POST AWARD DEADLINES AND FEE SCHEDULE Construction Documents as fully outlined in the Architectural Manual HOME Deadline: No later than May 1, 2017 (HOME projects may have more stringent deadlines)
Note on B86: Assumptions & Conditions Status Update Narrative: Provide a narrative that identifies each GHFA Letter of Determination "Assumptions & Conditions" of Funding section and provides a status update of each condition. Restate each "Assumptions & Conditions" verbatim from the Letter of Determination before each response. Note: - Only need to respond to items related to the Construction Services Department requirements
Note on B93: 2015 QAP - Core- EXHIBIT A - DCA POST AWARD DEADLINES AND FEE SCHEDULE HOME Loan Closing: On or before July 14, 2017
Note on B105: 2016 QAP - Core- EXHIBIT A - DCA POST AWARD DEADLINES AND FEE SCHEDULE Commencement of Construction/Rehabilitation (Projects w/Tax Credit and HOME) HOME Deadline: Must satisfy all conditions necessary to commence construction within 9 months of date of the initial preliminary HOME award

## 2016 HOME NOFA
GEORGIA DEPARTMENT OF COMMUNITY AFFAIRS | [9 empty] | HOME NOFA ONLY
Office of Housing Finance & Development
Construction Services Department
60 Executive Park South, NE, Atlanta, GA 30329-2231
2016 DCA CONSTRUCTION SERVICES TRANSMITTAL | [11 empty] | Form Date: | 06.20.2017
|  | DCA PROJECT #: |  | (2016-000) | [6 empty] | DATE:
PROJECT NAME:
DEVELOPER CONTACT | [8 empty] | BUILDING SCHEDULE
| Company: | [7 empty] | Residential Buildings
| Name: | [7 empty] | #Bldgs. | Bldg. Type |  | Conditioned SF | Covered SF
Email:
Phone:
PROJECT TEAM
Architect:
Contractor:
|  |  |  | Identity of Interest?: |  |  |  | Total: | 0 |  |  | 0 | 0
| Accessibility: | [7 empty] | Accessory Buildings (non-residential)
[9 empty] | #Bldgs. | Bldg. Type |  | Conditioned SF | Covered SF
PROPERTY ADDRESS
Street:
| City: |  |  | ZIP:
| County: | [6 empty] | Total: | 0 |  |  | 0 | 0
| Geo Coord: | Latitude: |  | Longitude
|  |  | (00.000000) |  | (00.000000) |  |  |  |  | UNIT SCHEDULE
PROJECT DESCRIPTION | [9 empty] | Residential Units
|  |  | Scattered Site?: | [6 empty] | #Units | #Bedrms. | #Bathrms. | Total Net SF
|  |  | If Yes, How Many Properties?: | [10 empty] | 0
0
|  |  | Tenancy1: | [10 empty] | 0
|  |  | Tenancy2: | [10 empty] | 0
0
|  |  | Constr. Type1: | [10 empty] | 0
|  |  | Constr. Type2: | [5 empty] | Total: | 0 | 0 |  | 0 | 0 | # of bedrms.
Accessibility Units
|  |  | Acreage: | [6 empty] | Total # of Mobility Impaired Units:
# of M.I. Units With "Roll-in Showers":
PROJECT SCHEDULE | [9 empty] | # of Sight / Hearing Impaired Units:
Notice to Proceed
|  |  | Estimated Date: |  |  |  | HARD COSTS
|  |  | Actual Date: |  |  |  | Description |  |  |  | Award | Due Dill. | Final Alloc.
Contractor Hard Costs:
|  |  |  | Placed in Service |  |  | Other Construction Hard Cost:
|  |  | DCA "Expected" PIS Date: |  |  |  | Construction Contingency:
|  |  | Last Residential Bldg. "Actual" PIS Date: | [6 empty] | Total Hard Costs: | 0 | 0 | 0
|  |  |  | Substantial Completion |  |  | Cost Per Unit Net SF: |  |  |  | #DIV/0! | #DIV/0! | #DIV/0!
|  |  | Estimated Date: |  |  |  | Cost Per Unit: |  |  |  | #DIV/0! | #DIV/0! | #DIV/0!
|  |  | Actual Date: |  |  |  | Cost Per Bedrm.: |  |  |  | #DIV/0! | #DIV/0! | #DIV/0!
*** DO NOT COMBINE THE STAGED SUBMISSION PACKAGES (maintain separate binders/flash drives per submission) ***
PLACE AN 'X' IN THE BOX NEXT TO EACH DOCUMENT SUBMITTED
DCA REVIEW SUBMISSION (60 Days Prior to DCA HOME Loan Closing)
01 | ALTA/ACSM Land Title Survey
02 | Geotechnical Report (new construction only)
03 | DCA Construction Document Log (Review Set) (drawing log)
04 | DCA "Review Set" of drawings (plans) (see directions for definition of "Review Set")
05 | DCA "Review Set" of Project Manual (specs)
06 | DCA Schedule of Values form (Review Set)
07 | DCA Amenities & Design Options Re-Certification form
08 | Green Building Consultant Agreement - "when applicable" (agreement/proposal/MOUs)
09 | Accessibility Consultant Agreement
10 | Contractor and Subcontractor Accessibility Training Sessions Action Plan (submit a document that states how this will be accomplished)
11 | Owner/Architect Agreement - Executed
12 | Owner/Contractor Agreement - Draft (current A101 Stipulated Sum or A102 Cost of Work Plus Fee With a Guaranteed Maximum Price forms)
13 | Contractor Approval Package (see page 53 of 59 of the 2016 QAP Threshold)
14 | Construction Schedule - Draft
15 | Narrative that identifies each Determination Letter "Assumptions & Conditions" and provides a status update of each condition (Constr Srvcs Dept items)
(ex.: wetlands delineations, noise mitigation plans, etc.) (restate each C.o.F in the narrative)
16 | Federal Work Authorization Affidavits (E-Verify)
17 | DCA Approved Architectural Waivers/Optional Amenities (including evidence of DCA approval)
18 | Other:
DCA#: |  | 0 |  |  |  | Program: | HOME NOFA |  |  |  |  | Page: | 01 of 02
*** DO NOT COMBINE THE STAGED SUBMISSION PACKAGES (maintain separate binders/flash drives per submission) ***
PLACE AN 'X' IN THE BOX NEXT TO EACH DOCUMENT SUBMITTED
LOAN CLOSING SUBMISSION (due prior to DCA Loan Closing )
01 | DCA Construction Document Log (Contract Set) (drawing log)
02 | DCA "Contract Set" of drawings (plans) (see directions for definition of "Contract Set")
03 | DCA "Contract Set" of Project Manual (specs)
04 | Addendum incorporating/outlining revisions from DCA Review Set into the DCA Contract Set
05 | DCA Schedule of Values form (Contract Set)
06 | DCA Amenities & Design Options Re-Certification form
07 | Owner/Contractor Agreement - Executed
08 | DCA Approved Architectural Waivers/Optional Amenities (including evidence of DCA approval)
09 | Other:
COMMENCEMENT SUBMISSION (due within 30 days of construction commencement)
01 | Notice to Proceed
02 | Construction Schedule - Finalized
03 | Permits (Land Development, Building,,,)
04 | Accessibility Consultant Plan Review Comments
05 | Accessibility Consultant Clearance Letter (acknowledgement of plan review comment resolutions)
06 | DCA Approved Architectural Waivers/Optional Amenities (including evidence of DCA approval)
07 | DCA Placed in Service form - Draft with estimated dates (DCA Compliance Dept. form)
08 | Other:
OTHER SUBMISSIONS
01 | Other:
02 | Other:
DCA#: |  | 0 |  |  |  | Program: | HOME NOFA |  |  |  |  | Page: | 02 of 02
Note on A12: DEVELOPER CONTACT FOR DCA CONSTRUCTION SERVICES DEPT.
Note on N14: Note: Gross Building "Conditioned" Square Footage
Note on O14: Note: Gross Building "Covered" Square Footage
Note on N23: Note: Gross Building "Conditioned" Square Footage
Note on O23: Note: Gross Building "Covered" Square Footage
Note on O31: 2016 Architectural Standards - V. BUILDING INTERIORS DESIGN STANDARDS - B. Unit Sizes: Net Rentable (Leasable) Square Footage: This is the DCA definition for calculating “Residential Unit Square Footage” as it pertains to the Architectural Manual and other documents in Qualified Allocation Plan (QAP). It is calculated for each individual dwelling type. The unit net rentable area is measured from the inside face of each of the unit’s perimeter walls. • Net area included air-conditioned space only. • Measure from the inside (paint) face of all unit perimeter walls. • Do not include any patio, balcony, or breezeway areas. • Do not include any outside storage closets. • Do not deduct any interior walls. • Include non-revenue units in total net rentable living area (Total Residential Unit Square Footage)
Note on O40: 2016 Qualified Allocation Plan - Threshold XVIII. ACCESSIBILITY STANDARDS B. Regardless of whether a project anticipates using federal HOME funds as a funding source, all proposed projects must include the following DCA requirements: 1. At least 5% of the total units (but no less than one unit) must be equipped for the mobility disabled, including wheelchair restricted residents. Roll-in showers must be incorporated into 40% of the mobility equipped units (but no fewer than one unit); and 2. At least an additional 2% of the total units (but no less than one unit) must be equipped for hearing and sight-impaired residents. The same unit cannot be used to satisfy the 5% and 2% requirement. Preservation of existing affordable housing that cannot be modified to meet accessibility requirements that are not required by law, may request a DCA waiver.
Note on O41: 2016 Qualified Allocation Plan - Threshold XVIII. ACCESSIBILITY STANDARDS B. Regardless of whether a project anticipates using federal HOME funds as a funding source, all proposed projects must include the following DCA requirements: 1. At least 5% of the total units (but no less than one unit) must be equipped for the mobility disabled, including wheelchair restricted residents. Roll-in showers must be incorporated into 40% of the mobility equipped units (but no fewer than one unit); and 2. At least an additional 2% of the total units (but no less than one unit) must be equipped for hearing and sight-impaired residents. The same unit cannot be used to satisfy the 5% and 2% requirement. Preservation of existing affordable housing that cannot be modified to meet accessibility requirements that are not required by law, may request a DCA waiver.
Note on O42: 2016 Qualified Allocation Plan - Threshold XVIII. ACCESSIBILITY STANDARDS B. Regardless of whether a project anticipates using federal HOME funds as a funding source, all proposed projects must include the following DCA requirements: 1. At least 5% of the total units (but no less than one unit) must be equipped for the mobility disabled, including wheelchair restricted residents. Roll-in showers must be incorporated into 40% of the mobility equipped units (but no fewer than one unit); and 2. At least an additional 2% of the total units (but no less than one unit) must be equipped for hearing and sight-impaired residents. The same unit cannot be used to satisfy the 5% and 2% requirement. Preservation of existing affordable housing that cannot be modified to meet accessibility requirements that are not required by law, may request a DCA waiver.
Note on M45: Note: Cost amounts on application
Note on N45: Due Diligence: Cost amounts at time of Construction Loan Closing (Owner/Contractor agreement, etc.) Enter data with Commencement submission.
Note on O45: Final Allocation: Final Construction Hard Cost amounts (Change Orders, etc.) Enter data with Architectural 8609 submission.
Note on E48: Note: The "Expected Placed In Service" date is from the DCA generated "Exhibit A: Building Designation" which is an exhibit to the Carryover Letter for projects receiving tax credits.
Note on F51: Note: The date for the "AIA G704 Certificate of Substantial Completion"
Note on B58: 2016 QAP - Core- EXHIBIT A - DCA POST AWARD DEADLINES AND FEE SCHEDULE Commencement of Construction/Rehabilitation (Tax Credit Only Projects) 4% Deadline: No later than September 30, 2017
Note on B68: 2016 QAP - Threshold - XVIII. ACCESSIBILITY STANDARDS : C. Each project selected for allocation is required to retain a "DCA Qualified" consultant to monitor the project for accessibility compliance. The Consultant cannot be a member of the proposed Project Team nor have an Identify of Interest with any member of the proposed Project Team. The DCA qualified consultant must perform the following: (1) a pre-construction plan and specification review to determine that the proposed property will meet all required accessibility requirements. The Consultant report must be included with the Step 2 construction documents submitted to DCA. At a minimum, the report will include the initial comments from the consultant, all documents related to resolution of identified accessibility issues and a certification from the consultant that the plans appear to meet all accessibility requirements. (2) provided at least two training sessions to the General Contractor and Subcontractors regarding accessibility requirements. One training must be on site. (3) an inspection of the construction site after framing is completed to determine that the property is following the approved plans and specifications as to accessibility. DCA must receive a copy of the report issued by the consultant as well as documentation that all issues, if any, have been resolved. (4) a final inspection of the property after completion of construction to determine that the property has been constructed in accordance with all accessibility requirements. DCA must receive a copy of the report issued by the consultant as well as documentation that all issues, if any, have been resolved prior to submission of the project cost certification.
Note on B69: 2016 QAP - Threshold Criteria: XVIII. ACCESSIBILITY STANDARDS: (2) provided at least two training sessions to the General Contractor and Subcontractors regarding accessibility requirements. One training must be on site.
Note on B74: Assumptions & Conditions Status Update Narrative: Provide a narrative that identifies each GHFA Letter of Determination "Assumptions & Conditions" of Funding section and provides a status update of each condition. Restate each "Assumptions & Conditions" verbatim from the Letter of Determination before each response. Note: - Only need to respond to items related to the Construction Services Department requirements
Note on B86: 2016 QAP - Core- EXHIBIT A - DCA POST AWARD DEADLINES AND FEE SCHEDULE Commencement of Construction/Rehabilitation (Tax Credit Only Projects) 4% Deadline: No later than September 30, 2017
Note on B98: See award letter for commencement date requirements.

## 2016 NHTF NOFA
GEORGIA DEPARTMENT OF COMMUNITY AFFAIRS | [9 empty] | NHTF NOFA ONLY
Office of Housing Finance & Development
Multifamily Construction Services Department - Attn: Administration
60 Executive Park South, NE, Atlanta, GA 30329-2231
2016 DCA CONSTRUCTION SERVICES TRANSMITTAL | [11 empty] | Form Date: | 06.20.2017
|  | DCA PROJECT #: |  | (2016-000) | [6 empty] | DATE:
PROJECT NAME:
DEVELOPER CONTACT | [8 empty] | BUILDING SCHEDULE
| Company: | [7 empty] | Residential Buildings
| Name: | [7 empty] | #Bldgs. | Bldg. Type |  | Conditioned SF | Covered SF
Email:
Phone:
PROJECT TEAM
Architect:
Contractor:
|  |  |  | Identity of Interest?: |  |  |  | Total: | 0 |  |  | 0 | 0
| Accessibility: | [7 empty] | Accessory Buildings (non-residential)
[9 empty] | #Bldgs. | Bldg. Type |  | Conditioned SF | Covered SF
PROPERTY ADDRESS
Street:
| City: |  |  | ZIP:
| County: | [6 empty] | Total: | 0 |  |  | 0 | 0
| Geo Coord: | Latitude: |  | Longitude
|  |  | (00.000000) |  | (00.000000) |  |  |  |  | UNIT SCHEDULE
PROJECT DESCRIPTION | [9 empty] | Residential Units
|  |  | Scattered Site?: | [6 empty] | #Units | #Bedrms. | #Bathrms. | Total Net SF
|  |  | If Yes, How Many Properties?: | [10 empty] | 0
0
|  |  | Tenancy1: | [10 empty] | 0
|  |  | Tenancy2: | [10 empty] | 0
0
|  |  | Constr. Type1: | [10 empty] | 0
|  |  | Constr. Type2: | [5 empty] | Total: | 0 | 0 |  | 0 | 0 | # of bedrms.
Accessibility Units
|  |  | Acreage: | [6 empty] | Total # of Mobility Impaired Units:
# of M.I. Units With "Roll-in Showers":
PROJECT SCHEDULE | [9 empty] | # of Sight / Hearing Impaired Units:
Notice to Proceed
|  |  | Estimated Date: |  |  |  | HARD COSTS
|  |  | Actual Date: |  |  |  | Description |  |  |  | Award | Due Dill. | Final Alloc.
Contractor Hard Costs:
|  |  |  | Placed in Service |  |  | Other Construction Hard Cost:
|  |  | DCA "Expected" PIS Date: |  |  |  | Construction Contingency:
|  |  | Last Residential Bldg. "Actual" PIS Date: | [6 empty] | Total Hard Costs: | 0 | 0 | 0
|  |  |  | Substantial Completion |  |  | Cost Per Unit Net SF: |  |  |  | #DIV/0! | #DIV/0! | #DIV/0!
|  |  | Estimated Date: |  |  |  | Cost Per Unit: |  |  |  | #DIV/0! | #DIV/0! | #DIV/0!
|  |  | Actual Date: |  |  |  | Cost Per Bedrm.: |  |  |  | #DIV/0! | #DIV/0! | #DIV/0!
*** DO NOT COMBINE THE STAGED SUBMISSION PACKAGES (maintain separate binders/flash drives per submission) ***
PLACE AN 'X' IN THE BOX NEXT TO EACH DOCUMENT SUBMITTED
DCA REVIEW SUBMISSION (60 Days Prior to DCA Loan Closing)
01 | ALTA/ACSM Land Title Survey
02 | Geotechnical Report (new construction only)
03 | DCA Construction Document Log (Review Set) (drawing log)
04 | DCA "Review Set" of drawings (plans) (see directions for definition of "Review Set")
05 | DCA "Review Set" of Project Manual (specs)
06 | DCA Schedule of Values form (Review Set)
07 | Other Construction Hard Cost Work Scope (support documentation)
08 | DCA Amenities & Design Options Re-Certification form
09 | Green Building Consultant Agreement - "when applicable" (agreement/proposal/MOUs)
10 | Accessibility Consultant Agreement
11 | Contractor and Subcontractor Accessibility Training Sessions Action Plan (submit a document that states how this will be accomplished)
12 | Owner/Architect Agreement - Executed
13 | Owner/Contractor Agreement - Draft (current A101 Stipulated Sum or A102 Cost of Work Plus Fee With a Guaranteed Maximum Price forms)
14 | Contractor Approval Package (see page 56 of 61 of the 2017 QAP Threshold)
15 | Construction Schedule - Draft
16 | Narrative that identifies each Determination Letter "Assumptions & Conditions" and provides a status update of each condition (Constr Srvcs Dept items)
(ex.: wetlands delineations, noise mitigation plans, etc.) (restate each C.o.F in the narrative)
17 | Federal Work Authorization Affidavits (E-Verify)
18 | DCA Approved Architectural Waivers/Optional Amenities (including evidence of DCA approval)
19 | Other:
DCA#: |  | 0 |  |  |  | Program: | NHTF NOFA |  |  |  |  | Page: | 01 of 02
LOAN CLOSING SUBMISSION (due prior to DCA Loan Closing )
01 | DCA Construction Document Log (Contract Set) (drawing log)
02 | DCA "Contract Set" of drawings (plans) (see directions for definition of "Contract Set")
03 | DCA "Contract Set" of Project Manual (specs)
04 | Addendum incorporating/outlining revisions from DCA Review Set into the DCA Contract Set
05 | DCA Schedule of Values form (Contract Set)
06 | Other Construction Hard Cost Work Scope (support documentation)
07 | DCA Amenities & Design Options Re-Certification form
08 | Owner/Contractor Agreement - Executed
09 | DCA Approved Architectural Waivers/Optional Amenities (including evidence of DCA approval)
10 | Other:
COMMENCEMENT SUBMISSION (due within 30 days of construction commencement)
01 | Notice to Proceed
02 | Construction Schedule - Finalized
03 | Permits (Land Development, Building,,,)
04 | Accessibility Consultant Plan Review Comments
05 | Accessibility Consultant Clearance Letter (acknowledgement of plan review comment resolutions)
06 | DCA Approved Architectural Waivers/Optional Amenities (including evidence of DCA approval)
07 | DCA Placed in Service form - Draft with estimated dates (DCA Compliance Dept. form)
08 | Other:
OTHER SUBMISSIONS
01 | Other:
DCA#: |  | 0 |  |  |  | Program: | NHTF NOFA |  |  |  |  | Page: | 02 of 02
Note on A12: DEVELOPER CONTACT FOR DCA CONSTRUCTION SERVICES DEPT.
Note on N14: Note: Gross Building "Conditioned" Square Footage
Note on O14: Note: Gross Building "Covered" Square Footage
Note on N23: Note: Gross Building "Conditioned" Square Footage
Note on O23: Note: Gross Building "Covered" Square Footage
Note on O31: 2016 Architectural Standards - V. BUILDING INTERIORS DESIGN STANDARDS - B. Unit Sizes: Net Rentable (Leasable) Square Footage: This is the DCA definition for calculating “Residential Unit Square Footage” as it pertains to the Architectural Manual and other documents in Qualified Allocation Plan (QAP). It is calculated for each individual dwelling type. The unit net rentable area is measured from the inside face of each of the unit’s perimeter walls. • Net area included air-conditioned space only. • Measure from the inside (paint) face of all unit perimeter walls. • Do not include any patio, balcony, or breezeway areas. • Do not include any outside storage closets. • Do not deduct any interior walls. • Include non-revenue units in total net rentable living area (Total Residential Unit Square Footage)
Note on M45: Note: Cost amounts on application
Note on N45: Due Diligence: Cost amounts at time of Construction Loan Closing (Owner/Contractor agreement, etc.) Enter data with Commencement submission.
Note on O45: Final Allocation: Final Construction Hard Cost amounts (Change Orders, etc.) Enter data with Architectural 8609 submission.
Note on E48: Note: The "Expected Placed In Service" date is from the DCA generated "Exhibit A: Building Designation" which is an exhibit to the Carryover Letter for projects receiving tax credits.
Note on F51: Note: The date for the "AIA G704 Certificate of Substantial Completion"
Note on B75: Assumptions & Conditions Status Update Narrative: Provide a narrative that identifies each GHFA Letter of Determination "Assumptions & Conditions" of Funding section and provides a status update of each condition. Restate each "Assumptions & Conditions" verbatim from the Letter of Determination before each response. Note: - Only need to respond to items related to the Construction Services Department requirements

## Formulas (hidden)
Formulas
ResBldgType |  | AccBldgType | ConstType
Walk-up |  | Community Bldg. | New
Elevator-Low Rise |  | Combo Bldg. | Rehab
Flat |  | Maintenance Bldg.
Townhome |  | Office Bldg.
Single Family
Elevator-Mid/High Rise