## Instructions
Georgia Department of Community Affairs Office of Housing and Finance Construction Services Department Form Date: 02/14/19
2019 DCA CONSTRUCTION SERVICES SUBMISSION INSTRUCTIONS
Overview
In order to ensure compliance with Georgia DCA’s Architectural Standards for safe, decent, affordable housing, DCA monitors the design and construction of all projects awarded tax credits and/or HOME funds. As such, the project team is required to submit documents to DCA throughout the design and construction process for review, which is accomplished through the Construction Services Department's defined staged submission process.
Each Construction Services (CS) submission comprises of a binder and flash drive which contain both hard and soft copies of the documents required for that submission. The flash drive must contain the appropriate 2019 DCA Construction Services Submittal Folder structure, with the applicable files placed inside of the appropriate subfolders. For the binder, hard copies will be limited to the completed DCA CS transmittal form, project team transmittals/cover letters and as well as original DCA payments/checks when required. When required, the hard copies of the drawings (plans) and project manual (specs) are to be included separate from the binder. The program specific DCA CS Transmittals included in this Excel workbook provides the outline as to what is to be included with each required CS submission. Additional information is provided in the 2019 Architectural Manual and the DCA Award Notices.
NOTE: Do NOT combine multiple staged CS submissions into one binder and one flash drive (maintain separate binders/flash drives for each staged submission package).
Due Dates
Each program specific DCA CS Transmittal form provides the due dates for each required program submission. Note: It is the responsibility of the Owner/Developer to request any necessary extensions.
Complete submission packages may be submitted earlier than the due dates, but documents should not be submitted in piecemeal or from multiple sources (i.e. the plans and specs should NOT be submitted separately by the design firm). DCA will not begin its review until all documents required for a particular submission have been received.
Extension Requests
For unforeseen circumstances, the project team may submit a formal extension request to DCA for consideration. All construction related extension requests must be submitted in writing to:
Donna Tyler Multifamily Construction Service Manager Donna.Tyler@dca.ga.gov (404) 679-3117
NOTE: Any DCA approved submission extension request does NOT extend any other deadlines, in particular, the 10% test.
DCA Construction Services Transmittal Forms
Each CS staged submission must be accompanied by the proper "program specific" 2019 DCA Construction Services Transmittal Form which are included in this Excel workbook and listed below:
• 2019 4% LIHTC Construction Services Transmittal
• 2019 9% LIHTC Construction Services Transmittal
• 2019 HOME 9% Construction Services Transmittal
• 2019 HOME Kresge Construction Services Transmittal
In addition to providing submission due dates, the CS transmittal forms also provide an outline of the documents required for each staged submission.
DCA Construction Services Forms
The CS forms and folder structure that are required as part of the staged submissions are listed below and are available on the Construction Services website page at the following link:
Construction Services Forms
• 2019 DCA Construction Services Transmittal Form (Excel)
• 2019 DCA Schedule of Values Form (Excel)
• 2019 DCA Amenities & Design Options Re‐Certification form (Excel)
• 2019 DCA Construction Document Log (Excel)
• E‐Verify Affidavits (Owner, Developer & Contractor) (Excel)
• 2019 DCA Construction Services Submittal Folder (Zipped Folder)
NOTE: The completed electronic copies must be provided in DCA's original file type format (i.e. Excel file in lieu of converting to PDF).
Paper Submission Requirements
Submit one hard cover binder ("1/2” wide spine) that contains copies of the completed DCA CS Transmittal Form and any applicable project team transmittals/cover letters, as well as DCA payments/checks when required (i.e. final inspection fees). The binder must be clearly labeled with the DCA project number, project name and submission type located on the front cover area. The binder should have plastic insert sleeves on the cover and spine areas.
NOTE: Do NOT include plans and specs in the binder.
All Drawing sheets (Plans) must be printed in DCA's standard archive size of 11x17 (scalable format preferred). There should be one complete bound plan set with one common cover sheet that identifies ALL of the project drawings
NOTE: Civil drawings should NOT be included separate from the main plan set.
The bound Project Manual (specs) should be soft bound with double sided printing.
The DCA project number and project name should be prominently displayed on the cover of both the Drawings and Project Manual (Specs) and should identify that it is either the “DCA Review Set” or the “DCA Contract Set”.
NOTE: DCA is required to archive these submittal docs for 20 plus years so it is very important that both the plan set and the project manual are professionally bound together (i.e. no loose sheets, no binder clips, no rubber bands.)
Electronic Submission Requirements
For each required CS submission provide one "virus-free" USB flash drive that contains enough storage space so that DCA may add additional documents to the drive as needed. The flash drive should contain an external identifying label/tag and "leash". A clear 2-3 ring plastic “zip lock” type pouch (heavy duty freezer type zip bag is acceptable) insert should be included inside the binder front area to contain the flash drive.
NOTE: Do NOT email these files.
The flash drive must contain the appropriate 2019 DCA Construction Services Submittal Folder, with the applicable files placed inside of the appropriate subfolders. For the provided drawings folder, add additional subfolders for each discipline (i.e. Architectural, Structure, Electrical) and note the sheet number on each file extension. The project manual is typically provided as a single PDF file but may be subdivided as long as it is organized.
The last section on the DCA CS Transmittal form titled "Other" should be used for additional documents submitted by the project team such as cover letters/internal transmittal forms.
The file extension names should be short as possible and NOT contain special characters (i.e.. $, &, #, %, *, / , \, etc.). All DCA forms should be submitted using the original file format (i.e. don't convert an Excel file type to a PDF).
Additional Submission Instructions
Double‐check the flash drive folders for “junk files” that have been added by software or other non Windows operating systems and remove as needed.
PDF files should have the ability to be searched or edited where feasible.
Electronic drawing file extensions must be labeled at minimum with the drawing page number which corresponds to the DCA Construction Document Log.
Only one project submission should be included per flash drive and binder (do NOT combine submissions).
Copies of all submitted paper documents should be included in the flash drive, including any delivery cover letters.
Definitions
DCA Review Set:
The set of Construction Documents (CDs) that will be submitted to the local building authority for review in order to obtain the permit for construction. These CDs would be expected to be at least 90% complete.
DCA Contract Set:
The set of Construction Documents (CDs) that are incorporated into the executed Owner/Contractor Agreement. These CDs would be expected to be 100% complete and should have incorporated the local building authority comments from the permitting process as well as comments from the syndicator/lender review, DCA review, accessibility consultant review, and all other consultant's design review comments (green building, historic preservation, etc.).
NOTE: If special circumstances arise where NOT all of the review comments/revisions are incorporated into the Contract Set at the time of the execution of the Owner/Contractor Agreement and will be incorporated into the Construction Documents at a later date (i.e. Change Order), then the Architect should provide a document identifying the missing elements.
DCA Contract Set Addendum (HOME Projects Only):
The Architect's contract document that identifies the revisions/additions that have occurred between the originally submitted DCA Review Set and the final DCA Contract Set (i.e.. design changes/completion, third party and municipality comments, etc.).
Front End Cost Review (FECR)
For ALL Projects, the Third-Party Front End Cost Review will be required per the appropriate program transmittal form. A Third Party Cost Reviewer DCA Qualifications Package is due with 60 Day Submission for all projects.
A “Qualified Consultant” is any individual who meets the experience requirements and qualifications as dictated in the Submission Requirements section (Third Party Front End Cost Review - FECR) of the 2019 Architectural Manual, Appendix II, Submission Requirements.
Mailing Instructions
Please deliver all submissions to:
Georgia Department of Community Affairs
Multifamily Construction Services Department
Attn: Construction Services Manager 60 Executive Park South NE Atlanta, Georgia 30329‐2231

## 2019 4pct
GEORGIA DEPARTMENT OF COMMUNITY AFFAIRS | [8 empty] | BOND 4%
Office of Housing Finance & Development
Multifamily Construction Services Department - Attn: Construction Services Manager
60 Executive Park South, NE, Atlanta, GA 30329-2231
2019 DCA CONSTRUCTION SERVICES TRANSMITTAL | [12 empty] | 2019-02-14
|  | DCA PROJECT #: |  | (2019-000) | [5 empty] | DATE:
PROJECT NAME:
|  | DEVELOPER CONTACT |  |  |  |  | BUILDING SCHEDULE
| Company: | [5 empty] | Residential Buildings
| Name: | [5 empty] | #Bldgs. | Constr. | Bldg. Type |  | Conditioned SF | Covered SF
Email:
Phone:
PROJECT TEAM
Architect:
Contractor:
Identity of Interest? | [5 empty] | Total: | 0 |  |  |  | 0 | 0
Accessibility:
Accessory Buildings (Non-Residential)
|  | PROPERTY ADDRESS |  |  |  |  | #Bldgs. | Constr. | Bldg. Type |  | Conditioned SF | Covered SF
Street:
City:
| County: |  |  |  |  | Total:
| Geo Coord: | Latitude |  | Longitude |  |  | 0 |  |  |  | 0 | 0
|  |  | (00.000000) |  | (00.000000)
UNIT SCHEDULE
|  | PROJECT DESCRIPTION |  |  |  |  | Residential Units
DCA Scattered Site?: | [6 empty] | #Units |  | #Bedrms. |  | #Bathrms. | Total Net SF |  | 0
If Yes, How Many Properties?: | [13 empty] | 0
| Tenancy1: | [12 empty] | 0
| Tenancy2: | [12 empty] | 0
| Acreage: | [12 empty] | 0
0
[14 empty] | 0 | # of bedrms.
[6 empty] | Total: | 0 |  | 0 |  | 0 | 0
Accessibility Units
Total # of Mobility Impaired Units:
|  |  | PROJECT SCHEDULE | [5 empty] | # of M.I. Units With "Roll-in Showers":
# of Sight / Hearing Impaired Units:
Notice to Proceed
DCA "Expected" Start Date: | [6 empty] | HARD COSTS
Actual NTP Date: | [6 empty] | Description |  |  | Award Amount | 60 Day | Commencement | Final Allocation
Contractor Hard Costs:
|  |  | Placed in Service |  |  |  | Other Construction Hard Costs:
DCA "Expected" PIS Date: | [6 empty] | Construction Contingency:
Last Residential Bldg. "Actual" PIS Date: | [6 empty] | Total Hard Costs: |  |  | 0 | 0 | 0 | 0
|  |  | Substantial Completion |  |  |  | Cost Per Unit Net SF: |  |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
|  | Estimated Date: |  |  |  |  | Cost Per Unit: |  |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
|  | Actual Date: |  |  |  |  | Cost Per Bedrm.: |  |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
*** DO NOT COMBINE THE STAGED SUBMISSION PACKAGES!!! Please Maintain Separate Binders/Flash Drives per Submission) ***
PLACE AN 'X' IN THE BOX NEXT TO EACH DOCUMENT SUBMITTED FOR EACH SECTION
60 DAY SUBMISSION *(Due no later than 60 days after the announcement of Awards)*
01 | DCA Award Letter - (Copy of LOD Letter/Exhibits)
02 | ALTA/ACSM Land Title Survey
03 | Geotechnical Report (New Construction Only)
04 | Accessibility Consultant DCA Qualifications Package --- (Refer to the Accessibility Manual for Requirements)
05 | Accessibility Consultant Agreement
06 | Accessibility Consultant's Training Sessions Action Plan
07 | Green Building Consultant Agreement/Proposal (as applicable)
08 | HERS Rater Consultant Agreement/Proposal
09 | Copy of Rehabilitation Standards Threshold Section "Energy Audit Report (ECM)" that was Due/Submitted with the Application - (Rehab Projects Only)
10 | Third Party Cost Reviewer DCA Qualifications Package - (For All Projects)
11 | DCA Amenities & Design Options Re-Certification Form - (Per the CORE Application)
12 | DCA Approved Architectural Waivers/Optional Amenities - (Including Evidence of DCA Approval)
13 | Other:
| DCA#: | 2019- |  |  |  | Program: | 2019 4-Percent |  |  |  | Page: | 01 of 02
PLACE AN 'X' IN THE BOX NEXT TO EACH DOCUMENT SUBMITTED FOR EACH SECTION
COMMENCEMENT SUBMISSION *(Due within 30 days of Construction Commencement. Any developments that represent an increase of hard costs from the Application Submission of 5% or more are subject to additional cost reasonableness review, supporting documentation requests, and possible project start delay.)*
01 | DCA Construction Document Log - (Contract Set / Drawing Log)
02 | DCA "Contract Set" of Drawings/Plans - (See Instructions for Definition of "Contract Set")
03 | DCA "Contract Set" of Project Manual - (Specifications)
04 | DCA Amenities & Design Options Re-Certification Form
05 | Accessibility Consultant Plan Review Comments
06 | Accessibility Consultant Clearance Letter - (Acknowledgement of Plan Review Comment Resolutions)
07 | DCA Schedule of Values Form - (See Instructions Tab for Definition of "Contract Set")
08 | Other Construction Hard Cost Work Scope - (Support documentation for work not included in the Owner/Contractor Agreement)
09 | Third Party Front-End Cost Review - (For All Projects)
10 | Executed Owner/Contractor Agreement
11 | Narrative that Identifies each Determination Letter "Assumptions & Conditions" and Provides a Status Update of Each Condition - (Construction and Environmental Services Dept. Items Only)
12 | Notice to Proceed (Restate each C.o.F in the Narrative) - (Examples: Wetlands, Delineations, Noise Mitigation Plans, etc.)
13 | Finalized Construction Schedule
14 | Permits - (Land Development, Building, etc.)
15 | DCA Approved Architectural Waivers/Optional Amenities (Including Evidence of DCA Approval)
16 | DCA Placed in Service Form - (Draft with Estimated Dates - DCA Compliance Dept. Form)
17 | Other:
**General reminder that two (2) Accessibility Training Sessions must be completed.**
DCA FINAL INSPECTION SUBMISSION *(Due within 30 days of Final Retainage Pay Application)
01 | Request For Final Construction Compliance Form
02 | Final Inspection Fee ($3,000)
03 | Certificates of Occupancy "CO's"
04 | AIA G704 Certificate of Substantial Completion
05 | Final Contractor Application & Certificate for Payment(s) - (100% Release of Retainage)
06 | Final Contractor Unconditional Lien Waiver
07 | Copies of all Change Orders - (Including support docs included with approved Change Order)
08 | Confirmation of all Project Participants during the Accessibility Training Sessions (Minimum of Two (2) Sessions)
09 | Copies of all Site Inspection Reports performed by the Accessibility Consultant - (Minimum Two (2) Reports per QAP)
10 | Clearance Letter from the Accessibility Consultant (Stating all reported accessibility concerns have been resolved)
11 | DCA Amenities & Design Options Re-Certification Form
12 | DCA Approved Architectural Waivers/Optional Amenities - (Including Evidence of DCA approval)
13 | DCA Placed in Service Form - (DCA Compliance Dept. Form)
14 | Other:
CONTRUCTION 8609 CLEARANCE SUBMISSION *(Due prior to final allocation of resources, which is spelled out in your 2019 LOD Award)*
01 | Green Building Certifications - (where applicable)
02 | Verification from a HERS Rater that Dwelling Unit Air Infiltration Rate meets or exceeds the QAP
03 | Certification Letter from Energy Auditor confirming project compliance with "Energy Audit" requirements of the Rehabilitation Standards Threshold Section
04 | Radon Testing that demonstrates levels below the EPA recommended limits:
a) Include a Radon Report from Radon Professional
b.) Include a Radon Test
05 | Verification of Compliance with each DCA Determination Letter "Condition of Funding"
| a.) Provide a Narrative that describes means of compliance with each Conditions of Funding "CoF" - (restate each C.o.F in the Narrative) - (Construction and Environmental Services Dept. Items Only) | [12 empty] | S
b.) Provide supporting documents/evidence as needed
06 | Contractor Cost Certification
a:) Auditor Opinion Letter
b:) Certification of Independent Certified Public Accountant EXHIBIT B
c:) General Contractor Certification EXHIBIT C
d:) Multifamily Loan Contractor's Cost Certification of Actual Project Costs EXHIBIT D
e:) Contractor’s Cost Certification EXHIBIT E
i:) Line Item Analysis and Explanation EXHIBIT F
ii:) Complete Change Order Log
iii:) A Copy of all Signed Change Orders
iv:) Complete Subcontractor Log
07 | DCA Approved Architectural Waivers/Optional Amenities - (Including Evidence of DCA Approval)
08 | DCA Approved Project Concept Changes - (Including Evidence of DCA Approval)
09 | Other:
OTHER SUBMISSIONS
01 | Other:
02 | Other:
| DCA#: | 2019- |  |  |  | Program: | 2019 4-Percent |  |  |  | Page: 02 of 02
Note on N15: Note: Gross Building "Conditioned" Square Footage
Note on O15: Note: Gross Building "Covered" Square Footage
Note on N25: Note: Gross Building "Conditioned" Square Footage
Note on O25: Note: Gross Building "Covered" Square Footage
Note on O33: 2016 Architectural Standards - V. BUILDING INTERIORS DESIGN STANDARDS - B. Unit Sizes: Net Rentable (Leasable) Square Footage: This is the DCA definition for calculating “Residential Unit Square Footage” as it pertains to the Architectural Manual and other documents in Qualified Allocation Plan (QAP). It is calculated for each individual dwelling type. The unit net rentable area is measured from the inside face of each of the unit’s perimeter walls. • Net area included air-conditioned space only. • Measure from the inside (paint) face of all unit perimeter walls. • Do not include any patio, balcony, or breezeway areas. • Do not include any outside storage closets. • Do not deduct any interior walls. • Include non-revenue units in total net rentable living area (Total Residential Unit Square Footage)
Note on A47: Note: The "Expected" start date is from the DCA generated "Exhibit A: Building Designation" which is an exhibit to the Determination Letter (42m) for Bond projects receiving 4% tax credits.
Note on M48: Note: Cost amounts on application
Note on N48: At 60 Day Submission: Cost amounts at time of Construction Loan Closing (Owner/Contractor agreement, etc.) Enter data with 60 Day Submission.
Note on O48: Due Diligence (due @ Commencement): Cost amounts at time of Construction Loan Closing (Owner/Contractor agreement, etc.) Enter data with Commencement submission.
Note on P48: Final Allocation: Final Construction Hard Cost amounts (Change Orders, etc.) Enter data with Architectural 8609 submission.
Note on A51: Note: The "Expected Placed In Service" date is from the DCA generated "Exhibit A: Building Designation" which is an exhibit to the Determination Letter (42m) for Bond projects receiving 4% tax credits.
Note on E54: Note: The date for the "AIA G704 Certificate of Substantial Completion"
Note on B96: Assumptions & Conditions Status Update Narrative: Provide a narrative that identifies each GHFA Letter of Determination "Assumptions & Conditions" of Funding section and provides a status update of each condition. Restate each "Assumptions & Conditions" verbatim from the Letter of Determination before each response. Note: - Only need to respond to items related to the Construction Services Department requirements
Note on B110: AIA G704 Certificate of Substantial Completion: Submit a copy of this AIA document and include a copy of any list of remaining "punch out items" that were referenced as part of the document.
Note on B111: Final Contractor Application & Certificate for Payment(s) (100% release of retainage): Submit a copy of this AIA document (HUD pay app if applicable). Document should note all added Change Orders.
Note on B112: Final Contractor Application & Certificate for Payment(s) (100% release of retainage): Submit a copy of this AIA document (HUD pay app if applicable). Document should note all added Change Orders.
Note on B130: Conditions of Funding Compliance Narrative: Provide a narrative that includes evidence of compliance with each GHFA Letter of Determination "Assumptions & Conditions" of Funding section. Restate each "Assumptions & Conditions" verbatim from the Letter of Determination before each response describing method of compliance. Provide supporting docs/evidence as needed. Note: - Only need to respond to items related to the Construction Services Department requirements
Note on B144: Note: Submit copies of DCA approved Project Concept Changes that are related to the Construction Services Dept.

## 2019 HOME 9pct
GEORGIA DEPARTMENT OF COMMUNITY AFFAIRS | [8 empty] | HOME 9% TAX CREDIT
Office of Housing Finance & Development
Multifamily Construction Services Department - Attn: Construction Services Manager
60 Executive Park South, NE, Atlanta, GA 30329-2231
2019 DCA CONSTRUCTION SERVICES TRANSMITTAL | [12 empty] | 2019-02-14
|  | DCA PROJECT #: |  |  | (2019-000) |  |  |  |  | DATE:
PROJECT NAME:
|  | DEVELOPER CONTACT |  |  |  |  | BUILDING SCHEDULE
| Company: | [5 empty] | Residential Buildings
| Name: | [5 empty] | #Bldgs. | Constr. | Bldg. Type |  | Conditioned SF | Covered SF
Email:
Phone:
PROJECT TEAM
Architect:
Contractor:
Identity of Interest? | [5 empty] | Total: | 0 |  |  |  | 0 | 0
Accessibility:
Accessory Buildings (Non-Residential)
|  | PROPERTY ADDRESS |  |  |  |  | #Bldgs. | Constr. | Bldg. Type |  | Conditioned SF | Covered SF
Street:
City:
| County: |  |  |  |  | Total:
| Geo Coord: | Latitude |  | Longitude |  |  | 0 |  |  |  | 0 | 0
|  |  | (00.000000) |  | (00.000000)
UNIT SCHEDULE
|  | PROJECT DESCRIPTION |  |  |  |  | Residential Units
DCA Scattered Site?: | [6 empty] | #Units |  | #Bedrms. |  | #Bathrms. | Total Net SF
If Yes, How Many Properties?: | [13 empty] | 0
| Tenancy1: | [12 empty] | 0
| Tenancy2: | [12 empty] | 0
| Acreage: | [12 empty] | 0
0
0
[6 empty] | Total: | 0 |  | 0 |  | 0 | 0 |  | 0 | # of bedrms.
Accessibility Units
Total # of Mobility Impaired Units:
|  |  | PROJECT SCHEDULE | [5 empty] | # of M.I. Units With "Roll-in Showers":
# of Sight / Hearing Impaired Units:
Notice to Proceed
DCA "Expected" Start Date: | [6 empty] | HARD COSTS
Actual NTP Date: | [6 empty] | Description |  |  | Award Amount | 60 Day | Commencement | Final Allocation
Contractor Hard Costs:
|  |  | Placed in Service |  |  |  | Other Construction Hard Costs:
DCA "Expected" PIS Date: | [6 empty] | Construction Contingency:
Last Residential Bldg. "Actual" PIS Date: | [6 empty] | Total Hard Costs: |  |  | 0 | 0 | 0 | 0
|  |  | Substantial Completion |  |  |  | Cost Per Unit Net SF: |  |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
|  | Estimated Date: |  |  |  |  | Cost Per Unit: |  |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
|  | Actual Date: |  |  |  |  | Cost Per Bedrm.: |  |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
*** DO NOT COMBINE THE STAGED SUBMISSION PACKAGES!!! Please Maintain Separate Binders/Flash Drives per Submission) ***
PLACE AN 'X' IN THE BOX NEXT TO EACH DOCUMENT SUBMITTED FOR EACH SECTION
60 DAY SUBMISSION *(Due no later than 60 days after the date of the Carryover Allocation and/or HOME Reservation Letter)*
01 | DCA Carryover Award and/or HOME Reservation Letter - (Copy of Letter/Exhibits)
02 | ALTA/ACSM Land Title Survey
03 | Geotechnical Report (New Construction Only)
04 | Contractor Approval Package - (See DCA 2019 QAP Threshold, Underwriting Policies, Paragraph 11. General Contactor)
05 | Accessibility Consultant DCA Qualifications Package - (See Accessibility Manual for Requirements)
06 | Accessibility Consultant Agreement
07 | Accessibility Consultant's Training Sessions Action Plan
08 | Green Building Consultant Agreement/Proposal (as applicable)
09 | HERS Rater Consultant Agreement/Proposal
10 | Copy of Rehabilitation Standards Threshold Section "Energy Audit Report (ECM)" that was Due/Submitted with the Application - (Rehab Projects Only)
11 | Third Party Cost Reviewer DCA Qualification's Package - (For All Projects)
12 | DCA Amenities & Design Options Re-Certification Form - (Per the CORE Application)
13 | DCA Approved Architectural Waivers/Optional Amenities - (Including Evidence of DCA Approval)
14 | Other:
| DCA#: | 2019- |  |  |  | Program: | 2019 HOME 9pct |  |  |  | Page: | 01 of 02
PLACE AN 'X' IN THE BOX NEXT TO EACH DOCUMENT SUBMITTED
DCA REVIEW SUBMISSION *(Due 30 days prior to Construction Loan and no later than May 30, 2020. Any developments that represent an increase of hard costs from the Application Submission of 5% or more are subject to additional cost reasonableness review, supporting documentation requests, and possible project start delay.)*
01 | DCA Construction Document Log - (Review Set/Drawing Log)
02 | DCA "Contract Set" of Drawings/Plans - (See Instructions for Definition of "Review Set")
03 | DCA "Review Set" of Project Manual - (Specifications)
04 | DCA Schedule of Values Form - (Review Set)
05 | DCA Amenities & Design Options Re-Certification Form
06 | Executed Owner/Architect Agreement
07 | Owner/Contractor Agreement (Draft) - Current A101 Stipulated Sum or A102 Cost of Work Plus Fee with a Guaranteed Maximum Price Forms
08 | Other Construction Hard Cost Work Scope - (Support documentation for work not included in Owner/Contractor Agreement )
09 | Third Party Front-End Cost Review - (For All Projects)
10 | Construction Schedule - (Draft)
11 | Narrative that Identifies each Carryover Allocation "Assumptions & Conditions" and Provides a Status Update of Each Condition - (Construction and Environmental Services Dept. Items Only) Restate each C.o.F in the Narrative - (Ex.: Wetlands delineations, Noise Mitigation Plans, etc.
12 | Federal Work Authorization Affidavits - (E-Verify)
13 | DCA Approved Architectural Waivers/Optional Amenities - (Including Evidence of DCA Approval)
14 | Other:
LOAN CLOSING SUBMISSION *(Due 30 days prior to DCA Construction Loan Closing)*
01 | DCA Construction Document Log - (Contract Set / Drawing Log)
02 | DCA "Contract Set" of Drawings/Plans - (See Instructions for Definition of "Contract Set")
03 | DCA "Contract Set" of Project Manual - (Specifications)
04 | Addendum Incorporating/Outlining Revisions from DCA Review Set into the DCA Contract Set
05 | DCA Schedule of Values Form - (Contract Set)
06 | DCA Amenities & Design Options Re-Certification Form
07 | Executed Owner/Contractor Agreement
08 | Other Construction Hard Cost Work Scope - (Support documentation for work not included in the Owner/Contractor Agreement)
08 | DCA Approved Architectural Waivers/Optional Amenities (Including Evidence of DCA Approval)
09 | Other:
COMMENCEMENT SUBMISSION *(Due 30 days before Construction Commencement, and no later than November 15, 2020)*
01 | Notice to Proceed
02 | Construction Schedule - (Finalized)
03 | Permits - (Land Development, Building, etc.)
04 | Accessibility Consultant Plan Review Comments
05 | Accessibility Consultant Clearance Letter - (Acknowledgement of Plan Review Comment Resolutions)
06 | DCA Approved Architectural Waivers/Optional Amenities - (Including Evidence of DCA Approval)
07 | DCA Placed in Service Form - (Draft with Estimated Dates - DCA Compliance Dept. Form)
08 | Other:
OTHER SUBMISSIONS
01 | Other:
*Link to the DCA HOME Final Checklist can be found on DCA's Public Website located here called HOME Project Closeout Documents*
| DCA#: | 2019- |  |  |  | Program: | 2019 Home/9pct |  |  |  | Page: | 02 of 02
Note on N15: Note: Gross Building "Conditioned" Square Footage
Note on O15: Note: Gross Building "Covered" Square Footage
Note on N25: Note: Gross Building "Conditioned" Square Footage
Note on O25: Note: Gross Building "Covered" Square Footage
Note on O33: 2016 Architectural Standards - V. BUILDING INTERIORS DESIGN STANDARDS - B. Unit Sizes: Net Rentable (Leasable) Square Footage: This is the DCA definition for calculating “Residential Unit Square Footage” as it pertains to the Architectural Manual and other documents in Qualified Allocation Plan (QAP). It is calculated for each individual dwelling type. The unit net rentable area is measured from the inside face of each of the unit’s perimeter walls. • Net area included air-conditioned space only. • Measure from the inside (paint) face of all unit perimeter walls. • Do not include any patio, balcony, or breezeway areas. • Do not include any outside storage closets. • Do not deduct any interior walls. • Include non-revenue units in total net rentable living area (Total Residential Unit Square Footage)
Note on A47: Note: The "Expected" start date is from the DCA generated "Exhibit A: Building Designation" which is an exhibit to the Determination Letter (42m) for Bond projects receiving 4% tax credits.
Note on M48: Note: Cost amounts on application
Note on N48: At 60 Day Submission: Cost amounts at time of Construction Loan Closing (Owner/Contractor agreement, etc.) Enter data with 60 Day Submission.
Note on O48: Due Diligence (due @ Commencement): Cost amounts at time of Construction Loan Closing (Owner/Contractor agreement, etc.) Enter data with Commencement submission.
Note on P48: Final Allocation: Final Construction Hard Cost amounts (Change Orders, etc.) Enter data with Architectural 8609 submission.
Note on A51: Note: The "Expected Placed In Service" date is from the DCA generated "Exhibit A: Building Designation" which is an exhibit to the Determination Letter (42m) for Bond projects receiving 4% tax credits.
Note on E54: Note: The date for the "AIA G704 Certificate of Substantial Completion"
Note on B96: Assumptions & Conditions Status Update Narrative: Provide a narrative that identifies each GHFA Letter of Determination "Assumptions & Conditions" of Funding section and provides a status update of each condition. Restate each "Assumptions & Conditions" verbatim from the Letter of Determination before each response. Note: - Only need to respond to items related to the Construction Services Department requirements
Note on A146: RC Connell: Double check that no new issues have arisen since we re‐reviewed the construction closeout package. In some cases, the owner continued to add construction items. We need to make sure we have verified completion & costs of additional items. If new hard costs have been added outside the GC’s workscope, you need to make sure the disbursement template reflects the project cost certification hard costs.
Note on A147: RC Connell: Double check your notes from the review of the final construction closeout package, and make sure we don’t have any outstanding issues. We let several minor issues go in order to get ARRA funds paid, assuming we had one last chance to get what we need. Check, especially, that we received subcontractor lien waivers. Think this was the most often waived final closeout item.
Note on A149: RC Connell: The final inspection should have already been performed in order to release the contractor retainage. It is the owner’s responsibility to contact the inspector in order to obtain a final report to go along with the retainage draw request.
Note on A154: RC Connell: Provide the underwriter with a copy of the approved Contractor Cost Certification (you can use the pile on my desk to make copies); the underwriter should check that the contractor cost certification matches the project cost certification that they received. If it does not, the underwriter should ask the owner for clarification (& copy you).

## 2019 HOME Kresge
GEORGIA DEPARTMENT OF COMMUNITY AFFAIRS | [8 empty] | HOME Kresge
Office of Housing Finance & Development
Multifamily Construction Services Department - Attn: Construction Services Manager
60 Executive Park South, NE, Atlanta, GA 30329-2231
2019 DCA CONSTRUCTION SERVICES TRANSMITTAL | [12 empty] | 2019-02-14
|  | DCA PROJECT #: |  |  | (2019-000) |  |  |  |  | DATE:
PROJECT NAME:
|  | DEVELOPER CONTACT |  |  |  |  | BUILDING SCHEDULE
| Company: | [5 empty] | Residential Buildings
| Name: | [5 empty] | #Bldgs. | Constr. | Bldg. Type |  | Conditioned SF | Covered SF
Email:
Phone:
PROJECT TEAM
Architect:
Contractor:
Identity of Interest? | [5 empty] | Total: | 0 |  |  |  | 0 | 0
Accessibility:
Accessory Buildings (Non-Residential)
|  | PROPERTY ADDRESS |  |  |  |  | #Bldgs. | Constr. | Bldg. Type |  | Conditioned SF | Covered SF
Street:
City:
| County: |  |  |  |  | Total:
| Geo Coord: | Latitude |  | Longitude |  |  | 0 |  |  |  | 0 | 0
|  |  | (00.000000) |  | (00.000000)
UNIT SCHEDULE
|  | PROJECT DESCRIPTION |  |  |  |  | Residential Units
DCA Scattered Site?: | [6 empty] | #Units |  | #Bedrms. |  | #Bathrms. | Total Net SF
If Yes, How Many Properties?: | [13 empty] | 0
| Tenancy1: | [12 empty] | 0
| Tenancy2: | [12 empty] | 0
| Acreage: | [12 empty] | 0
0
0
[6 empty] | Total: | 0 |  | 0 |  | 0 | 0 |  | 0 | # of bedrms.
Accessibility Units
Total # of Mobility Impaired Units:
|  |  | PROJECT SCHEDULE | [5 empty] | # of M.I. Units With "Roll-in Showers":
# of Sight / Hearing Impaired Units:
Notice to Proceed
DCA "Expected" Start Date: | [6 empty] | HARD COSTS
Actual NTP Date: | [6 empty] | Description |  |  | Award Amount | 60 Day | Commencement | Final Allocation
Contractor Hard Costs:
|  |  | Placed in Service |  |  |  | Other Construction Hard Costs:
DCA "Expected" PIS Date: | [6 empty] | Construction Contingency:
Last Residential Bldg. "Actual" PIS Date: | [6 empty] | Total Hard Costs: |  |  | 0 | 0 | 0 | 0
|  |  | Substantial Completion |  |  |  | Cost Per Unit Net SF: |  |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
|  | Estimated Date: |  |  |  |  | Cost Per Unit: |  |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
|  | Actual Date: |  |  |  |  | Cost Per Bedrm.: |  |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
*** DO NOT COMBINE THE STAGED SUBMISSION PACKAGES!!! Please Maintain Separate Binders/Flash Drives per Submission) ***
PLACE AN 'X' IN THE BOX NEXT TO EACH DOCUMENT SUBMITTED
60 DAY SUBMISSION *(Due no later than 60 days after the date of the Carryover Allocation and/or HOME Reservation Letter)*
01 | DCA Carryover Award and/or HOME Reservation Letter - (Copy of Letter/Exhibits)
02 | Geotechnical Report - (New Construction Only)
03 | Contractor Approval Package - (See DCA 2019 QAP Threshold, Underwriting Policies, Paragraph 11. General Contactor)
04 | Accessibility Consultant DCA Qualifications Package - (See Accessibility Manual for Requirements)
05 | Accessibility Consultant Agreement
06 | Accessibility Consultant's Training Sessions Action Plan
07 | Green Building Consultant Agreement/Proposal (as applicable)
08 | HERS Rater Consultant Agreement/Proposal
09 | Copy of Rehabilitation Standards Threshold Section "Energy Audit Report (ECM)" that was Due/Submitted with the Application - (Rehab Projects Only)
10 | Third Party Cost Reviewer DCA Qualification's Package - (For All Projects)
11 | DCA Amenities & Design Options Re-Certification Form - (Per the CORE Application)
12 | DCA Approved Architectural Waivers/Optional Amenities - (Including Evidence of DCA Approval)
13 | Other:
| DCA#: | 2019- |  |  |  | Program: | 2019 HOME/ Kresge |  |  |  | Page: | 01 of 02
PLACE AN 'X' IN THE BOX NEXT TO EACH DOCUMENT SUBMITTED
DCA REVIEW SUBMISSION *(Due 30 days prior to DCA Construction Loan Closing. Any developments that represent an increase of hard costs from the Application Submission of 5% or more are subject to additional cost reasonableness review, supporting documentation requests, and possible project start delay.)*
01 | DCA Construction Document Log - (Review Set/Drawing Log)
02 | DCA "Contract Set" of Drawings/Plans - (See Instructions for Definition of "Review Set")
03 | DCA "Review Set" of Project Manual - (Specifications)
04 | DCA Schedule of Values Form - (Review Set)
05 | DCA Amenities & Design Options Re-Certification Form
06 | Executed Owner/Architect Agreement
07 | Owner/Contractor Agreement (Draft) - Current A101 Stipulated Sum or A102 Cost of Work Plus Fee with a Guaranteed Maximum Price Forms
08 | Other Construction Hard Cost Work Scope - (Support documentation for work not included in Owner/Contractor Agreement )
09 | Third Party Front-End Cost Review - (For All Projects)
10 | Construction Schedule - (Draft)
Narrative that Identifies each Carryover Allocation "Assumptions & Conditions" and Provides a Status Update of Each Condition - (Construction and Environmental Services Dept. Items Only) Restate each C.o.F in the Narrative - (Ex.: Wetlands delineations, Noise Mitigation Plans, etc.
11 | Federal Work Authorization Affidavits - (E-Verify)
12 | DCA Approved Architectural Waivers/Optional Amenities - (Including Evidence of DCA Approval)
13 | Other:
LOAN CLOSING SUBMISSION *(Due 30 days prior to DCA Construction Loan Closing)*
01 | DCA Construction Document Log - (Contract Set / Drawing Log)
02 | DCA "Contract Set" of Drawings/Plans - (See Instructions for Definition of "Contract Set")
03 | DCA "Contract Set" of Project Manual - (Specifications)
04 | Addendum Incorporating/Outlining Revisions from DCA Review Set into the DCA Contract Set
05 | DCA Schedule of Values Form - (Contract Set)
06 | DCA Amenities & Design Options Re-Certification Form
07 | Executed Owner/Contractor Agreement
08 | Other Construction Hard Cost Work Scope - (Support documentation for work not included in the Owner/Contractor Agreement)
08 | DCA Approved Architectural Waivers/Optional Amenities (Including Evidence of DCA Approval)
09 | Other:
COMMENCEMENT SUBMISSION *(Due prior to 30 days of Bond Finance Closing date)*
01 | Notice to Proceed
02 | Construction Schedule - (Finalized)
03 | Permits - (Land Development, Building, etc.)
04 | Accessibility Consultant Plan Review Comments
05 | Accessibility Consultant Clearance Letter - (Acknowledgement of Plan Review Comment Resolutions)
06 | DCA Approved Architectural Waivers/Optional Amenities - (Including Evidence of DCA Approval)
07 | DCA Placed in Service Form - (Draft with Estimated Dates - DCA Compliance Dept. Form)
08 | Other:
OTHER SUBMISSIONS
01 | Other:
* Link to the DCA HOME Final Checklist can be found on DCA's Public Website located here called HOME Project Closeout Documents*
| DCA#: | 2019- |  |  |  | Program: | 2019/ HOME Kresge |  |  |  | Page: | 02 of 02
Note on N15: Note: Gross Building "Conditioned" Square Footage
Note on O15: Note: Gross Building "Covered" Square Footage
Note on N25: Note: Gross Building "Conditioned" Square Footage
Note on O25: Note: Gross Building "Covered" Square Footage
Note on O33: 2016 Architectural Standards - V. BUILDING INTERIORS DESIGN STANDARDS - B. Unit Sizes: Net Rentable (Leasable) Square Footage: This is the DCA definition for calculating “Residential Unit Square Footage” as it pertains to the Architectural Manual and other documents in Qualified Allocation Plan (QAP). It is calculated for each individual dwelling type. The unit net rentable area is measured from the inside face of each of the unit’s perimeter walls. • Net area included air-conditioned space only. • Measure from the inside (paint) face of all unit perimeter walls. • Do not include any patio, balcony, or breezeway areas. • Do not include any outside storage closets. • Do not deduct any interior walls. • Include non-revenue units in total net rentable living area (Total Residential Unit Square Footage)
Note on A47: Note: The "Expected" start date is from the DCA generated "Exhibit A: Building Designation" which is an exhibit to the Determination Letter (42m) for Bond projects receiving 4% tax credits.
Note on M48: Note: Cost amounts on application
Note on N48: At 60 Day Submission: Cost amounts at time of Construction Loan Closing (Owner/Contractor agreement, etc.) Enter data with 60 Day Submission.
Note on O48: Due Diligence (due @ Commencement): Cost amounts at time of Construction Loan Closing (Owner/Contractor agreement, etc.) Enter data with Commencement submission.
Note on P48: Final Allocation: Final Construction Hard Cost amounts (Change Orders, etc.) Enter data with Architectural 8609 submission.
Note on A51: Note: The "Expected Placed In Service" date is from the DCA generated "Exhibit A: Building Designation" which is an exhibit to the Determination Letter (42m) for Bond projects receiving 4% tax credits.
Note on E54: Note: The date for the "AIA G704 Certificate of Substantial Completion"
Note on B96: Assumptions & Conditions Status Update Narrative: Provide a narrative that identifies each GHFA Letter of Determination "Assumptions & Conditions" of Funding section and provides a status update of each condition. Restate each "Assumptions & Conditions" verbatim from the Letter of Determination before each response. Note: - Only need to respond to items related to the Construction Services Department requirements

## 2019 9pct
GEORGIA DEPARTMENT OF COMMUNITY AFFAIRS | [8 empty] | TAX CREDIT 9%
Office of Housing Finance & Development
Multifamily Construction Services Department - Attn: Construction Services Manager
60 Executive Park South, NE, Atlanta, GA 30329-2231
2019 DCA CONSTRUCTION SERVICES TRANSMITTAL | [12 empty] | 2019-02-14
|  | DCA PROJECT #: |  | (2019-000) | [5 empty] | DATE:
PROJECT NAME:
|  | DEVELOPER CONTACT |  |  |  |  | BUILDING SCHEDULE
| Company: | [5 empty] | Residential Buildings
| Name: | [5 empty] | #Bldgs. | Constr. | Bldg. Type |  | Conditioned SF | Covered SF
Email:
Phone:
PROJECT TEAM
Architect:
Contractor:
Identity of Interest? | [5 empty] | Total: | 0 |  |  |  | 0 | 0
Accessibility:
Accessory Buildings (Non-Residential)
|  | PROPERTY ADDRESS |  |  |  |  | #Bldgs. | Constr. | Bldg. Type |  | Conditioned SF | Covered SF
Street:
City:
| County: |  |  |  |  | Total:
| Geo Coord: | Latitude |  | Longitude |  |  | 0 |  |  |  | 0 | 0
|  |  | (00.000000) |  | (00.000000)
UNIT SCHEDULE
|  | PROJECT DESCRIPTION |  |  |  |  | Residential Units
DCA Scattered Site?: | [6 empty] | #Units |  | #Bedrms. |  | #Bathrms. | Total Net SF |  | 0
If Yes, How Many Properties?: | [13 empty] | 0
| Tenancy1: | [12 empty] | 0
| Tenancy2: | [12 empty] | 0
| Acreage: | [12 empty] | 0
0
[14 empty] | 0 | # of bedrms.
[6 empty] | Total: | 0 |  | 0 |  | 0 | 0
Accessibility Units
Total # of Mobility Impaired Units:
|  |  | PROJECT SCHEDULE | [5 empty] | # of M.I. Units With "Roll-in Showers":
# of Sight / Hearing Impaired Units:
Notice to Proceed
DCA "Expected" Start Date: | [6 empty] | HARD COSTS
Actual NTP Date: | [6 empty] | Description |  |  | Award Amount | 60 Day | Commencement | Final Allocation
Contractor Hard Costs:
|  |  | Placed in Service |  |  |  | Other Construction Hard Costs:
DCA "Expected" PIS Date: | [6 empty] | Construction Contingency:
Last Residential Bldg. "Actual" PIS Date: | [6 empty] | Total Hard Costs: |  |  | 0 | 0 | 0 | 0
|  |  | Substantial Completion |  |  |  | Cost Per Unit Net SF: |  |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
|  | Estimated Date: |  |  |  |  | Cost Per Unit: |  |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
|  | Actual Date: |  |  |  |  | Cost Per Bedrm.: |  |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
*** DO NOT COMBINE THE STAGED SUBMISSION PACKAGES!!! Please Maintain Separate Binders/Flash Drives per Submission) ***
PLACE AN 'X' IN THE BOX NEXT TO EACH DOCUMENT SUBMITTED FOR EACH SECTION
60 DAY SUBMISSION *(Due no later than 60 days after the date of the Carryover Allocation Letter)*
01 | DCA Carryover Award Letter - (Copy of Letter/Exhibits)
02 | ALTA/ACSM Land Title Survey
03 | Geotechnical Report (New Construction Only)
04 | Accessibility Consultant DCA Qualifications Package --- (Refer to the Accessibility Manual for Requirements)
05 | Accessibility Consultant Agreement
06 | Accessibility Consultant's Training Sessions Action Plan
07 | Green Building Consultant Agreement/Proposal (as applicable)
08 | HERS Rater Consultant Agreement/Proposal
09 | Copy of Rehabilitation Standards Threshold Section "Energy Audit Report (ECM)" that was Due/Submitted with the Application - (Rehab Projects Only)
10 | Third Party Cost Reviewer DCA Qualifications Package - (For All Projects)
11 | DCA Amenities & Design Options Re-Certification Form - (Per the CORE Application)
12 | DCA Approved Architectural Waivers/Optional Amenities - (Including Evidence of DCA Approval)
13 | Resident Engagement for Occupied Rehabilitation - (Rehab Projects Only)
A.) Methods Used and Number of Participants.
B.) Summary of resident feedback. What did the residence say.
C.) Will the residence feedback be incorporated into the project plans? Why or why not?
14 | Other:
| DCA#: | 2019- |  |  |  | Program: | 2019 9-Percent |  |  |  | Page: | 01 of 02
PLACE AN 'X' IN THE BOX NEXT TO EACH DOCUMENT SUBMITTED FOR EACH SECTION
COMMENCEMENT SUBMISSION *(Due 30 days prior to Construction Commencement. Any developments that represent an increase of hard costs from the Application Submission of 5% or more are subject to additional cost reasonableness review, supporting documentation requests, and possible project start delay.)*
01 | DCA Construction Document Log - (Contract Set / Drawing Log)
02 | DCA "Contract Set" of Drawings/Plans - (See Instructions for Definition of "Contract Set")
03 | DCA "Contract Set" of Project Manual - (Specifications)
04 | DCA Amenities & Design Options Re-Certification Form
05 | Accessibility Consultant Plan Review Comments
06 | Accessibility Consultant Clearance Letter - (Acknowledgement of Plan Review Comment Resolutions)
07 | DCA Schedule of Values Form - (Contract Set)
08 | Other Construction Hard Cost Work Scope - (Support documentation for work not included in the Owner/Contractor Agreement)
09 | Third Party Front-End Cost Review - (For All Projects)
10 | Executed Owner/Contractor Agreement
11 | Narrative that Identifies each Determination Letter "Assumptions & Conditions" and Provides a Status Update of Each Condition - (Construction and Environmental Services Dept. Items Only)
12 | Notice to Proceed (Restate each C.o.F in the Narrative) - (Examples: Wetlands, Delineations, Noise Mitigation Plans, etc.)
13 | Finalized Construction Schedule
14 | Permits - (Land Development, Building, etc.)
15 | DCA Approved Architectural Waivers/Optional Amenities (Including Evidence of DCA Approval)
16 | DCA Placed in Service Form - (Draft with Estimated Dates - DCA Compliance Dept. Form)
17 | Other:
**General reminder that two (2) Accessibility Training Sessions must be completed.**
DCA FINAL INSPECTION SUBMISSION *(Due within 30 days of Final Retainage Certified Pay Application Date)
01 | Request For Final Construction Compliance Form
02 | Final Inspection Fee ($3,000)
03 | Certificates of Occupancy "CO's"
04 | AIA G704 Certificate of Substantial Completion
05 | Final Contractor Application & Certificate for Payment(s) - (100% Release of Retainage)
06 | Final Contractor Unconditional Lien Waiver
07 | Copies of all Change Orders - (Including support docs included with approved Change Order)
08 | Confirmation of all Project Participants during the Accessibility Training Sessions (Minimum of Two (2) Sessions)
09 | Copies of all Site Inspection Reports performed by the Accessibility Consultant - (Minimum Two (2) Reports per QAP)
10 | Clearance Letter from the Accessibility Consultant (Stating all reported accessibility concerns have been resolved)
11 | DCA Amenities & Design Options Re-Certification Form
12 | DCA Approved Architectural Waivers/Optional Amenities - (Including Evidence of DCA approval)
13 | DCA Placed in Service Form - (DCA Compliance Dept. Form)
14 | Other:
CONTRUCTION 8609 CLEARANCE SUBMISSION *(Due prior to final allocation of resources, which is spelled out in your 2019 Carryover Allocation Letter)*
01 | Green Building Certifications - (where applicable)
02 | Verification from a HERS Rater that Dwelling Unit Air Infiltration Rate meets or exceeds the QAP
03 | Certification Letter from Energy Auditor confirming project compliance with "Energy Audit" requirements of the Rehabilitation Standards Threshold Section
04 | Radon Testing that demonstrates levels below the EPA recommended limits:
a) Include a Radon Report from Radon Professional
b.) Include a Radon Test
05 | Verification of Compliance with each DCA Determination Letter "Condition of Funding"
a.) Provide a Narrative that describes means of compliance with each Conditions of Funding "CoF" - (restate each C.o.F in the Narrative) - (Construction and Environmental Services Dept. Items Only)
b.) Provide supporting documents/evidence as needed
06 | Contractor Cost Certification
a:) Auditor Opinion Letter
b:) Certification of Independent Certified Public Accountant EXHIBIT B
c:) General Contractor Certification EXHIBIT C
d:) Multifamily Loan Contractor's Cost Certification of Actual Project Costs EXHIBIT D
e:) Contractor’s Cost Certification EXHIBIT E
i:) Line Item Analysis and Explanation EXHIBIT F
ii:) Complete Change Order Log
iii:) A Copy of all Signed Change Orders
iv:) Complete Subcontractor Log
07 | DCA Approved Architectural Waivers/Optional Amenities - (Including Evidence of DCA Approval)
08 | DCA Approved Project Concept Changes - (Including Evidence of DCA Approval)
09 | Other:
OTHER SUBMISSIONS
01 | Other:
02 | Other:
| DCA#: | 2019- |  |  |  | Program: | 2019 9-Percent |  |  |  | Page: 02 of 02
Note on N15: Note: Gross Building "Conditioned" Square Footage
Note on O15: Note: Gross Building "Covered" Square Footage
Note on N25: Note: Gross Building "Conditioned" Square Footage
Note on O25: Note: Gross Building "Covered" Square Footage
Note on O33: 2016 Architectural Standards - V. BUILDING INTERIORS DESIGN STANDARDS - B. Unit Sizes: Net Rentable (Leasable) Square Footage: This is the DCA definition for calculating “Residential Unit Square Footage” as it pertains to the Architectural Manual and other documents in Qualified Allocation Plan (QAP). It is calculated for each individual dwelling type. The unit net rentable area is measured from the inside face of each of the unit’s perimeter walls. • Net area included air-conditioned space only. • Measure from the inside (paint) face of all unit perimeter walls. • Do not include any patio, balcony, or breezeway areas. • Do not include any outside storage closets. • Do not deduct any interior walls. • Include non-revenue units in total net rentable living area (Total Residential Unit Square Footage)
Note on A47: Note: The "Expected" start date is from the DCA generated "Exhibit A: Building Designation" which is an exhibit to the Determination Letter (42m) for Bond projects receiving 4% tax credits.
Note on M48: Note: Cost amounts on application
Note on N48: At 60 Day Submission: Cost amounts at time of Construction Loan Closing (Owner/Contractor agreement, etc.) Enter data with 60 Day Submission.
Note on O48: Due Diligence (due @ Commencement): Cost amounts at time of Construction Loan Closing (Owner/Contractor agreement, etc.) Enter data with Commencement submission.
Note on P48: Final Allocation: Final Construction Hard Cost amounts (Change Orders, etc.) Enter data with Architectural 8609 submission.
Note on A51: Note: The "Expected Placed In Service" date is from the DCA generated "Exhibit A: Building Designation" which is an exhibit to the Determination Letter (42m) for Bond projects receiving 4% tax credits.
Note on E54: Note: The date for the "AIA G704 Certificate of Substantial Completion"
Note on B99: Assumptions & Conditions Status Update Narrative: Provide a narrative that identifies each GHFA Letter of Determination "Assumptions & Conditions" of Funding section and provides a status update of each condition. Restate each "Assumptions & Conditions" verbatim from the Letter of Determination before each response. Note: - Only need to respond to items related to the Construction Services Department requirements
Note on B113: AIA G704 Certificate of Substantial Completion: Submit a copy of this AIA document and include a copy of any list of remaining "punch out items" that were referenced as part of the document.
Note on B114: Final Contractor Application & Certificate for Payment(s) (100% release of retainage): Submit a copy of this AIA document (HUD pay app if applicable). Document should note all added Change Orders.
Note on B115: Final Contractor Application & Certificate for Payment(s) (100% release of retainage): Submit a copy of this AIA document (HUD pay app if applicable). Document should note all added Change Orders.
Note on B133: Conditions of Funding Compliance Narrative: Provide a narrative that includes evidence of compliance with each GHFA Letter of Determination "Assumptions & Conditions" of Funding section. Restate each "Assumptions & Conditions" verbatim from the Letter of Determination before each response describing method of compliance. Provide supporting docs/evidence as needed. Note: - Only need to respond to items related to the Construction Services Department requirements
Note on B147: Note: Submit copies of DCA approved Project Concept Changes that are related to the Construction Services Dept.

## 2019 HOME 4pct
GEORGIA DEPARTMENT OF COMMUNITY AFFAIRS | [8 empty] | HOME 4%
Office of Housing Finance & Development
Multifamily Construction Services Department - Attn: Construction Services Manager
60 Executive Park South, NE, Atlanta, GA 30329-2231
2019 DCA CONSTRUCTION SERVICES TRANSMITTAL | [12 empty] | 2019-02-14
|  | DCA PROJECT #: |  |  | (2019-000) |  |  |  |  | DATE:
PROJECT NAME:
|  | DEVELOPER CONTACT |  |  |  |  | BUILDING SCHEDULE
| Company: | [5 empty] | Residential Buildings
| Name: | [5 empty] | #Bldgs. | Constr. | Bldg. Type |  | Conditioned SF | Covered SF
Email:
Phone:
PROJECT TEAM
Architect:
Contractor:
Identity of Interest? | [5 empty] | Total: | 0 |  |  |  | 0 | 0
Accessibility:
Accessory Buildings (Non-Residential)
|  | PROPERTY ADDRESS |  |  |  |  | #Bldgs. | Constr. | Bldg. Type |  | Conditioned SF | Covered SF
Street:
City:
| County: |  |  |  |  | Total:
| Geo Coord: | Latitude |  | Longitude |  |  | 0 |  |  |  | 0 | 0
|  |  | (00.000000) |  | (00.000000)
UNIT SCHEDULE
|  | PROJECT DESCRIPTION |  |  |  |  | Residential Units
DCA Scattered Site?: | [6 empty] | #Units |  | #Bedrms. |  | #Bathrms. | Total Net SF
If Yes, How Many Properties?: | [13 empty] | 0
| Tenancy1: | [12 empty] | 0
| Tenancy2: | [12 empty] | 0
| Acreage: | [12 empty] | 0
0
0
[6 empty] | Total: | 0 |  | 0 |  | 0 | 0 |  | 0 | # of bedrms.
Accessibility Units
Total # of Mobility Impaired Units:
|  |  | PROJECT SCHEDULE | [5 empty] | # of M.I. Units With "Roll-in Showers":
# of Sight / Hearing Impaired Units:
Notice to Proceed
DCA "Expected" Start Date: | [6 empty] | HARD COSTS
Actual NTP Date: | [6 empty] | Description |  |  | Award Amount | 60 Day | Commencement | Final Allocation
Contractor Hard Costs:
|  |  | Placed in Service |  |  |  | Other Construction Hard Costs:
DCA "Expected" PIS Date: | [6 empty] | Construction Contingency:
Last Residential Bldg. "Actual" PIS Date: | [6 empty] | Total Hard Costs: |  |  | 0 | 0 | 0 | 0
|  |  | Substantial Completion |  |  |  | Cost Per Unit Net SF: |  |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
|  | Estimated Date: |  |  |  |  | Cost Per Unit: |  |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
|  | Actual Date: |  |  |  |  | Cost Per Bedrm.: |  |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
*** DO NOT COMBINE THE STAGED SUBMISSION PACKAGES!!! Please Maintain Separate Binders/Flash Drives per Submission) ***
PLACE AN 'X' IN THE BOX NEXT TO EACH DOCUMENT SUBMITTED
60 DAY SUBMISSION *(Due no later than 60 days after the date of the Carryover Allocation and/or HOME Reservation Letter)*
01 | DCA Carryover Award and/or HOME Reservation Letter - (Copy of Letter/Exhibits)
02 | Geotechnical Report - (New Construction Only)
03 | Contractor Approval Package - (See DCA 2019 QAP Threshold, Underwriting Policies, Paragraph 11. General Contactor)
04 | Accessibility Consultant DCA Qualifications Package - (See Accessibility Manual for Requirements)
05 | Accessibility Consultant Agreement
06 | Accessibility Consultant's Training Sessions Action Plan
07 | Green Building Consultant Agreement/Proposal (as applicable)
08 | HERS Rater Consultant Agreement/Proposal
09 | Copy of Rehabilitation Standards Threshold Section "Energy Audit Report (ECM)" that was Due/Submitted with the Application - (Rehab Projects Only)
10 | Third Party Cost Reviewer DCA Qualification's Package ( For All Projects )
11 | DCA Amenities & Design Options Re-Certification Form - (Per the CORE Application)
12 | DCA Approved Architectural Waivers/Optional Amenities - (Including Evidence of DCA Approval)
13 | Other:
| DCA#: | 2019- |  |  |  | Program: | 2019 HOME 4pct |  |  |  | Page: | 01 of 02
PLACE AN 'X' IN THE BOX NEXT TO EACH DOCUMENT SUBMITTED
DCA REVIEW SUBMISSION *(Due 30 days prior to DCA Construction Loan Closing. Any developments that represent an increase of hard costs from the Application Submission of 5% or more are subject to additional cost reasonableness review, supporting documentation requests, and possible project start delay.)*
01 | DCA Construction Document Log - (Review Set/Drawing Log)
02 | DCA "Contract Set" of Drawings/Plans - (See Instructions for Definition of "Review Set")
03 | DCA "Review Set" of Project Manual - (Specifications)
04 | DCA Schedule of Values Form - (Review Set)
05 | DCA Amenities & Design Options Re-Certification Form
06 | Executed Owner/Architect Agreement
07 | Owner/Contractor Agreement (Draft) - Current A101 Stipulated Sum or A102 Cost of Work Plus Fee with a Guaranteed Maximum Price Forms
08 | Other Construction Hard Cost Work Scope - (Support documentation for work not included in Owner/Contractor Agreement )
09 | Third Party Front-End Cost Review ( For All Projects )
10 | Construction Schedule - (Draft)
Narrative that Identifies each Carryover Allocation "Assumptions & Conditions" and Provides a Status Update of Each Condition - (Construction and Environmental Services Dept. Items Only) Restate each C.o.F in the Narrative - (Ex.: Wetlands delineations, Noise Mitigation Plans, etc.)
11 | Federal Work Authorization Affidavits - (E-Verify)
12 | DCA Approved Architectural Waivers/Optional Amenities - (Including Evidence of DCA Approval)
13 | Other:
LOAN CLOSING SUBMISSION *(Due 30 days prior to DCA Construction Loan Closing)*
01 | DCA Construction Document Log - (Contract Set / Drawing Log)
02 | DCA "Contract Set" of Drawings/Plans - (See Instructions for Definition of "Contract Set")
03 | DCA "Contract Set" of Project Manual - (Specifications)
04 | Addendum Incorporating/Outlining Revisions from DCA Review Set into the DCA Contract Set
05 | DCA Schedule of Values Form - (Contract Set)
06 | DCA Amenities & Design Options Re-Certification Form
07 | Executed Owner/Contractor Agreement
08 | Other Construction Hard Cost Work Scope - (Support documentation for work not included in the Owner/Contractor Agreement)
08 | DCA Approved Architectural Waivers/Optional Amenities (Including Evidence of DCA Approval)
09 | Other:
COMMENCEMENT SUBMISSION *(Due prior to 30 days of Bond Finance Closing date)*
01 | Notice to Proceed
02 | Construction Schedule - (Finalized)
03 | Permits - (Land Development, Building, etc.)
04 | Accessibility Consultant Plan Review Comments
05 | Accessibility Consultant Clearance Letter - (Acknowledgement of Plan Review Comment Resolutions)
06 | DCA Approved Architectural Waivers/Optional Amenities - (Including Evidence of DCA Approval)
07 | DCA Placed in Service Form - (Draft with Estimated Dates - DCA Compliance Dept. Form)
08 | Other:
OTHER SUBMISSIONS
01 | Other:
* Link to the DCA HOME Final Checklist can be found on DCA's Public Website located here called HOME Project Closeout Documents*
| DCA#: | 2019- |  |  |  | Program: | 2019 HOME 4pct |  |  |  | Page: | 02 of 02
Note on N15: Note: Gross Building "Conditioned" Square Footage
Note on O15: Note: Gross Building "Covered" Square Footage
Note on N25: Note: Gross Building "Conditioned" Square Footage
Note on O25: Note: Gross Building "Covered" Square Footage
Note on O33: 2016 Architectural Standards - V. BUILDING INTERIORS DESIGN STANDARDS - B. Unit Sizes: Net Rentable (Leasable) Square Footage: This is the DCA definition for calculating “Residential Unit Square Footage” as it pertains to the Architectural Manual and other documents in Qualified Allocation Plan (QAP). It is calculated for each individual dwelling type. The unit net rentable area is measured from the inside face of each of the unit’s perimeter walls. • Net area included air-conditioned space only. • Measure from the inside (paint) face of all unit perimeter walls. • Do not include any patio, balcony, or breezeway areas. • Do not include any outside storage closets. • Do not deduct any interior walls. • Include non-revenue units in total net rentable living area (Total Residential Unit Square Footage)
Note on A47: Note: The "Expected" start date is from the DCA generated "Exhibit A: Building Designation" which is an exhibit to the Determination Letter (42m) for Bond projects receiving 4% tax credits.
Note on M48: Note: Cost amounts on application
Note on N48: At 60 Day Submission: Cost amounts at time of Construction Loan Closing (Owner/Contractor agreement, etc.) Enter data with 60 Day Submission.
Note on O48: Due Diligence (due @ Commencement): Cost amounts at time of Construction Loan Closing (Owner/Contractor agreement, etc.) Enter data with Commencement submission.
Note on P48: Final Allocation: Final Construction Hard Cost amounts (Change Orders, etc.) Enter data with Architectural 8609 submission.
Note on A51: Note: The "Expected Placed In Service" date is from the DCA generated "Exhibit A: Building Designation" which is an exhibit to the Determination Letter (42m) for Bond projects receiving 4% tax credits.
Note on E54: Note: The date for the "AIA G704 Certificate of Substantial Completion"
Note on B95: Assumptions & Conditions Status Update Narrative: Provide a narrative that identifies each GHFA Letter of Determination "Assumptions & Conditions" of Funding section and provides a status update of each condition. Restate each "Assumptions & Conditions" verbatim from the Letter of Determination before each response. Note: - Only need to respond to items related to the Construction Services Department requirements

## Formulas (hidden)
Formulas
ResBldgType |  | AccBldgType | ConstType
Elevator-Low Rise |  | Combo Bldg. | New
Elevator-Mid/High Rise |  | Community Bldg. | Rehab
Flat |  | Maintenance Bldg.
Single Family |  | Office Bldg.
Townhome
Walk-up