2020 CONTRACTOR COST CERTIFICATION GUIDELINES

The owner/developer should check the auditor and contractor’s submissions before submitting the contractor cost certification with the checklist below and ensure explanations have been provided where required:

- Verify that all forms have been submitted:

  - Auditor opinion letter

  - General Contractor Certification

  - Multifamily Loan Contractor’s Cost Certification of Actual Project Costs

  - Contractor’s Cost Certification

- Verify that the “General Contractor Certification” document has the correct box checked.  If there is an identity of interest, you must provide an additional sheet explaining the relationship.

- Regarding Exhibit E, the “Contractor’s Cost Certification (CCC) form”

  - Is the total in the “Budgeted Amount” column equal to the “Original Contract Sum” as stated in the contract incorporated in the closing documents?

Note: The CCC schedule of values line item distribution should reconcile to the first contractor AIA pay app form (G703) schedule of values line item distribution.

  - Does the total in the “Actual Cost” column (which includes contractor fee) equal the “Contract Sum To Date” amount per the final contractor pay app form (AIA G702/703)?  If not, provide additional supporting payment documents (i.e. off contract invoices, etc.) and an explanation.

Note:  The CCC form is for Hard Costs and should not include off contract expenses incurred by the contractor related to DCA Soft Cost items (i.e. cost incurred for purchasing the payment/performance bond for the owner, etc.).

- Verify the supplemental material has been provided by the contractor:

  - Explanation of changes in the line items from the budget to actual column that exceeds 10% and $10,000.

  - Completed DCA Executed Change Order Log and a copy of each signed change orders (including supporting documents).

* Note that DCA may require additional information such as copies of subcontracts or general ledgers to verify information presented in the certification.