## Instructions
Georgia Department of Community Affairs (DCA)
Office of Housing Finance (OHF)
Construction Services Dept. (CS)
2021 DCA CONSTRUCTION SERVICES (CS) "QAP COMPLIANCE" SUBMISSION INSTRUCTIONS
|  |  | Form Date: | 04.01.22
Overview
In order to ensure compliance with Georgia DCA’s QAP Architectural Standards for safe, decent, affordable housing, DCA monitors the design and construction of all projects awarded tax credits and/or GHFA (HOME) funds. As such, the project team is required to submit QAP compliance documents to DCA throughout the design and construction process for review. This is accomplished through the Construction Services (CS) Department's defined staged CS QAP Compliance submission process. Each staged CS QAP Compliance submission comprises of:
• 2021 DCA Construction Services (CS) QAP Compliance Submission "Transmittal" form
• 2021 DCA Construction Services (CS) QAP Compliance Submission "Folder" structure
The "CS Transmittal form" must be updated for each owner certified submission, and only contain the information that is applicable to that particular submission type. Each of the "program specific" DCA CS transmittal forms included in this Excel workbook provide the "outline" as to what is to be included with each required CS submission.
For the "CS Submission Folders", there is a unique set of staged CS submission folders for each program type. Each staged submission folder name (i.e. "21-000 60day_date00.00.00) needs to have the actual "DCA project number" and the actual "submission date" added to the DCA submission folder name prior to submission.
Additional information is provided for in the 2021 Architectural Manual, 2021 QAP and the DCA award letters.
NOTE: Do NOT combine multiple staged CS submissions into one binder and one flash drive (maintain separate binders/flash drives for each staged submission package).
NOTE: Do NOT submit a "paper set" of project plans and specs (PDF format only).
Due Dates
Each program specific DCA CS Transmittal form provides the due dates for each required program submission.
Complete submission packages may be submitted earlier than the due dates but documents should not be submitted piecemeal, or from multiple sources (i.e. the plans and specs should NOT be submitted separately by the design firm). DCA will not begin its review until all documents required for a particular submission have been received.
Note: It is the responsibility of the Owner/Developer to request any necessary extensions.
Extension Requests
For unforeseen circumstances, the project team may submit a formal extension request to DCA for consideration. All construction related extension requests must be submitted in writing to:
Sherrie Potter, Office of Affordable Housing Assistant Office Director
Sherrie.Potter@dca.ga.gov
(470) 773-2799
NOTE: Any DCA approved submission extension request does NOT extend any other deadlines, in particular, the 10% test.
DCA Construction Services QAP Compliance Forms
The CS QAP Compliance forms and folder structures that are required as part of the staged submissions are listed below and are available on the Construction Services website page at the following link:
Construction Services Web Page
• 2021 DCA Construction Services (CS) QAP Compliance Transmittal form (Excel)
• 2021 DCA Schedule of Values form (Excel)
• 2021 DCA Amenities & Design Options Re‐Certification form (Excel)
• 2021 DCA Construction Document Log (Excel)
• 2021 DCA Construction Inspection Fee Submission form (Excel)
• E‐verify affidavits (owner, developer & contractor) (Excel)
• 2021 DCA Construction Services (CS) QAP Compliance Submission Folder structure (zipped folder)
NOTE: The completed electronic copies must be provided in DCA's original file type format (i.e. Excel file in lieu of converting to PDF).
DCA CS QAP Compliance Submission Transmittal forms
Each CS staged submission must be accompanied by the proper "program specific" 2021 DCA Construction Services Transmittal form which are included in this Excel workbook and listed below:
• 2021 4% LIHTC Construction Services Transmittal
• 2021 9% LIHTC Construction Services Transmittal
• 2021 HOME 9% Construction Services Transmittal
• 2021 HOME 4% NOFA Construction Services Transmittal
• 2021 NHTF 9% NOFA Construction Services Transmittal
• 2021 NHTF 4% NOFA Construction Services Transmittal
The last section on the DCA CS Transmittal form titled "Other" should be used for additional documents submitted by the project team such as cover letters/internal transmittal forms.
DCA CS QAP Compliance Submission Folders
Each submission must contain the applicable CS QAP Compliance Submission Folder structure, with the applicable files placed inside of the appropriate subfolders.
• 21-000 60day_date00.00.00
• 21-000 DCARvw_date00.00.00
• 21-000 LoanClosng_date00.00.00
• 21-000 Commence_date00.00.00
• 21-000 DCAFinalInsp_date00.00.00
• 21-000 Constr8609Clear_date00.00.00
• 21-000 Other_date00.00.00
NOTE: Do not delete unused/empty subfolders (leave subfolder intact, and add "N/A" at the end of the folder name)
Electronic Documents
The file extension names should be short as possible and NOT contain special characters (i.e.. $, &, #, %, *, / , \, etc.).
All completed DCA forms (CS Transmittal, CD Log, DCA SoV,,,) shall be submitted in the Excel format (i.e. don't convert an Excel file type to a PDF).
Drawings
For the provided drawings folder, additional subfolders are provided for each discipline (i.e. Architectural, Structure, Electrical,,,) and the plans should NOT be submitted as one large PDF file. Each drawing sheet should be a single PDF file and contain the sheet ID number on each file extension which corresponds to the DCA Construction Document Log. The project manual is typically provided as a single PDF file but may be subdivided as long as it is organized.
NOTE: The "DCA "project number" and DCA "project name" should be prominently displayed on the "Drawings" plan set cover sheet .
Project Manual (specs)
The project manual is typically provided as a single PDF file but may be subdivided as long as it is organized.
NOTE: The "DCA "project number" and DCA "project name" should be prominently displayed on the "Project Manual" (specs) cover page.
Binder and USB Flash Drive Submission Method ("shipped/delivered" to DCA on-site premises)
Hard Cover Binder
Submit one hard cover 3-ring binder ("1/2” wide spine) that contains the USB flash drive. The binder must be clearly labeled with the DCA "project number", DCA "project name" and CS "submission type" located on the front cover area.
Inside the binder, include a "paper" copy of the completed DCA CS transmittal form, as well as DCA payments/checks when applicable (i.e. final inspection fees,,,).
NOTE: Do NOT submit a full "paper set" of submission documents
USB Flash Drives
For each required CS submission, provide one "virus-free" USB flash drive that contains enough storage space so that DCA may add additional documents to the drive as needed. The flash drive should contain an external identifying label/tag and "leash". A clear 2-3 ring plastic “zip lock” type pouch (heavy duty freezer type zip bag is acceptable) insert should be included inside the binder front area to contain the flash drive.
The flash drive must contain the appropriate "DCA CS QAP Compliance Submission Folder" structure, with the applicable files placed inside of the appropriate subfolders.
Optional Direct Electronic Submission Method (beta)
NOTE: See bottom of form for "Optional Electronic Submission Instructions"
Additional Submission Instructions
Only one project submission should be included per flash drive and binder (do NOT combine submissions).
PDF files should have the ability to be searched or edited where feasible.
Double‐check the submission folders for duplicate “junk files” that have been added by software or other non Windows operating systems and remove as needed.(i.e. Apple computer zip/compression methods,,,)
Definitions
DCA "Review" Set:
The set of Construction Documents (CDs) that will be submitted to the local building authority for review in order to obtain the permit for construction. These CDs would be expected to be at least 90% complete.
DCA "Contract" Set:
The set of Construction Documents (CDs) that are incorporated into the executed Owner/Contractor Agreement. These CDs would be expected to be 100% complete and should have incorporated the local building authority comments from the permitting process as well as comments from the syndicator/lender review, DCA review, accessibility consultant review, and all other consultant's design review comments (green building, historic preservation, etc.).
NOTE: If special circumstances arise where NOT all of the review comments/revisions are incorporated into the Contract Set at the time of the execution of the Owner/Contractor Agreement and will be incorporated into the Construction Documents at a later date (i.e. Change Order), then the Architect should provide a document identifying the missing elements.
DCA Contract Set Addendum (GHFA/HOME projects only):
The Architect's contract document that identifies the revisions/additions that have occurred between the originally submitted DCA Review Set and the final DCA Contract Set (i.e.. design changes/completion, third party and municipality comments, etc.).
Third Party Front End Cost Review - FECR
2021 Qualified Allocation Plan (QAP) – Core: SECTION 11. TAX CREDIT ADMINISTRATION – D. Cost Reasonableness
Front End Cost Review: Owners may not close equity until after the review is complete. A Third-Party Front End Cost Review (“FECR”) of the construction costs must be conducted post-award for projects funded by programs administered through the QAP. DCA must approve the Third-Party Front-End Cost Reviewer’s qualifications beforehand (See Submission Requirements Manual). DCA will have forty-five (45) days to respond to the FECR , plus any days added for questions or clarifications. Owners may not close equity until after the earlier of this time period expiring or DCA’s approval.
CS Submission Clarification Note:
For projects where the FECR Consultant's estimate is within "5%" of the Contractor's "DCA Contract Set" of Construction Documents (CDs) total Hard Cost amount (executed O/C Agreement amount), the FECR report may be submitted to DCA after the Owner's equity closing (due with the Commencement submission).
For projects where the Contractor's "DCA Contract Set" of Construction Documents (CDs) total Hard Cost amount (executed O/C Agreement amount) exceeds the FECR Consultant's estimate by more than "5%", then the FECR report must be submitted to DCA prior to the Owner's equity closing, and where DCA will have forty-five (45) days to respond to the FECR, plus any days added for questions or clarifications.
NOTE: A “Qualified Consultant” is any individual who meets the experience requirements and qualifications as dictated in the Submission Requirements section (Third Party Front End Cost Analysis - FECA) of the 2020 Architectural Manual.
Mailing Instructions
Please deliver all submissions to:
Georgia Department of Community Affairs
Multifamily Construction Services Department
Attn: Administration
60 Executive Park South NE
Atlanta, Georgia 30329‐2231
Optional Direct Electronic Submission Method (beta)
The Construction Services Department is currently “beta testing” a direct electronic submission policy and procedures (in lieu of binder/flash submission) and if you would like to participate, than feel free to submit your “Construction Submission” using the below procedures.
DCA OHF Construction Services (CS) Department - “direct electronic submissions” Policy and Procedures (beta 03.08.22)
The DCA OHF Construction Services (CS) Department is now accepting “direct electronic submissions” for all required (post award) construction QAP Compliance submissions, as dictated by the “DCA CS Transmittal” form. Paper copies, including plans and project manuals (specs), are no longer requested/required to be submitted.
NOTE: This submission method would replace the legacy requirement for the construction submissions to be delivered to DCA via a ½-inch binder/flash drive.
The required CS Transmittal submissions are to be transmitted by electronic means to DCA using the following criteria:
| • | Must submit directly to the “OHFconstructionsubmissions@dca.ga.gov” email account.
NOTE: DCA has dedicated staff for the submission receipt/processing, so please do not send to DCA staff email accounts).
| • | Only submissions required by the project’s “DCA CS QAP Compliance Transmittal” form should be submitted to this email account.
| • | Only one project submission should be included per cloud account submission email/cloud link (do NOT combine submissions).
| • | The email must sent from the Owner/Developer company email account (v.s. a direct submission from a cloud account). The direct email notifications from the cloud services typically do not provide enough information as to who is sending it, and can appear to be "spam". Also, DCA needs to be able to respond directly to the sender and the cloud direct emails do not always allow for that.
| • | The email “Subject” line must include the “DCA Project Number”, the “DCA Project Name” and the name of the “submission type” (i.e. 60day submission,,,).
| • | The program specific DCA “CS Submission Folder” structure must be used, and shall have the “six digit” submission date added at the end of the folder name (i.e. 20-067 60day_date07.15.21)
| • | The completed DCA CS Submission Folder shall be uploaded to the Owner's cloud account, with a “shared” link to the cloud account included in the submission email, that then would be downloaded by DCA staff.
NOTE: The shared link will need to be “generic” since multiple DCA staff would need access for downloading.
| • | As a policy, once the Owner’s certified CS submission folder has been formally submitted to DCA, then the CS folder structure should not be used/resubmitted as part of any requested clarifications needed by the assigned CS Project Manager. In addition, docs should "not" be added to the folder structure that is located on the Owner's cloud account with the intention for DCA staff to retrieve at a later date (after the formal submission date).
NOTE: Any additional needed/revised docs requested by the CS Project Manager during the submission review/approval process would typically be submitted as separate file attachments.
| • | If DCA “denies” the formal submission due to non-compliance issues (i.e. not using the CS submission folder, altering the submission folder structure, submission not 100% complete,,,), then the “revised“ resubmitted Owner’s certified CS submission folder would need to have the “six digit” submission date updated, and “rev” added to the end of the date (i.e. “20-067 60day_date07.20.21rev”).
| • | For any submission that requires a DCA "check" payment (i.e. DCA Final Inspection submission,,,). the check must be sent to DCA prior to that submission. Evidence of payment must be included in the applicable submission folder (i.e. a completed CS Inspection Fee Submission form that includes a copy of the check,,,).
| • | It is the responsibility of the Owner/Developer to confirm that the submission email was received by DCA.
The DCA CS submission forms and submission folder structures are available at the OHF Construction Services webpage “Construction Services ¦ Georgia Department of Community Affairs (ga.gov)”

## 2021 4pct
GEORGIA DEPARTMENT OF COMMUNITY AFFAIRS (DCA) | [9 empty] | 4% TAX CREDIT BOND ONLY
Office of Housing Finance (OHF)
Multifamily Construction Services (CS) Department - Attn: Administration
60 Executive Park South, NE, Atlanta, GA 30329-2231
2021 DCA CONSTRUCTION SERVICES (CS) "QAP COMPLIANCE" TRANSMITTAL | [11 empty] | Form Date: | 04.01.22
|  | DCA PROJECT #: |  | (2021-000) | [5 empty] | SUBMISSION TYPE:
|  | PROJECT NAME: | [7 empty] | FORM CERTIF. DATE:
CERTIF. EMAIL:
DEVELOPER CONTACT | [6 empty] | BUILDING SCHEDULE
| Company: | [5 empty] | Residential Buildings
| Name: | [5 empty] | #Bldgs. | Constr. |  | Bldg. Type |  | Conditioned SF | Covered SF
Email:
Phone:
PROJECT TEAM
Architect:
Contractor:
|  |  |  | Identity of Interest?: |  | Total: | 0 |  |  |  |  | 0 | 0
| Accessibility: | [5 empty] | Accessory Buildings (non-residential)
| Inspector: | [5 empty] | #Bldgs. | Constr. |  | Bldg. Type |  | Conditioned SF | Covered SF
FECR:
PROPERTY ADDRESS
| Street: |  |  |  |  | Total: | 0 |  |  |  |  | 0 | 0
| City: |  |  | ZIP:
| County: | [8 empty] | UNIT SCHEDULE (unit mix breakdown)
| Geo Coord: | Latitude: |  | Longitude | [5 empty] | Residential Units
|  |  | (00.000000) |  | (00.000000) |  |  |  |  | #Units | #Bedrms. | #Bathrms. | Total Net SF
PROJECT DESCRIPTION | [13 empty] | 0
|  |  | DCA Scattered Site?: | [10 empty] | 0
|  |  | If Yes, How Many Properties?: | [10 empty] | 0
0
|  |  | Tenancy1: | [10 empty] | 0
|  |  | Tenancy2: | [10 empty] | 0
[9 empty] | Total: | 0 | 0 |  | 0 | 0 | # of bedrms.
|  |  | Acreage On-site: | [6 empty] | Accessibility Units
|  |  | Acreage Off-site: | [6 empty] | Total # of Mobility Impaired Units:
|  |  | Acreage Total: | 0 | [5 empty] | # of M.I. Units With "Roll-in Showers":
# of Sight / Hearing Impaired Units:
CONTRACT PROJECT SCHEDULE (AIA/HUD)
|  |  |  | Notice to Proceed (NTP) |  |  | USES of FUNDS DEVELOPMENT COSTS - HARD COSTS
|  |  | Current "estimated" NTP Date: |  |  |  | Description |  |  |  | Award | Due Dill. | Final Alloc.
|  |  | Actual NTP Date: |  |  |  | Contractor Hard Costs:
|  |  |  | Contract Time |  |  | Other Construction Hard Cost:
|  |  | Contract # of Days: |  |  |  | Construction Contingency:
|  |  | Actual Contract Start Date: | [6 empty] | Total Hard Costs: | 0 | 0 | 0
|  |  | Change Order # of Days: |  |  |  | Description |  |  |  | Award | Due Dill. | Final Alloc.
|  |  | Total Contract to-date Days: | 0 |  |  | Cost Per Unit Net SF: |  |  |  | #DIV/0! | #DIV/0! | #DIV/0!
|  |  |  | Certificate of Substantial Completion (AIA) |  |  | Cost Per Unit: |  |  |  | #DIV/0! | #DIV/0! | #DIV/0!
|  |  | Current "estimated" Date: |  |  |  | Cost Per Bedrm.: |  |  |  | #DIV/0! | #DIV/0! | #DIV/0!
Actual Project Cert of SC Date:
LIHTC MILESTONES | [6 empty] | USES of FUNDS DEVELOPMENT COSTS - SOFT COSTS
|  |  |  | Placed in Service (PIS) |  |  | Description |  |  |  | Award | Due Dill. | Final Alloc.
|  |  | Current "estimated" PIS Date: |  |  |  | Acquisition - Site Demolition:
Last Residential Bldg. "Actual" PIS Date:
*** DO NOT COMBINE THE STAGED SUBMISSION PACKAGES (maintain separate binders/flash drives per submission) ***
PLACE AN 'X' IN THE BOX NEXT TO EACH DOCUMENT SUBMITTED
60 DAY SUBMISSION (due no later than 60 days after the Date of Letter of Determination - 42m)
01 | DCA Award letter |  |  | (copy of LoD ltr/exhibits)
02 | Awarded QAP Conceptual Site Development Plan (CSD plan) |  |  |  |  | (DCA approved application CSD plan)
03 | Awarded QAP DCA Rehab Work Scope form |  |  |  |  | (DCA approved application DCA Rehab Work Scope form)
04 | ALTA/ACSM Land Title Survey
05 | Geotechnical Report |  |  | (new construction only)
06 | Owner/Architect Agreement - executed
07 | Accessibility Consultant DCA Qualifications Package |  |  |  |  | (see QAP & Accessibility Manual for requirements)
08 | Accessibility Consultant Agreement
09 | Accessibility Contractor and Subcontractor Training Sessions Action Plan (submit a document that states how this will be accomplished) | [10 empty] | (min. two training sessions)
10 | Sustainable Building Certification "draft" scoring sheet for the development and related Consultant Agreement | [9 empty] | (agreement/proposal)
11 | HERS Rater Consultant Agreement - (agreement/proposal)
12 | 3rd Party Front-End Cost Review (FECR) DCA Qualifications Package | [5 empty] | (ALL projects) |  |  | (see QAP & Architectural Manual for requirements)
13 | Construction Compliance Inspector Agreement |  |  |  |  | (ALL projects) |  |  | (see QAP & Architectural Manual for requirements)
14 | DCA Amenities & Design Options Re-Certification form (ADO recert) | [5 empty] | (per the awarded CORE application)
15 | DCA Approved Architectural Waivers/Optional Amenities | [5 empty] | (including evidence of DCA approval)
16 | DCA Approved Project Concept Changes |  |  |  | (including evidence of DCA approval)
17 | Other:
COMMENCEMENT SUBMISSION (due prior to construction commencement which must occur within 30 days of bond finance closing date)
01 | DCA Construction Document Log (drawing log) |  |  |  | (DCA "Contract Set") |  | (see instructions for definition of DCA "Contract Set")
02 | DCA "Contract Set" of drawings (plans) |  |  |  | (DCA "Contract Set") |  | (no paper set required-PDF only)
03 | DCA "Contract Set" of Project Manual (specs) |  |  |  | (DCA "Contract Set") |  | (no paper set required-PDF only)
04 | DCA Schedule of Values form (dca sov) |  |  |  | (DCA "Contract Set")
05 | Accessibility Consultant Plan Review Comments
06 | Accessibility Consultant Clearance Letter |  |  |  | (acknowledgement of "plan review" comment resolutions)
07 | Other Construction Hard Cost Work Scope |  |  |  | (support documentation for hard cost work scope not included in O/C agreement)
08 | Acquisition Soft Cost - Site Demolition Work Scope |  |  |  |  | (support documentation for "soft cost" site demolition work scope )
09 | 3rd Party Front-End Cost Review (FECR) Report |  |  |  |  | (ALL projects) |  |  | (see QAP & Architectural Manual for requirements)
10 | Owner/Contractor Agreement - executed |  |  |  | (DCA Contract Set of Construction Documents)
11 | Narrative that identifies each Determination Letter "Assumptions & Conditions" and provides a status update of each condition
|  | (ex.: wetlands delineations, noise mitigation plans, etc.) |  |  |  | (restate each C.o.F in the narrative) |  |  |  | (Construction Srvcs Dept items only)
12 | Notice to Proceed (NTP) Document |  |  |  | (O/C Agreement notification from Owner to Contractor)
13 | Construction Schedule - Finalized |  |  |  | (must include the "Certificate of Substantial Completion" milestone)
14 | Permits |  | (Land Development, Building,,,)
15 | DCA Placed in Service (PIS) form - draft with estimated dates | [5 empty] | (DCA OPM Compliance Dept. form)
16 | DCA Amenities & Design Options Re-Certification form (ADO recert)
17 | DCA Approved Architectural Waivers/Optional Amenities |  |  |  |  | (including evidence of DCA approval)
18 | DCA Approved Project Concept Changes |  |  |  | (including evidence of DCA approval)
19 | Other:
DCA FINAL INSPECTION SUBMISSION (due within 30 days of final retainage draw certified pay application date)
01 | DCA Construction Inspection Fee Submission form |  |  |  |  | fee: $3000 per QAP project "site" |  |  |  | include copy of check "on" form
02 | Certificates of Occupancy (COs)
03 | AIA G704 Certificate of Substantial Completion |  |  |  |  | (for entire project completion)
04 | Architect Rehab Work Scope Certification Statement |  |  |  |  | (see rehab guide for details)
05 | Final Contractor Application & Certificate for Payment(s) |  |  |  |  | (100% release of retainage)
06 | Final Contractor Unconditional Lien Waiver
07 | Copies of all Change Orders |  |  | (including support docs included with approved Change Order)
08 | Contractor's "Change Order Log" |  |  |  | (this is NOT a DCA form)
09 | Other Construction Hard Cost Work Scope |  |  |  | (support documentation for final hard cost work scope costs "not included" in O/C agreement)
10 | Acquisition Soft Cost- Site Demolition Work Scope |  |  |  |  | (support documentation for final "soft cost" site demolition work scope costs )
11 | Confirmation of Contractor and Subcontractor Accessibility Training Sessions | [7 empty] | (minimum two sessions)
12 | Copies of all site inspection reports performed by the Accessibility Consultant | [7 empty] | (minimum two rpts. per QAP)
13 | Clearance letter from the Accessibility Consultant |  |  |  |  | stating all reported "accessibility concerns" have been resolved
14 | Copies of all "monthly" site inspection reports performed by the Construction Compliance Inspector
15 | DCA Placed in Service (PIS) form |  |  |  | (DCA OPM Compliance Dept. form)
16 | DCA Amenities & Design Options Re-Certification form (ADO recert)
17 | DCA Approved Architectural Waivers/Optional Amenities |  |  |  |  | (including evidence of DCA approval)
18 | DCA Approved Project Concept Changes |  |  |  | (including evidence of DCA approval)
19 | Other:
CONSTRUCTION 8609 CLEARANCE SUBMISSION (due prior to final allocation of resources which is due September 13, 2024 for 2021 LOD Awards)
01 | DCA Construction Document Log (drawing log) |  |  |  | ("As-Built" DCA Contract Set) |  |  |  | (incorporated work scope changes)
02 | ALTA/ACSM As-built Survey
03 | Update endorsement of title insurance policy.
04 | Copy of the DCA "final" site inspection report performed by the Construction Compliance Inspector | [8 empty] | (including DCA Final Checklist)
05 | Sustainable Building Certifications (ALL projects)
06 | Verification from a HERS rater that dwelling unit air infiltration rate meets or exceeds the QAP
07 | Radon Testing that demonstrates levels below the EPA recommended limits | [7 empty] | (ALL projects)
--include a radon report from radon professional
--include a radon tests
08 | Verification of compliance with each DCA Determination Letter "Condition of Funding" | [7 empty] | (Construction Srvcs Dept items only)
| --provide a narrative that describes means of compliance with each Conditions of Funding | [8 empty] | (restate each C.o.F in the narrative)
--provide supporting docs/evidence as needed
09 | Contractor Cost Certification |  |  | (ALL projects)
a: Auditor opinion letter:
b: Certification of Independent Certified Public Accountant EXHIBIT B:
c: General Contractor Certification EXHIBIT C:
d: Multifamily Loan Contractors’ Cost Certification of Actual Project Costs EXHIBIT D:
e: Contractor’s Cost Certification EXHIBIT E:
i: Line item analysis and explanation EXHIBIT F:
ii: Complete change order log:
iii: A copy of all signed change orders:
|  | iv: Provide a completed subcontractor log: |  |  |  | (this is NOT a DCA form)
10 | DCA Amenities & Design Options Re-Certification form (ADO recert)
11 | DCA Approved Architectural Waivers/Optional Amenities | [5 empty] | (including evidence of DCA approval)
12 | DCA Approved Project Concept Changes |  |  |  | (including evidence of DCA approval)
13 | Other:
OTHER CS SUBMISSIONS
01 | Other:
DCA#: |  | 0 |  |  |  | Program: | 2021 4 Percent |  |  |  |  | Date: | 0
Note on A13: DEVELOPER CONTACT FOR DCA CONSTRUCTION SERVICES DEPT.
Note on N15: Note: Gross Building "Conditioned" Square Footage
Note on O15: Note: Gross Building "Covered" Square Footage
Note on N24: Note: Gross Building "Conditioned" Square Footage
Note on O24: Note: Gross Building "Covered" Square Footage
Note on O32: Architectural Standards - V. BUILDING INTERIORS DESIGN STANDARDS - B. Unit Sizes: Net Rentable (Leasable) Square Footage: This is the DCA definition for calculating “Residential Unit Square Footage” as it pertains to the Architectural Manual and other documents in Qualified Allocation Plan (QAP). It is calculated for each individual dwelling type. The unit net rentable area is measured from the inside face of each of the unit’s perimeter walls. • Net area included air-conditioned space only. • Measure from the inside (paint) face of all unit perimeter walls. • Do not include any patio, balcony, or breezeway areas. • Do not include any outside storage closets. • Do not deduct any interior walls. • Include non-revenue units in total net rentable living area (Total Residential Unit Square Footage)
Note on M46: Award Notes: Enter hard cost amounts from "awarded" QAP core application Enter data with "60-day" submission.
Note on N46: Due Diligence Notes: Enter hard cost amounts at time of Construction Loan Closing (executed Owner/Contractor agreement, etc.) Enter data with "Commencement" submission.
Note on O46: Final Allocation Notes: Final construction Hard Cost amounts (Change Orders, etc.) that reflect the Final Allocation Application. Enter data with "Construction 8609" submission.
Note on F53: Note: The date for the "AIA G704 Certificate of Substantial Completion"
Note on M57: Award Notes: Enter hard cost amounts from "awarded" QAP core application Enter data with "60-day" submission.
Note on N57: Due Diligence Notes: Enter hard cost amounts at time of Construction Loan Closing (executed Owner/Contractor agreement, etc.) Enter data with "Commencement" submission.
Note on O57: Final Allocation Notes: Final construction Soft Cost amount that reflect the Final Allocation Application. Enter data with "Construction 8609" submission.
Note on B81: Note: Submit copies of DCA approved Project Concept Changes that are related to the Construction Services Dept.
Note on B94: 2021 QAP: D. Cost Reasonableness Front End Cost Review: Owners may not close equity until after the review is complete. A Third-Party Front End Cost Review (“FECR”) of the construction costs must be conducted post-award for projects funded by programs administered through the QAP. DCA must approve the Third-Party Front-End Cost Reviewer’s qualifications beforehand (See Submission Requirements Manual). DCA will have forty-five (45) days to respond to the FECR , plus any days added for questions or clarifications. Owners may not close equity until after the earlier of this time period expiring or DCA’s approval. CS "Clarification" Note: For projects where the FECR Consultant's estimate is within "5%" of the Contractor's "DCA Contract Set" of Construction Documents (CDs) total Hard Cost amount (executed O/C Agreement amount), the FECR report may be submitted to DCA after the Owner's equity closing (due with the Commencement submission). For projects where the Contractor's "DCA Contract Set" of Construction Documents (CDs) total Hard Cost amount (executed O/C Agreement amount) exceeds the FECR Consultant's estimate by more than "5%", then the FECR report must be submitted to DCA prior to the Owner's equity closing, and where DCA will have forty-five (45) days to respond to the FECR , plus any days added for questions or clarifications.
Note on B96: Assumptions & Conditions Status Update Narrative: Provide a narrative that identifies each GHFA Letter of Determination "Assumptions & Conditions" of Funding section and provides a status update of each condition. Restate each "Assumptions & Conditions" verbatim from the Letter of Determination before each response. Note: - Only need to respond to items related to the Construction Services Department requirements
Note on B104: Note: Submit copies of DCA approved Project Concept Changes that are related to the Construction Services Dept.
Note on B111: AIA G704 Certificate of Substantial Completion: Submit a copy of this AIA document and include a copy of any list of remaining "punch out items" that were referenced as part of the document.
Note on B113: Final Contractor Application & Certificate for Payment(s) (100% release of retainage): Submit a copy of this AIA document (HUD pay app if applicable). Document should note all added Change Orders.
Note on B114: Final Contractor Application & Certificate for Payment(s) (100% release of retainage): Submit a copy of this AIA document (HUD pay app if applicable). Document should note all added Change Orders.
Note on B126: Note: Submit copies of DCA approved Project Concept Changes that are related to the Construction Services Dept.
Note on B140: Conditions of Funding Compliance Narrative: Provide a narrative that includes evidence of compliance with each GHFA Letter of Determination "Assumptions & Conditions" of Funding section. Restate each "Assumptions & Conditions" verbatim from the Letter of Determination before each response describing method of compliance. Provide supporting docs/evidence as needed. Note: - Only need to respond to items related to the Construction Services Department requirements
Note on B155: Note: Submit copies of DCA approved Project Concept Changes that are related to the Construction Services Dept.

## 2021 9pct
GEORGIA DEPARTMENT OF COMMUNITY AFFAIRS (DCA) | [9 empty] | 9% TAX CREDIT ONLY
Office of Housing Finance (OHF)
Multifamily Construction Services (CS) Department - Attn: Administration
60 Executive Park South, NE, Atlanta, GA 30329-2231
2021 DCA CONSTRUCTION SERVICES (CS) "QAP COMPLIANCE" TRANSMITTAL | [11 empty] | Form Date: | 04.01.22
|  | DCA PROJECT #: |  | (2021-000) | [5 empty] | SUBMISSION TYPE:
|  | PROJECT NAME: | [7 empty] | FORM CERTIF. DATE:
CERTIF. EMAIL:
DEVELOPER CONTACT | [6 empty] | BUILDING SCHEDULE
| Company: | [5 empty] | Residential Buildings
| Name: | [5 empty] | #Bldgs. | Constr. |  | Bldg. Type |  | Conditioned SF | Covered SF
Email:
Phone:
PROJECT TEAM
Architect:
Contractor:
|  |  |  | Identity of Interest?: |  | Total: | 0 |  |  |  |  | 0 | 0
| Accessibility: | [5 empty] | Accessory Buildings (non-residential)
| Inspector: | [5 empty] | #Bldgs. | Constr. |  | Bldg. Type |  | Conditioned SF | Covered SF
FECR:
PROPERTY ADDRESS
| Street: |  |  |  |  | Total: | 0 |  |  |  |  | 0 | 0
| City: |  |  | ZIP:
| County: | [8 empty] | UNIT SCHEDULE (unit mix breakdown)
| Geo Coord: | Latitude: |  | Longitude | [5 empty] | Residential Units
|  |  | (00.000000) |  | (00.000000) |  |  |  |  | #Units | #Bedrms. | #Bathrms. | Total Net SF
PROJECT DESCRIPTION | [13 empty] | 0
|  |  | DCA Scattered Site?: | [10 empty] | 0
|  |  | If Yes, How Many Properties?: | [10 empty] | 0
0
|  |  | Tenancy1: | [10 empty] | 0
|  |  | Tenancy2: | [10 empty] | 0
[9 empty] | Total: | 0 | 0 |  | 0 | 0 | # of bedrms.
|  |  | Acreage On-site: | [6 empty] | Accessibility Units
|  |  | Acreage Off-site: | [6 empty] | Total # of Mobility Impaired Units:
|  |  | Acreage Total: | 0 | [5 empty] | # of M.I. Units With "Roll-in Showers":
# of Sight / Hearing Impaired Units:
CONTRACT PROJECT SCHEDULE (AIA/HUD)
|  |  |  | Notice to Proceed (NTP) |  |  | USES of FUNDS DEVELOPMENT COSTS - HARD COSTS
|  |  | Current "estimated" NTP Date: |  |  |  | Description |  |  |  | Award | Due Dill. | Final Alloc.
|  |  | Actual NTP Date: |  |  |  | Contractor Hard Costs:
|  |  |  | Contract Time |  |  | Other Construction Hard Cost:
|  |  | Contract # of Days: |  |  |  | Construction Contingency:
|  |  | Actual Contract Start Date: | [6 empty] | Total Hard Costs: | 0 | 0 | 0
|  |  | Change Order # of Days: |  |  |  | Description |  |  |  | Award | Due Dill. | Final Alloc.
|  |  | Total Contract to-date Days: | 0 |  |  | Cost Per Unit Net SF: |  |  |  | #DIV/0! | #DIV/0! | #DIV/0!
|  |  |  | Certificate of Substantial Completion (AIA) |  |  | Cost Per Unit: |  |  |  | #DIV/0! | #DIV/0! | #DIV/0!
|  |  | Current "estimated" Date: |  |  |  | Cost Per Bedrm.: |  |  |  | #DIV/0! | #DIV/0! | #DIV/0!
Actual Project Cert of SC Date:
LIHTC MILESTONES | [6 empty] | USES of FUNDS DEVELOPMENT COSTS - SOFT COSTS
|  |  |  | Placed in Service (PIS) |  |  | Description |  |  |  | Award | Due Dill. | Final Alloc.
|  |  | Current "estimated" PIS Date: |  |  |  | Acquisition - Site Demolition:
Last Residential Bldg. "Actual" PIS Date:
*** DO NOT COMBINE THE STAGED SUBMISSION PACKAGES (maintain separate binders/flash drives per submission) ***
PLACE AN 'X' IN THE BOX NEXT TO EACH DOCUMENT SUBMITTED
60 DAY SUBMISSION (due no later than 60 days after announcement of awards; or no later than March 30, 2022)
01 | DCA Award letter |  |  | (copy of Carryover ltr/exhibits)
02 | Awarded QAP Conceptual Site Development Plan (CSD plan) |  |  |  |  | (DCA approved application CSD plan)
03 | Awarded QAP DCA Rehab Work Scope form |  |  |  |  | (DCA approved application DCA Rehab Work Scope form)
04 | ALTA/ACSM Land Title Survey
05 | Geotechnical Report |  |  | (new construction only)
06 | Owner/Architect Agreement - executed
07 | Accessibility Consultant DCA Qualifications Package |  |  |  |  | (see QAP & Accessibility Manual for requirements)
08 | Accessibility Consultant Agreement
09 | Accessibility Contractor and Subcontractor Training Sessions Action Plan (submit a document that states how this will be accomplished) | [10 empty] | (min. two training sessions)
10 | Sustainable Building Certification "draft" scoring sheet for the development and related Consultant Agreement | [9 empty] | (agreement/proposal)
11 | HERS Rater Consultant Agreement - (agreement/proposal)
12 | 3rd Party Front-End Cost Review (FECR) DCA Qualifications Package | [5 empty] | (ALL projects) |  |  | (see QAP & Architectural Manual for requirements)
13 | Construction Compliance Inspector Agreement |  |  |  |  | (ALL projects) |  |  | (see QAP & Architectural Manual for requirements)
14 | DCA Amenities & Design Options Re-Certification form (ADO recert) | [5 empty] | (per the awarded CORE application)
15 | DCA Approved Architectural Waivers/Optional Amenities | [5 empty] | (including evidence of DCA approval)
16 | DCA Approved Project Concept Changes |  |  |  | (including evidence of DCA approval)
17 | Other:
COMMENCEMENT SUBMISSION (Prior to construction commencement which must occur no later than November 15, 2022)
01 | DCA Construction Document Log (drawing log) |  |  |  | (DCA "Contract Set") |  | (see instructions for definition of DCA "Contract Set")
02 | DCA "Contract Set" of drawings (plans) |  |  |  | (DCA "Contract Set") |  | (no paper set required-PDF only)
03 | DCA "Contract Set" of Project Manual (specs) |  |  |  | (DCA "Contract Set") |  | (no paper set required-PDF only)
04 | DCA Schedule of Values form (dca sov) |  |  |  | (DCA "Contract Set")
05 | Accessibility Consultant Plan Review Comments
06 | Accessibility Consultant Clearance Letter |  |  |  | (acknowledgement of "plan review" comment resolutions)
07 | Other Construction Hard Cost Work Scope |  |  |  | (support documentation for hard cost work scope not included in O/C agreement)
08 | Acquisition Soft Cost - Site Demolition Work Scope |  |  |  |  | (support documentation for "soft cost" site demolition work scope )
09 | 3rd Party Front-End Cost Review (FECR) Report |  |  |  |  | (ALL projects) |  |  | (see QAP & Architectural Manual for requirements)
10 | Owner/Contractor Agreement - executed |  |  |  | (DCA Contract Set of Construction Documents)
11 | Narrative that identifies each Determination Letter "Assumptions & Conditions" and provides a status update of each condition
|  | (ex.: wetlands delineations, noise mitigation plans, etc.) |  |  |  | (restate each C.o.F in the narrative) |  |  |  | (Construction Srvcs Dept items only)
12 | Notice to Proceed (NTP) Document |  |  |  | (O/C Agreement notification from Owner to Contractor)
13 | Construction Schedule - Finalized |  |  |  | (must include the "Certificate of Substantial Completion" milestone)
14 | Permits |  | (Land Development, Building,,,)
15 | DCA Placed in Service (PIS) form - draft with estimated dates | [5 empty] | (DCA OPM Compliance Dept. form)
16 | DCA Amenities & Design Options Re-Certification form (ADO recert)
17 | DCA Approved Architectural Waivers/Optional Amenities |  |  |  |  | (including evidence of DCA approval)
18 | DCA Approved Project Concept Changes |  |  |  | (including evidence of DCA approval)
19 | Other:
DCA FINAL INSPECTION SUBMISSION (due within 30 days of final retainage draw certified pay application date)
01 | DCA Construction Inspection Fee Submission form |  |  |  |  | fee: $3000 per QAP project "site" |  |  |  | include copy of check "on" form
02 | Certificates of Occupancy (COs)
03 | AIA G704 Certificate of Substantial Completion |  |  |  |  | (for entire project completion)
04 | Architect Rehab Work Scope Certification Statement |  |  |  |  | (see rehab guide for details)
05 | Final Contractor Application & Certificate for Payment(s) |  |  |  |  | (100% release of retainage)
06 | Final Contractor Unconditional Lien Waiver
07 | Copies of all Change Orders |  |  | (including support docs included with approved Change Order)
08 | Contractor's "Change Order Log" |  |  |  | (this is NOT a DCA form)
09 | Other Construction Hard Cost Work Scope |  |  |  | (support documentation for final hard cost work scope costs "not included" in O/C agreement)
10 | Acquisition Soft Cost- Site Demolition Work Scope |  |  |  |  | (support documentation for final "soft cost" site demolition work scope costs )
11 | Confirmation of Contractor and Subcontractor Accessibility Training Sessions | [7 empty] | (minimum two sessions)
12 | Copies of all site inspection reports performed by the Accessibility Consultant | [7 empty] | (minimum two rpts. per QAP)
13 | Clearance letter from the Accessibility Consultant |  |  |  |  | stating all reported "accessibility concerns" have been resolved
14 | Copies of all "monthly" site inspection reports performed by the Construction Compliance Inspector
15 | DCA Placed in Service (PIS) form |  |  |  | (DCA OPM Compliance Dept. form)
16 | DCA Amenities & Design Options Re-Certification form (ADO recert)
17 | DCA Approved Architectural Waivers/Optional Amenities |  |  |  |  | (including evidence of DCA approval)
18 | DCA Approved Project Concept Changes |  |  |  | (including evidence of DCA approval)
19 | Other:
CONSTRUCTION 8609 CLEARANCE SUBMISSION (due prior to final allocation of resources which is due no later than February 15, 2024 for 2021 allocated credits)
01 | DCA Construction Document Log (drawing log) |  |  |  | ("As-Built" DCA Contract Set) |  |  |  | (incorporated work scope changes)
02 | ALTA/ACSM As-built Survey
03 | Update endorsement of title insurance policy.
04 | Copy of the DCA "final" site inspection report performed by the Construction Compliance Inspector | [8 empty] | (including DCA Final Checklist)
05 | Sustainable Building Certifications (ALL projects)
06 | Verification from a HERS rater that dwelling unit air infiltration rate meets or exceeds the QAP
07 | Radon Testing that demonstrates levels below the EPA recommended limits | [7 empty] | (ALL projects)
--include a radon report from radon professional
--include a radon tests
08 | Verification of compliance with each DCA Determination Letter "Condition of Funding" | [7 empty] | (Construction Srvcs Dept items only)
| --provide a narrative that describes means of compliance with each Conditions of Funding | [8 empty] | (restate each C.o.F in the narrative)
--provide supporting docs/evidence as needed
09 | Contractor Cost Certification |  |  | (ALL projects)
a: Auditor opinion letter:
b: Certification of Independent Certified Public Accountant EXHIBIT B:
c: General Contractor Certification EXHIBIT C:
d: Multifamily Loan Contractors’ Cost Certification of Actual Project Costs EXHIBIT D:
e: Contractor’s Cost Certification EXHIBIT E:
i: Line item analysis and explanation EXHIBIT F:
ii: Complete change order log:
iii: A copy of all signed change orders:
|  | iv: Provide a completed subcontractor log: |  |  |  | (this is NOT a DCA form)
10 | DCA Amenities & Design Options Re-Certification form (ADO recert)
11 | DCA Approved Architectural Waivers/Optional Amenities | [5 empty] | (including evidence of DCA approval)
12 | DCA Approved Project Concept Changes |  |  |  | (including evidence of DCA approval)
13 | Other:
OTHER CS SUBMISSIONS
01 | Other:
DCA#: |  | 0 |  |  |  | Program: | 2021 9pct |  |  |  |  | Date: | 0
Note on A13: DEVELOPER CONTACT FOR DCA CONSTRUCTION SERVICES DEPT.
Note on N15: Note: Gross Building "Conditioned" Square Footage
Note on O15: Note: Gross Building "Covered" Square Footage
Note on N24: Note: Gross Building "Conditioned" Square Footage
Note on O24: Note: Gross Building "Covered" Square Footage
Note on O32: Architectural Standards - V. BUILDING INTERIORS DESIGN STANDARDS - B. Unit Sizes: Net Rentable (Leasable) Square Footage: This is the DCA definition for calculating “Residential Unit Square Footage” as it pertains to the Architectural Manual and other documents in Qualified Allocation Plan (QAP). It is calculated for each individual dwelling type. The unit net rentable area is measured from the inside face of each of the unit’s perimeter walls. • Net area included air-conditioned space only. • Measure from the inside (paint) face of all unit perimeter walls. • Do not include any patio, balcony, or breezeway areas. • Do not include any outside storage closets. • Do not deduct any interior walls. • Include non-revenue units in total net rentable living area (Total Residential Unit Square Footage)
Note on M46: Award Notes: Enter hard cost amounts from "awarded" QAP core application Enter data with "60-day" submission.
Note on N46: Due Diligence Notes: Enter hard cost amounts at time of Construction Loan Closing (executed Owner/Contractor agreement, etc.) Enter data with "Commencement" submission.
Note on O46: Final Allocation Notes: Final construction Hard Cost amounts (Change Orders, etc.) that reflect the Final Allocation Application. Enter data with "Construction 8609" submission.
Note on F53: Note: The date for the "AIA G704 Certificate of Substantial Completion"
Note on M57: Award Notes: Enter hard cost amounts from "awarded" QAP core application Enter data with "60-day" submission.
Note on N57: Due Diligence Notes: Enter hard cost amounts at time of Construction Loan Closing (executed Owner/Contractor agreement, etc.) Enter data with "Commencement" submission.
Note on O57: Final Allocation Notes: Final construction Soft Cost amount that reflect the Final Allocation Application. Enter data with "Construction 8609" submission.
Note on B81: Note: Submit copies of DCA approved Project Concept Changes that are related to the Construction Services Dept.
Note on B94: 2021 QAP: D. Cost Reasonableness Front End Cost Review: Owners may not close equity until after the review is complete. A Third-Party Front End Cost Review (“FECR”) of the construction costs must be conducted post-award for projects funded by programs administered through the QAP. DCA must approve the Third-Party Front-End Cost Reviewer’s qualifications beforehand (See Submission Requirements Manual). DCA will have forty-five (45) days to respond to the FECR , plus any days added for questions or clarifications. Owners may not close equity until after the earlier of this time period expiring or DCA’s approval. CS "Clarification" Note: For projects where the FECR Consultant's estimate is within "5%" of the Contractor's "DCA Contract Set" of Construction Documents (CDs) total Hard Cost amount (executed O/C Agreement amount), the FECR report may be submitted to DCA after the Owner's equity closing (due with the Commencement submission). For projects where the Contractor's "DCA Contract Set" of Construction Documents (CDs) total Hard Cost amount (executed O/C Agreement amount) exceeds the FECR Consultant's estimate by more than "5%", then the FECR report must be submitted to DCA prior to the Owner's equity closing, and where DCA will have forty-five (45) days to respond to the FECR , plus any days added for questions or clarifications.
Note on B96: Assumptions & Conditions Status Update Narrative: Provide a narrative that identifies each GHFA Letter of Determination "Assumptions & Conditions" of Funding section and provides a status update of each condition. Restate each "Assumptions & Conditions" verbatim from the Letter of Determination before each response. Note: - Only need to respond to items related to the Construction Services Department requirements
Note on B104: Note: Submit copies of DCA approved Project Concept Changes that are related to the Construction Services Dept.
Note on B111: AIA G704 Certificate of Substantial Completion: Submit a copy of this AIA document and include a copy of any list of remaining "punch out items" that were referenced as part of the document.
Note on B113: Final Contractor Application & Certificate for Payment(s) (100% release of retainage): Submit a copy of this AIA document (HUD pay app if applicable). Document should note all added Change Orders.
Note on B114: Final Contractor Application & Certificate for Payment(s) (100% release of retainage): Submit a copy of this AIA document (HUD pay app if applicable). Document should note all added Change Orders.
Note on B126: Note: Submit copies of DCA approved Project Concept Changes that are related to the Construction Services Dept.
Note on B140: Conditions of Funding Compliance Narrative: Provide a narrative that includes evidence of compliance with each GHFA Letter of Determination "Assumptions & Conditions" of Funding section. Restate each "Assumptions & Conditions" verbatim from the Letter of Determination before each response describing method of compliance. Provide supporting docs/evidence as needed. Note: - Only need to respond to items related to the Construction Services Department requirements
Note on B155: Note: Submit copies of DCA approved Project Concept Changes that are related to the Construction Services Dept.

## 2021 HOME 9pct
GEORGIA DEPARTMENT OF COMMUNITY AFFAIRS (DCA) | [9 empty] | HOME 9%
Office of Housing Finance (OHF)
Multifamily Construction Services (CS) Department - Attn: Administration
60 Executive Park South, NE, Atlanta, GA 30329-2231
2021 DCA CONSTRUCTION SERVICES (CS) "QAP COMPLIANCE" TRANSMITTAL | [11 empty] | Form Date: | 04.01.22
|  | DCA PROJECT #: |  | (2021-000) | [5 empty] | SUBMISSION TYPE:
|  | PROJECT NAME: | [7 empty] | FORM CERTIF. DATE:
CERTIF. EMAIL:
DEVELOPER CONTACT | [6 empty] | BUILDING SCHEDULE
| Company: | [5 empty] | Residential Buildings
| Name: | [5 empty] | #Bldgs. | Constr. |  | Bldg. Type |  | Conditioned SF | Covered SF
Email:
Phone:
PROJECT TEAM
Architect:
Contractor:
|  |  |  | Identity of Interest?: |  | Total: | 0 |  |  |  |  | 0 | 0
| Accessibility: | [5 empty] | Accessory Buildings (non-residential)
| Inspector: | [5 empty] | #Bldgs. | Constr. |  | Bldg. Type |  | Conditioned SF | Covered SF
FECR:
PROPERTY ADDRESS
| Street: |  |  |  |  | Total: | 0 |  |  |  |  | 0 | 0
| City: |  |  | ZIP:
| County: | [8 empty] | UNIT SCHEDULE (unit mix breakdown)
| Geo Coord: | Latitude: |  | Longitude | [5 empty] | Residential Units
|  |  | (00.000000) |  | (00.000000) |  |  |  |  | #Units | #Bedrms. | #Bathrms. | Total Net SF
PROJECT DESCRIPTION | [13 empty] | 0
|  |  | DCA Scattered Site?: | [10 empty] | 0
|  |  | If Yes, How Many Properties?: | [10 empty] | 0
0
|  |  | Tenancy1: | [10 empty] | 0
|  |  | Tenancy2: | [10 empty] | 0
[9 empty] | Total: | 0 | 0 |  | 0 | 0 | # of bedrms.
|  |  | Acreage On-site: | [6 empty] | Accessibility Units
|  |  | Acreage Off-site: | [6 empty] | Total # of Mobility Impaired Units:
|  |  | Acreage Total: | 0 | [5 empty] | # of M.I. Units With "Roll-in Showers":
# of Sight / Hearing Impaired Units:
CONTRACT PROJECT SCHEDULE (AIA/HUD)
|  |  |  | Notice to Proceed (NTP) |  |  | USES of FUNDS DEVELOPMENT COSTS - HARD COSTS
|  |  | Current "estimated" NTP Date: |  |  |  | Description |  |  |  | Award | Due Dill. | Final Alloc.
|  |  | Actual NTP Date: |  |  |  | Contractor Hard Costs:
|  |  |  | Contract Time |  |  | Other Construction Hard Cost:
|  |  | Contract # of Days: |  |  |  | Construction Contingency:
|  |  | Actual Contract Start Date: | [6 empty] | Total Hard Costs: | 0 | 0 | 0
|  |  | Change Order # of Days: |  |  |  | Description |  |  |  | Award | Due Dill. | Final Alloc.
|  |  | Total Contract to-date Days: | 0 |  |  | Cost Per Unit Net SF: |  |  |  | #DIV/0! | #DIV/0! | #DIV/0!
|  |  |  | Certificate of Substantial Completion (AIA) |  |  | Cost Per Unit: |  |  |  | #DIV/0! | #DIV/0! | #DIV/0!
|  |  | Current "estimated" Date: |  |  |  | Cost Per Bedrm.: |  |  |  | #DIV/0! | #DIV/0! | #DIV/0!
Actual Project Cert of SC Date:
LIHTC MILESTONES | [6 empty] | USES of FUNDS DEVELOPMENT COSTS - SOFT COSTS
|  |  |  | Placed in Service (PIS) |  |  | Description |  |  |  | Award | Due Dill. | Final Alloc.
|  |  | Current "estimated" PIS Date: |  |  |  | Acquisition - Site Demolition:
Last Residential Bldg. "Actual" PIS Date:
*** DO NOT COMBINE THE STAGED SUBMISSION PACKAGES (maintain separate binders/flash drives per submission) ***
PLACE AN 'X' IN THE BOX NEXT TO EACH DOCUMENT SUBMITTED
60 DAY SUBMISSION (due no later than 60 days after announcement of awards; or no later than March 30, 2022)
01 | DCA Award letter |  |  | (copy of Carryover and HOME Consent ltrs/exhibits)
02 | Awarded QAP Conceptual Site Development Plan (CSD plan) |  |  |  |  | (DCA approved application CSD plan)
03 | Awarded QAP DCA Rehab Work Scope form |  |  |  |  | (DCA approved application DCA Rehab Work Scope form)
04 | ALTA/ACSM Land Title Survey
05 | Geotechnical Report |  |  | (new construction only)
06 | Contractor Approval Package |  |  | (see HOME Underwriting Policies of the QAP Threshold)
07 | Owner/Architect Agreement - executed
08 | Accessibility Consultant DCA Qualifications Package |  |  |  |  | (see QAP & Accessibility Manual for requirements)
09 | Accessibility Consultant Agreement
10 | Accessibility Contractor and Subcontractor Training Sessions Action Plan (submit a document that states how this will be accomplished) | [10 empty] | (min. two training sessions)
11 | Sustainable Building Certification "draft" scoring sheet for the development and related Consultant Agreement | [9 empty] | (agreement/proposal)
12 | HERS Rater Consultant Agreement - (agreement/proposal)
13 | 3rd Party Front-End Cost Review (FECR) DCA Qualifications Package | [5 empty] | (ALL projects) |  |  | (see QAP & Architectural Manual for requirements)
14 | Construction Compliance Inspector Agreement |  |  |  |  | (ALL projects) |  |  | (see QAP & Architectural Manual for requirements)
15 | DCA Amenities & Design Options Re-Certification form (ADO recert) | [5 empty] | (per the awarded CORE application)
16 | DCA Approved Architectural Waivers/Optional Amenities | [5 empty] | (including evidence of DCA approval)
17 | DCA Approved Project Concept Changes |  |  |  | (including evidence of DCA approval)
18 | Other:
DCA REVIEW SUBMISSION (Due 45 days prior to DCA GHFA construction loan closing and no later than May 30, 2022)
01 | DCA Construction Document Log (drawing log) |  |  |  | (DCA "Review Set") |  | (see instructions for definition of DCA "Review Set")
02 | DCA "Review Set" of drawings (plans) |  |  |  | (DCA "Review Set") |  | (no paper set required-PDF only)
03 | DCA "Review Set" of Project Manual (specs) |  |  |  | (DCA "Review Set") |  | (no paper set required-PDF only)
04 | DCA Schedule of Values form (dca sov) |  |  |  | (DCA "Review Set")
05 | Owner/Contractor Agreement - draft |  |  |  | (current A101 Stipulated Sum or A102 Cost of Work Plus Fee With a Guaranteed Maximum Price forms)
06 | Other Construction Hard Cost Work Scope |  |  |  | (support documentation for hard cost work scope not included in O/C agreement)
07 | Acquisition Soft Cost - Site Demolition Work Scope |  |  |  | (support documentation for "soft cost" site demolition work scope )
08 | Construction Schedule - draft |  |  | (DCA Review Set)
09 | Third Party Front-End Cost Review |  |  | (DCA Review Set) |  | (ALL projects)
10 | Narrative that identifies each Carryover Allocation letter "Assumptions & Conditions" and provides a status update of each condition
|  | (ex.: wetlands delineations, noise mitigation plans, etc.) |  |  |  | (restate each C.o.F in the narrative) |  |  |  | (Construction Srvcs Dept items only)
11 | Federal Work Authorization Affidavits |  |  |  | (E-Verify)
12 | DCA Amenities & Design Options Re-Certification form (ADO recert)
13 | DCA Approved Architectural Waivers/Optional Amenities |  |  |  |  | (including evidence of DCA approval)
14 | DCA Approved Project Concept Changes |  |  |  | (including evidence of DCA approval)
15 | Other:
LOAN CLOSING SUBMISSION (due 10 days prior to DCA GHFA construction loan closing)
01 | DCA Construction Document Log (drawing log) |  |  |  | (DCA "Contract Set") |  | (see instructions for definition of DCA "Contract Set")
02 | DCA "Contract Set" of drawings (plans) |  |  |  | (DCA "Contract Set") |  | (no paper set required-PDF only)
03 | DCA "Contract Set" of Project Manual (specs) |  |  |  | (DCA "Contract Set") |  | (no paper set required-PDF only)
04 | DCA Schedule of Values form (dca sov) |  |  |  | (DCA "Contract Set")
05 | Addendum incorporating/outlining revisions from DCA "Review Set" into the DCA "Contract Set"
06 | Owner/Contractor Agreement - executed |  |  |  | (DCA Contract Set)
07 | Other Construction Hard Cost Work Scope |  |  |  | (support documentation for work not included in O/C agreement)
08 | Acquisition Soft Cost - Site Demolition Work Scope |  |  |  | (support documentation for "soft cost" site demolition work scope )
09 | DCA Amenities & Design Options Re-Certification form (ADO recert)
10 | DCA Approved Architectural Waivers/Optional Amenities |  |  |  |  | (including evidence of DCA approval)
11 | DCA Approved Project Concept Changes |  |  |  | (including evidence of DCA approval)
12 | Other:
COMMENCEMENT SUBMISSION (Prior to construction commencement which must occur no later than November 15, 2022)
01 | Notice to Proceed
02 | Construction Schedule - finalized
03 | Permits |  | (Land Development, Building,,,)
04 | Accessibility Consultant Plan Review Comments
05 | Accessibility Consultant Clearance Letter (acknowledgement of plan review comment resolutions)
06 | DCA Placed in Service (PIS) form - draft with estimated dates | [5 empty] | (DCA OPM Compliance Dept. form)
07 | DCA Amenities & Design Options Re-Certification form (ADO recert)
08 | DCA Approved Architectural Waivers/Optional Amenities |  |  |  |  | (including evidence of DCA approval)
09 | DCA Approved Project Concept Changes |  |  |  | (including evidence of DCA approval)
10 | Other:
OTHER CS SUBMISSIONS
01 | Other:
02 | Other:
DCA#: |  | 0 |  |  |  | Program: | 2021 HOME 9pct |  |  |  |  | Date: | 0
Note on A13: DEVELOPER CONTACT FOR DCA CONSTRUCTION SERVICES DEPT.
Note on N15: Note: Gross Building "Conditioned" Square Footage
Note on O15: Note: Gross Building "Covered" Square Footage
Note on N24: Note: Gross Building "Conditioned" Square Footage
Note on O24: Note: Gross Building "Covered" Square Footage
Note on O32: Architectural Standards - V. BUILDING INTERIORS DESIGN STANDARDS - B. Unit Sizes: Net Rentable (Leasable) Square Footage: This is the DCA definition for calculating “Residential Unit Square Footage” as it pertains to the Architectural Manual and other documents in Qualified Allocation Plan (QAP). It is calculated for each individual dwelling type. The unit net rentable area is measured from the inside face of each of the unit’s perimeter walls. • Net area included air-conditioned space only. • Measure from the inside (paint) face of all unit perimeter walls. • Do not include any patio, balcony, or breezeway areas. • Do not include any outside storage closets. • Do not deduct any interior walls. • Include non-revenue units in total net rentable living area (Total Residential Unit Square Footage)
Note on M46: Award Notes: Enter hard cost amounts from "awarded" QAP core application Enter data with "60-day" submission.
Note on N46: Due Diligence Notes: Enter hard cost amounts at time of Construction Loan Closing (executed Owner/Contractor agreement, etc.) Enter data with "Commencement" submission.
Note on O46: Final Allocation Notes: Final construction Hard Cost amounts (Change Orders, etc.) that reflect the Final Allocation Application. Enter data with "Construction 8609" submission.
Note on F53: Note: The date for the "AIA G704 Certificate of Substantial Completion"
Note on M57: Award Notes: Enter hard cost amounts from "awarded" QAP core application Enter data with "60-day" submission.
Note on N57: Due Diligence Notes: Enter hard cost amounts at time of Construction Loan Closing (executed Owner/Contractor agreement, etc.) Enter data with "Commencement" submission.
Note on O57: Final Allocation Notes: Final construction Soft Cost amount that reflect the Final Allocation Application. Enter data with "Construction 8609" submission.
Note on B82: Note: Submit copies of DCA approved Project Concept Changes that are related to the Construction Services Dept.
Note on B96: Assumptions & Conditions Status Update Narrative: Provide a narrative that identifies each GHFA Letter of Determination "Assumptions & Conditions" of Funding section and provides a status update of each condition. Restate each "Assumptions & Conditions" verbatim from the Letter of Determination before each response. Note: - Only need to respond to items related to the Construction Services Department requirements
Note on B101: Note: Submit copies of DCA approved Project Concept Changes that are related to the Construction Services Dept.
Note on B116: Note: Submit copies of DCA approved Project Concept Changes that are related to the Construction Services Dept.
Note on B129: Note: Submit copies of DCA approved Project Concept Changes that are related to the Construction Services Dept.

## 2021 HOME 4pct
GEORGIA DEPARTMENT OF COMMUNITY AFFAIRS (DCA) | [9 empty] | HOME 4% NOFA
Office of Housing Finance (OHF)
Multifamily Construction Services (CS) Department - Attn: Administration
60 Executive Park South, NE, Atlanta, GA 30329-2231
2021 DCA CONSTRUCTION SERVICES (CS) "QAP COMPLIANCE" TRANSMITTAL | [11 empty] | Form Date: | 04.01.22
|  | DCA PROJECT #: |  | (2021-000) | [5 empty] | SUBMISSION TYPE:
|  | PROJECT NAME: | [7 empty] | FORM CERTIF. DATE:
CERTIF. EMAIL:
DEVELOPER CONTACT | [6 empty] | BUILDING SCHEDULE
| Company: | [5 empty] | Residential Buildings
| Name: | [5 empty] | #Bldgs. | Constr. |  | Bldg. Type |  | Conditioned SF | Covered SF
Email:
Phone:
PROJECT TEAM
Architect:
Contractor:
|  |  |  | Identity of Interest?: |  | Total: | 0 |  |  |  |  | 0 | 0
| Accessibility: | [5 empty] | Accessory Buildings (non-residential)
| Inspector: | [5 empty] | #Bldgs. | Constr. |  | Bldg. Type |  | Conditioned SF | Covered SF
FECR:
PROPERTY ADDRESS
| Street: |  |  |  |  | Total: | 0 |  |  |  |  | 0 | 0
| City: |  |  | ZIP:
| County: | [8 empty] | UNIT SCHEDULE (unit mix breakdown)
| Geo Coord: | Latitude: |  | Longitude | [5 empty] | Residential Units
|  |  | (00.000000) |  | (00.000000) |  |  |  |  | #Units | #Bedrms. | #Bathrms. | Total Net SF
PROJECT DESCRIPTION | [13 empty] | 0
|  |  | DCA Scattered Site?: | [10 empty] | 0
|  |  | If Yes, How Many Properties?: | [10 empty] | 0
0
|  |  | Tenancy1: | [10 empty] | 0
|  |  | Tenancy2: | [10 empty] | 0
[9 empty] | Total: | 0 | 0 |  | 0 | 0 | # of bedrms.
|  |  | Acreage On-site: | [6 empty] | Accessibility Units
|  |  | Acreage Off-site: | [6 empty] | Total # of Mobility Impaired Units:
|  |  | Acreage Total: | 0 | [5 empty] | # of M.I. Units With "Roll-in Showers":
# of Sight / Hearing Impaired Units:
CONTRACT PROJECT SCHEDULE (AIA/HUD)
|  |  |  | Notice to Proceed (NTP) |  |  | USES of FUNDS DEVELOPMENT COSTS - HARD COSTS
|  |  | Current "estimated" NTP Date: |  |  |  | Description |  |  |  | Award | Due Dill. | Final Alloc.
|  |  | Actual NTP Date: |  |  |  | Contractor Hard Costs:
|  |  |  | Contract Time |  |  | Other Construction Hard Cost:
|  |  | Contract # of Days: |  |  |  | Construction Contingency:
|  |  | Actual Contract Start Date: | [6 empty] | Total Hard Costs: | 0 | 0 | 0
|  |  | Change Order # of Days: |  |  |  | Description |  |  |  | Award | Due Dill. | Final Alloc.
|  |  | Total Contract to-date Days: | 0 |  |  | Cost Per Unit Net SF: |  |  |  | #DIV/0! | #DIV/0! | #DIV/0!
|  |  |  | Certificate of Substantial Completion (AIA) |  |  | Cost Per Unit: |  |  |  | #DIV/0! | #DIV/0! | #DIV/0!
|  |  | Current "estimated" Date: |  |  |  | Cost Per Bedrm.: |  |  |  | #DIV/0! | #DIV/0! | #DIV/0!
Actual Project Cert of SC Date:
LIHTC MILESTONES | [6 empty] | USES of FUNDS DEVELOPMENT COSTS - SOFT COSTS
|  |  |  | Placed in Service (PIS) |  |  | Description |  |  |  | Award | Due Dill. | Final Alloc.
|  |  | Current "estimated" PIS Date: |  |  |  | Acquisition - Site Demolition:
Last Residential Bldg. "Actual" PIS Date:
*** DO NOT COMBINE THE STAGED SUBMISSION PACKAGES (maintain separate binders/flash drives per submission) ***
PLACE AN 'X' IN THE BOX NEXT TO EACH DOCUMENT SUBMITTED
60 DAY SUBMISSION (due no later than 60 days after the date of Letter of Determination - 42m)
01 | DCA Award letter |  |  | (copy of LoD and HOME Consent ltrs/exhibits)
02 | Awarded QAP Conceptual Site Development Plan (CSD plan) |  |  |  |  | (DCA approved application CSD plan)
03 | Awarded QAP DCA Rehab Work Scope form |  |  |  |  | (DCA approved application DCA Rehab Work Scope form)
04 | ALTA/ACSM Land Title Survey
05 | Geotechnical Report |  |  | (new construction only)
06 | Contractor Approval Package |  |  | (see HOME Underwriting Policies of the QAP Threshold)
07 | Owner/Architect Agreement - executed
08 | Accessibility Consultant DCA Qualifications Package |  |  |  |  | (see QAP & Accessibility Manual for requirements)
09 | Accessibility Consultant Agreement
10 | Accessibility Contractor and Subcontractor Training Sessions Action Plan (submit a document that states how this will be accomplished) | [10 empty] | (min. two training sessions)
11 | Sustainable Building Certification "draft" scoring sheet for the development and related Consultant Agreement | [9 empty] | (agreement/proposal)
12 | HERS Rater Consultant Agreement - (agreement/proposal)
13 | 3rd Party Front-End Cost Review (FECR) DCA Qualifications Package | [5 empty] | (ALL projects) |  |  | (see QAP & Architectural Manual for requirements)
14 | Construction Compliance Inspector Agreement |  |  |  |  | (ALL projects) |  |  | (see QAP & Architectural Manual for requirements)
15 | DCA Amenities & Design Options Re-Certification form (ADO recert) | [5 empty] | (per the awarded CORE application)
16 | DCA Approved Architectural Waivers/Optional Amenities | [5 empty] | (including evidence of DCA approval)
17 | DCA Approved Project Concept Changes |  |  |  | (including evidence of DCA approval)
18 | Other:
DCA REVIEW SUBMISSION (Due 45 days prior to DCA GHFA construction loan closing)
01 | DCA Construction Document Log (drawing log) |  |  |  | (DCA "Review Set") |  | (see instructions for definition of DCA "Review Set")
02 | DCA "Review Set" of drawings (plans) |  |  |  | (DCA "Review Set") |  | (no paper set required-PDF only)
03 | DCA "Review Set" of Project Manual (specs) |  |  |  | (DCA "Review Set") |  | (no paper set required-PDF only)
04 | DCA Schedule of Values form (dca sov) |  |  |  | (DCA "Review Set")
05 | Owner/Contractor Agreement - draft |  |  |  | (current A101 Stipulated Sum or A102 Cost of Work Plus Fee With a Guaranteed Maximum Price forms)
06 | Other Construction Hard Cost Work Scope |  |  |  | (support documentation for hard cost work scope not included in O/C agreement)
07 | Acquisition Soft Cost - Site Demolition Work Scope |  |  |  | (support documentation for "soft cost" site demolition work scope )
08 | Construction Schedule - draft |  |  | (DCA Review Set)
09 | Third Party Front-End Cost Review |  |  | (DCA Review Set) |  | (ALL projects)
10 | Narrative that identifies each Carryover Allocation letter "Assumptions & Conditions" and provides a status update of each condition
|  | (ex.: wetlands delineations, noise mitigation plans, etc.) |  |  |  | (restate each C.o.F in the narrative) |  |  |  | (Construction Srvcs Dept items only)
11 | Federal Work Authorization Affidavits |  |  |  | (E-Verify)
12 | DCA Amenities & Design Options Re-Certification form (ADO recert)
13 | DCA Approved Architectural Waivers/Optional Amenities |  |  |  |  | (including evidence of DCA approval)
14 | DCA Approved Project Concept Changes |  |  |  | (including evidence of DCA approval)
15 | Other:
LOAN CLOSING SUBMISSION (due 10 days prior to DCA GHFA construction loan closing)
01 | DCA Construction Document Log (drawing log) |  |  |  | (DCA "Contract Set") |  | (see instructions for definition of DCA "Contract Set")
02 | DCA "Contract Set" of drawings (plans) |  |  |  | (DCA "Contract Set") |  | (no paper set required-PDF only)
03 | DCA "Contract Set" of Project Manual (specs) |  |  |  | (DCA "Contract Set") |  | (no paper set required-PDF only)
04 | DCA Schedule of Values form (dca sov) |  |  |  | (DCA "Contract Set")
05 | Addendum incorporating/outlining revisions from DCA "Review Set" into the DCA "Contract Set"
06 | Owner/Contractor Agreement - executed |  |  |  | (DCA Contract Set)
07 | Other Construction Hard Cost Work Scope |  |  |  | (support documentation for work not included in O/C agreement)
08 | Acquisition Soft Cost - Site Demolition Work Scope |  |  |  | (support documentation for "soft cost" site demolition work scope )
09 | DCA Amenities & Design Options Re-Certification form (ADO recert)
10 | DCA Approved Architectural Waivers/Optional Amenities |  |  |  |  | (including evidence of DCA approval)
11 | DCA Approved Project Concept Changes |  |  |  | (including evidence of DCA approval)
12 | Other:
COMMENCEMENT SUBMISSION (due prior to construction commencement which must occur within 30 days of bond finance closing date)
01 | Notice to Proceed
02 | Construction Schedule - finalized
03 | Permits |  | (Land Development, Building,,,)
04 | Accessibility Consultant Plan Review Comments
05 | Accessibility Consultant Clearance Letter (acknowledgement of plan review comment resolutions)
06 | DCA Placed in Service (PIS) form - draft with estimated dates | [5 empty] | (DCA OPM Compliance Dept. form)
07 | DCA Amenities & Design Options Re-Certification form (ADO recert)
08 | DCA Approved Architectural Waivers/Optional Amenities |  |  |  |  | (including evidence of DCA approval)
09 | DCA Approved Project Concept Changes |  |  |  | (including evidence of DCA approval)
10 | Other:
OTHER CS SUBMISSIONS
01 | Other:
02 | Other:
DCA#: |  | 0 |  |  |  | Program: | 2021 HOME 4pct |  |  |  |  | Date: | 0
Note on A13: DEVELOPER CONTACT FOR DCA CONSTRUCTION SERVICES DEPT.
Note on N15: Note: Gross Building "Conditioned" Square Footage
Note on O15: Note: Gross Building "Covered" Square Footage
Note on N24: Note: Gross Building "Conditioned" Square Footage
Note on O24: Note: Gross Building "Covered" Square Footage
Note on O32: Architectural Standards - V. BUILDING INTERIORS DESIGN STANDARDS - B. Unit Sizes: Net Rentable (Leasable) Square Footage: This is the DCA definition for calculating “Residential Unit Square Footage” as it pertains to the Architectural Manual and other documents in Qualified Allocation Plan (QAP). It is calculated for each individual dwelling type. The unit net rentable area is measured from the inside face of each of the unit’s perimeter walls. • Net area included air-conditioned space only. • Measure from the inside (paint) face of all unit perimeter walls. • Do not include any patio, balcony, or breezeway areas. • Do not include any outside storage closets. • Do not deduct any interior walls. • Include non-revenue units in total net rentable living area (Total Residential Unit Square Footage)
Note on M46: Award Notes: Enter hard cost amounts from "awarded" QAP core application Enter data with "60-day" submission.
Note on N46: Due Diligence Notes: Enter hard cost amounts at time of Construction Loan Closing (executed Owner/Contractor agreement, etc.) Enter data with "Commencement" submission.
Note on O46: Final Allocation Notes: Final construction Hard Cost amounts (Change Orders, etc.) that reflect the Final Allocation Application. Enter data with "Construction 8609" submission.
Note on F53: Note: The date for the "AIA G704 Certificate of Substantial Completion"
Note on M57: Award Notes: Enter hard cost amounts from "awarded" QAP core application Enter data with "60-day" submission.
Note on N57: Due Diligence Notes: Enter hard cost amounts at time of Construction Loan Closing (executed Owner/Contractor agreement, etc.) Enter data with "Commencement" submission.
Note on O57: Final Allocation Notes: Final construction Soft Cost amount that reflect the Final Allocation Application. Enter data with "Construction 8609" submission.
Note on B82: Note: Submit copies of DCA approved Project Concept Changes that are related to the Construction Services Dept.
Note on B96: Assumptions & Conditions Status Update Narrative: Provide a narrative that identifies each GHFA Letter of Determination "Assumptions & Conditions" of Funding section and provides a status update of each condition. Restate each "Assumptions & Conditions" verbatim from the Letter of Determination before each response. Note: - Only need to respond to items related to the Construction Services Department requirements
Note on B101: Note: Submit copies of DCA approved Project Concept Changes that are related to the Construction Services Dept.
Note on B116: Note: Submit copies of DCA approved Project Concept Changes that are related to the Construction Services Dept.
Note on B129: Note: Submit copies of DCA approved Project Concept Changes that are related to the Construction Services Dept.

## 2021 NHTF 9pct
GEORGIA DEPARTMENT OF COMMUNITY AFFAIRS (DCA) | [9 empty] | NHTF 9%
Office of Housing Finance (OHF)
Multifamily Construction Services (CS) Department - Attn: Administration
60 Executive Park South, NE, Atlanta, GA 30329-2231
2021 DCA CONSTRUCTION SERVICES (CS) "QAP COMPLIANCE" TRANSMITTAL | [11 empty] | Form Date: | 04.01.22
|  | DCA PROJECT #: |  | (2021-000) | [5 empty] | SUBMISSION TYPE:
|  | PROJECT NAME: | [7 empty] | FORM CERTIF. DATE:
CERTIF. EMAIL:
DEVELOPER CONTACT | [6 empty] | BUILDING SCHEDULE
| Company: | [5 empty] | Residential Buildings
| Name: | [5 empty] | #Bldgs. | Constr. |  | Bldg. Type |  | Conditioned SF | Covered SF
Email:
Phone:
PROJECT TEAM
Architect:
Contractor:
|  |  |  | Identity of Interest?: |  | Total: | 0 |  |  |  |  | 0 | 0
| Accessibility: | [5 empty] | Accessory Buildings (non-residential)
| Inspector: | [5 empty] | #Bldgs. | Constr. |  | Bldg. Type |  | Conditioned SF | Covered SF
FECR:
PROPERTY ADDRESS
| Street: |  |  |  |  | Total: | 0 |  |  |  |  | 0 | 0
| City: |  |  | ZIP:
| County: | [8 empty] | UNIT SCHEDULE (unit mix breakdown)
| Geo Coord: | Latitude: |  | Longitude | [5 empty] | Residential Units
|  |  | (00.000000) |  | (00.000000) |  |  |  |  | #Units | #Bedrms. | #Bathrms. | Total Net SF
PROJECT DESCRIPTION | [13 empty] | 0
|  |  | DCA Scattered Site?: | [10 empty] | 0
|  |  | If Yes, How Many Properties?: | [10 empty] | 0
0
|  |  | Tenancy1: | [10 empty] | 0
|  |  | Tenancy2: | [10 empty] | 0
[9 empty] | Total: | 0 | 0 |  | 0 | 0 | # of bedrms.
|  |  | Acreage On-site: | [6 empty] | Accessibility Units
|  |  | Acreage Off-site: | [6 empty] | Total # of Mobility Impaired Units:
|  |  | Acreage Total: | 0 | [5 empty] | # of M.I. Units With "Roll-in Showers":
# of Sight / Hearing Impaired Units:
CONTRACT PROJECT SCHEDULE (AIA/HUD)
|  |  |  | Notice to Proceed (NTP) |  |  | USES of FUNDS DEVELOPMENT COSTS - HARD COSTS
|  |  | Current "estimated" NTP Date: |  |  |  | Description |  |  |  | Award | Due Dill. | Final Alloc.
|  |  | Actual NTP Date: |  |  |  | Contractor Hard Costs:
|  |  |  | Contract Time |  |  | Other Construction Hard Cost:
|  |  | Contract # of Days: |  |  |  | Construction Contingency:
|  |  | Actual Contract Start Date: | [6 empty] | Total Hard Costs: | 0 | 0 | 0
|  |  | Change Order # of Days: |  |  |  | Description |  |  |  | Award | Due Dill. | Final Alloc.
|  |  | Total Contract to-date Days: | 0 |  |  | Cost Per Unit Net SF: |  |  |  | #DIV/0! | #DIV/0! | #DIV/0!
|  |  |  | Certificate of Substantial Completion (AIA) |  |  | Cost Per Unit: |  |  |  | #DIV/0! | #DIV/0! | #DIV/0!
|  |  | Current "estimated" Date: |  |  |  | Cost Per Bedrm.: |  |  |  | #DIV/0! | #DIV/0! | #DIV/0!
Actual Project Cert of SC Date:
LIHTC MILESTONES | [6 empty] | USES of FUNDS DEVELOPMENT COSTS - SOFT COSTS
|  |  |  | Placed in Service (PIS) |  |  | Description |  |  |  | Award | Due Dill. | Final Alloc.
|  |  | Current "estimated" PIS Date: |  |  |  | Acquisition - Site Demolition:
Last Residential Bldg. "Actual" PIS Date:
*** DO NOT COMBINE THE STAGED SUBMISSION PACKAGES (maintain separate binders/flash drives per submission) ***
PLACE AN 'X' IN THE BOX NEXT TO EACH DOCUMENT SUBMITTED
60 DAY SUBMISSION (due no later than 60 days after announcement of awards; or no later than March 30, 2022)
01 | DCA Award letter |  |  | (copy of Carryover and HOME Consent ltrs/exhibits)
02 | Awarded QAP Conceptual Site Development Plan (CSD plan) |  |  |  |  | (DCA approved application CSD plan)
03 | Awarded QAP DCA Rehab Work Scope form |  |  |  |  | (DCA approved application DCA Rehab Work Scope form)
04 | ALTA/ACSM Land Title Survey
05 | Geotechnical Report |  |  | (new construction only)
06 | Contractor Approval Package |  |  | (see HOME Underwriting Policies of the QAP Threshold)
07 | Owner/Architect Agreement - executed
08 | Accessibility Consultant DCA Qualifications Package |  |  |  |  | (see QAP & Accessibility Manual for requirements)
09 | Accessibility Consultant Agreement
10 | Accessibility Contractor and Subcontractor Training Sessions Action Plan (submit a document that states how this will be accomplished) | [10 empty] | (min. two training sessions)
11 | Sustainable Building Certification "draft" scoring sheet for the development and related Consultant Agreement | [9 empty] | (agreement/proposal)
12 | HERS Rater Consultant Agreement - (agreement/proposal)
13 | 3rd Party Front-End Cost Review (FECR) DCA Qualifications Package | [5 empty] | (ALL projects) |  |  | (see QAP & Architectural Manual for requirements)
14 | Construction Compliance Inspector Agreement |  |  |  |  | (ALL projects) |  |  | (see QAP & Architectural Manual for requirements)
15 | DCA Amenities & Design Options Re-Certification form (ADO recert) | [5 empty] | (per the awarded CORE application)
16 | DCA Approved Architectural Waivers/Optional Amenities | [5 empty] | (including evidence of DCA approval)
17 | DCA Approved Project Concept Changes |  |  |  | (including evidence of DCA approval)
18 | Other:
DCA REVIEW SUBMISSION (Due 45 days prior to DCA GHFA construction loan closing and no later than May 30, 2022)
01 | DCA Construction Document Log (drawing log) |  |  |  | (DCA "Review Set") |  | (see instructions for definition of DCA "Review Set")
02 | DCA "Review Set" of drawings (plans) |  |  |  | (DCA "Review Set") |  | (no paper set required-PDF only)
03 | DCA "Review Set" of Project Manual (specs) |  |  |  | (DCA "Review Set") |  | (no paper set required-PDF only)
04 | DCA Schedule of Values form (dca sov) |  |  |  | (DCA "Review Set")
05 | Owner/Contractor Agreement - draft |  |  |  | (current A101 Stipulated Sum or A102 Cost of Work Plus Fee With a Guaranteed Maximum Price forms)
06 | Other Construction Hard Cost Work Scope |  |  |  | (support documentation for hard cost work scope not included in O/C agreement)
07 | Acquisition Soft Cost - Site Demolition Work Scope |  |  |  | (support documentation for "soft cost" site demolition work scope )
08 | Construction Schedule - draft |  |  | (DCA Review Set)
09 | Third Party Front-End Cost Review |  |  | (DCA Review Set) |  | (ALL projects)
10 | Narrative that identifies each Carryover Allocation letter "Assumptions & Conditions" and provides a status update of each condition
|  | (ex.: wetlands delineations, noise mitigation plans, etc.) |  |  |  | (restate each C.o.F in the narrative) |  |  |  | (Construction Srvcs Dept items only)
11 | Federal Work Authorization Affidavits |  |  |  | (E-Verify)
12 | DCA Amenities & Design Options Re-Certification form (ADO recert)
13 | DCA Approved Architectural Waivers/Optional Amenities |  |  |  |  | (including evidence of DCA approval)
14 | DCA Approved Project Concept Changes |  |  |  | (including evidence of DCA approval)
15 | Other:
LOAN CLOSING SUBMISSION (due 10 days prior to DCA GHFA construction loan closing)
01 | DCA Construction Document Log (drawing log) |  |  |  | (DCA "Contract Set") |  | (see instructions for definition of DCA "Contract Set")
02 | DCA "Contract Set" of drawings (plans) |  |  |  | (DCA "Contract Set") |  | (no paper set required-PDF only)
03 | DCA "Contract Set" of Project Manual (specs) |  |  |  | (DCA "Contract Set") |  | (no paper set required-PDF only)
04 | DCA Schedule of Values form (dca sov) |  |  |  | (DCA "Contract Set")
05 | Addendum incorporating/outlining revisions from DCA "Review Set" into the DCA "Contract Set"
06 | Owner/Contractor Agreement - executed |  |  |  | (DCA Contract Set)
07 | Other Construction Hard Cost Work Scope |  |  |  | (support documentation for work not included in O/C agreement)
08 | Acquisition Soft Cost - Site Demolition Work Scope |  |  |  | (support documentation for "soft cost" site demolition work scope )
09 | DCA Amenities & Design Options Re-Certification form (ADO recert)
10 | DCA Approved Architectural Waivers/Optional Amenities |  |  |  |  | (including evidence of DCA approval)
11 | DCA Approved Project Concept Changes |  |  |  | (including evidence of DCA approval)
12 | Other:
COMMENCEMENT SUBMISSION (Prior to construction commencement which must occur no later than November 15, 2022)
01 | Notice to Proceed
02 | Construction Schedule - finalized
03 | Permits |  | (Land Development, Building,,,)
04 | Accessibility Consultant Plan Review Comments
05 | Accessibility Consultant Clearance Letter (acknowledgement of plan review comment resolutions)
06 | DCA Placed in Service (PIS) form - draft with estimated dates | [5 empty] | (DCA OPM Compliance Dept. form)
07 | DCA Amenities & Design Options Re-Certification form (ADO recert)
08 | DCA Approved Architectural Waivers/Optional Amenities |  |  |  |  | (including evidence of DCA approval)
09 | DCA Approved Project Concept Changes |  |  |  | (including evidence of DCA approval)
10 | Other:
OTHER CS SUBMISSIONS
01 | Other:
02 | Other:
DCA#: |  | 0 |  |  |  | Program: | 2021 NHTF 9pct |  |  |  |  | Date: | 0
Note on A13: DEVELOPER CONTACT FOR DCA CONSTRUCTION SERVICES DEPT.
Note on N15: Note: Gross Building "Conditioned" Square Footage
Note on O15: Note: Gross Building "Covered" Square Footage
Note on N24: Note: Gross Building "Conditioned" Square Footage
Note on O24: Note: Gross Building "Covered" Square Footage
Note on O32: Architectural Standards - V. BUILDING INTERIORS DESIGN STANDARDS - B. Unit Sizes: Net Rentable (Leasable) Square Footage: This is the DCA definition for calculating “Residential Unit Square Footage” as it pertains to the Architectural Manual and other documents in Qualified Allocation Plan (QAP). It is calculated for each individual dwelling type. The unit net rentable area is measured from the inside face of each of the unit’s perimeter walls. • Net area included air-conditioned space only. • Measure from the inside (paint) face of all unit perimeter walls. • Do not include any patio, balcony, or breezeway areas. • Do not include any outside storage closets. • Do not deduct any interior walls. • Include non-revenue units in total net rentable living area (Total Residential Unit Square Footage)
Note on M46: Award Notes: Enter hard cost amounts from "awarded" QAP core application Enter data with "60-day" submission.
Note on N46: Due Diligence Notes: Enter hard cost amounts at time of Construction Loan Closing (executed Owner/Contractor agreement, etc.) Enter data with "Commencement" submission.
Note on O46: Final Allocation Notes: Final construction Hard Cost amounts (Change Orders, etc.) that reflect the Final Allocation Application. Enter data with "Construction 8609" submission.
Note on F53: Note: The date for the "AIA G704 Certificate of Substantial Completion"
Note on M57: Award Notes: Enter hard cost amounts from "awarded" QAP core application Enter data with "60-day" submission.
Note on N57: Due Diligence Notes: Enter hard cost amounts at time of Construction Loan Closing (executed Owner/Contractor agreement, etc.) Enter data with "Commencement" submission.
Note on O57: Final Allocation Notes: Final construction Soft Cost amount that reflect the Final Allocation Application. Enter data with "Construction 8609" submission.
Note on B82: Note: Submit copies of DCA approved Project Concept Changes that are related to the Construction Services Dept.
Note on B96: Assumptions & Conditions Status Update Narrative: Provide a narrative that identifies each GHFA Letter of Determination "Assumptions & Conditions" of Funding section and provides a status update of each condition. Restate each "Assumptions & Conditions" verbatim from the Letter of Determination before each response. Note: - Only need to respond to items related to the Construction Services Department requirements
Note on B101: Note: Submit copies of DCA approved Project Concept Changes that are related to the Construction Services Dept.
Note on B116: Note: Submit copies of DCA approved Project Concept Changes that are related to the Construction Services Dept.
Note on B129: Note: Submit copies of DCA approved Project Concept Changes that are related to the Construction Services Dept.

## 2021 NHTF 4pct
GEORGIA DEPARTMENT OF COMMUNITY AFFAIRS (DCA) | [9 empty] | NHTF 4% NOFA
Office of Housing Finance (OHF)
Multifamily Construction Services (CS) Department - Attn: Administration
60 Executive Park South, NE, Atlanta, GA 30329-2231
2021 DCA CONSTRUCTION SERVICES (CS) "QAP COMPLIANCE" TRANSMITTAL | [11 empty] | Form Date: | 04.01.22
|  | DCA PROJECT #: |  | (2021-000) | [5 empty] | SUBMISSION TYPE:
|  | PROJECT NAME: | [7 empty] | FORM CERTIF. DATE:
CERTIF. EMAIL:
DEVELOPER CONTACT | [6 empty] | BUILDING SCHEDULE
| Company: | [5 empty] | Residential Buildings
| Name: | [5 empty] | #Bldgs. | Constr. |  | Bldg. Type |  | Conditioned SF | Covered SF
Email:
Phone:
PROJECT TEAM
Architect:
Contractor:
|  |  |  | Identity of Interest?: |  | Total: | 0 |  |  |  |  | 0 | 0
| Accessibility: | [5 empty] | Accessory Buildings (non-residential)
| Inspector: | [5 empty] | #Bldgs. | Constr. |  | Bldg. Type |  | Conditioned SF | Covered SF
FECR:
PROPERTY ADDRESS
| Street: |  |  |  |  | Total: | 0 |  |  |  |  | 0 | 0
| City: |  |  | ZIP:
| County: | [8 empty] | UNIT SCHEDULE (unit mix breakdown)
| Geo Coord: | Latitude: |  | Longitude | [5 empty] | Residential Units
|  |  | (00.000000) |  | (00.000000) |  |  |  |  | #Units | #Bedrms. | #Bathrms. | Total Net SF
PROJECT DESCRIPTION | [13 empty] | 0
|  |  | DCA Scattered Site?: | [10 empty] | 0
|  |  | If Yes, How Many Properties?: | [10 empty] | 0
0
|  |  | Tenancy1: | [10 empty] | 0
|  |  | Tenancy2: | [10 empty] | 0
[9 empty] | Total: | 0 | 0 |  | 0 | 0 | # of bedrms.
|  |  | Acreage On-site: | [6 empty] | Accessibility Units
|  |  | Acreage Off-site: | [6 empty] | Total # of Mobility Impaired Units:
|  |  | Acreage Total: | 0 | [5 empty] | # of M.I. Units With "Roll-in Showers":
# of Sight / Hearing Impaired Units:
CONTRACT PROJECT SCHEDULE (AIA/HUD)
|  |  |  | Notice to Proceed (NTP) |  |  | USES of FUNDS DEVELOPMENT COSTS - HARD COSTS
|  |  | Current "estimated" NTP Date: |  |  |  | Description |  |  |  | Award | Due Dill. | Final Alloc.
|  |  | Actual NTP Date: |  |  |  | Contractor Hard Costs:
|  |  |  | Contract Time |  |  | Other Construction Hard Cost:
|  |  | Contract # of Days: |  |  |  | Construction Contingency:
|  |  | Actual Contract Start Date: | [6 empty] | Total Hard Costs: | 0 | 0 | 0
|  |  | Change Order # of Days: |  |  |  | Description |  |  |  | Award | Due Dill. | Final Alloc.
|  |  | Total Contract to-date Days: | 0 |  |  | Cost Per Unit Net SF: |  |  |  | #DIV/0! | #DIV/0! | #DIV/0!
|  |  |  | Certificate of Substantial Completion (AIA) |  |  | Cost Per Unit: |  |  |  | #DIV/0! | #DIV/0! | #DIV/0!
|  |  | Current "estimated" Date: |  |  |  | Cost Per Bedrm.: |  |  |  | #DIV/0! | #DIV/0! | #DIV/0!
Actual Project Cert of SC Date:
LIHTC MILESTONES | [6 empty] | USES of FUNDS DEVELOPMENT COSTS - SOFT COSTS
|  |  |  | Placed in Service (PIS) |  |  | Description |  |  |  | Award | Due Dill. | Final Alloc.
|  |  | Current "estimated" PIS Date: |  |  |  | Acquisition - Site Demolition:
Last Residential Bldg. "Actual" PIS Date:
*** DO NOT COMBINE THE STAGED SUBMISSION PACKAGES (maintain separate binders/flash drives per submission) ***
PLACE AN 'X' IN THE BOX NEXT TO EACH DOCUMENT SUBMITTED
60 DAY SUBMISSION (due no later than 60 days after the date of Letter of Determination - 42m)
01 | DCA Award letter |  |  | (copy of LoD and HOME Consent ltrs/exhibits)
02 | Awarded QAP Conceptual Site Development Plan (CSD plan) |  |  |  |  | (DCA approved application CSD plan)
03 | Awarded QAP DCA Rehab Work Scope form |  |  |  |  | (DCA approved application DCA Rehab Work Scope form)
04 | ALTA/ACSM Land Title Survey
05 | Geotechnical Report |  |  | (new construction only)
06 | Contractor Approval Package |  |  | (see HOME Underwriting Policies of the QAP Threshold)
07 | Owner/Architect Agreement - executed
08 | Accessibility Consultant DCA Qualifications Package |  |  |  |  | (see QAP & Accessibility Manual for requirements)
09 | Accessibility Consultant Agreement
10 | Accessibility Contractor and Subcontractor Training Sessions Action Plan (submit a document that states how this will be accomplished) | [10 empty] | (min. two training sessions)
11 | Sustainable Building Certification "draft" scoring sheet for the development and related Consultant Agreement | [9 empty] | (agreement/proposal)
12 | HERS Rater Consultant Agreement - (agreement/proposal)
13 | 3rd Party Front-End Cost Review (FECR) DCA Qualifications Package | [5 empty] | (ALL projects) |  |  | (see QAP & Architectural Manual for requirements)
14 | Construction Compliance Inspector Agreement |  |  |  |  | (ALL projects) |  |  | (see QAP & Architectural Manual for requirements)
15 | DCA Amenities & Design Options Re-Certification form (ADO recert) | [5 empty] | (per the awarded CORE application)
16 | DCA Approved Architectural Waivers/Optional Amenities | [5 empty] | (including evidence of DCA approval)
17 | DCA Approved Project Concept Changes |  |  |  | (including evidence of DCA approval)
18 | Other:
DCA REVIEW SUBMISSION (Due 45 days prior to DCA GHFA construction loan closing)
01 | DCA Construction Document Log (drawing log) |  |  |  | (DCA "Review Set") |  | (see instructions for definition of DCA "Review Set")
02 | DCA "Review Set" of drawings (plans) |  |  |  | (DCA "Review Set") |  | (no paper set required-PDF only)
03 | DCA "Review Set" of Project Manual (specs) |  |  |  | (DCA "Review Set") |  | (no paper set required-PDF only)
04 | DCA Schedule of Values form (dca sov) |  |  |  | (DCA "Review Set")
05 | Owner/Contractor Agreement - draft |  |  |  | (current A101 Stipulated Sum or A102 Cost of Work Plus Fee With a Guaranteed Maximum Price forms)
06 | Other Construction Hard Cost Work Scope |  |  |  | (support documentation for hard cost work scope not included in O/C agreement)
07 | Acquisition Soft Cost - Site Demolition Work Scope |  |  |  | (support documentation for "soft cost" site demolition work scope )
08 | Construction Schedule - draft |  |  | (DCA Review Set)
09 | Third Party Front-End Cost Review |  |  | (DCA Review Set) |  | (ALL projects)
10 | Narrative that identifies each Carryover Allocation letter "Assumptions & Conditions" and provides a status update of each condition
|  | (ex.: wetlands delineations, noise mitigation plans, etc.) |  |  |  | (restate each C.o.F in the narrative) |  |  |  | (Construction Srvcs Dept items only)
11 | Federal Work Authorization Affidavits |  |  |  | (E-Verify)
12 | DCA Amenities & Design Options Re-Certification form (ADO recert)
13 | DCA Approved Architectural Waivers/Optional Amenities |  |  |  |  | (including evidence of DCA approval)
14 | DCA Approved Project Concept Changes |  |  |  | (including evidence of DCA approval)
15 | Other:
LOAN CLOSING SUBMISSION (due 10 days prior to DCA GHFA construction loan closing)
01 | DCA Construction Document Log (drawing log) |  |  |  | (DCA "Contract Set") |  | (see instructions for definition of DCA "Contract Set")
02 | DCA "Contract Set" of drawings (plans) |  |  |  | (DCA "Contract Set") |  | (no paper set required-PDF only)
03 | DCA "Contract Set" of Project Manual (specs) |  |  |  | (DCA "Contract Set") |  | (no paper set required-PDF only)
04 | DCA Schedule of Values form (dca sov) |  |  |  | (DCA "Contract Set")
05 | Addendum incorporating/outlining revisions from DCA "Review Set" into the DCA "Contract Set"
06 | Owner/Contractor Agreement - executed |  |  |  | (DCA Contract Set)
07 | Other Construction Hard Cost Work Scope |  |  |  | (support documentation for work not included in O/C agreement)
08 | Acquisition Soft Cost - Site Demolition Work Scope |  |  |  | (support documentation for "soft cost" site demolition work scope )
09 | DCA Amenities & Design Options Re-Certification form (ADO recert)
10 | DCA Approved Architectural Waivers/Optional Amenities |  |  |  |  | (including evidence of DCA approval)
11 | DCA Approved Project Concept Changes |  |  |  | (including evidence of DCA approval)
12 | Other:
COMMENCEMENT SUBMISSION (due prior to construction commencement which must occur within 30 days of bond finance closing date)
01 | Notice to Proceed
02 | Construction Schedule - finalized
03 | Permits |  | (Land Development, Building,,,)
04 | Accessibility Consultant Plan Review Comments
05 | Accessibility Consultant Clearance Letter (acknowledgement of plan review comment resolutions)
06 | DCA Placed in Service (PIS) form - draft with estimated dates | [5 empty] | (DCA OPM Compliance Dept. form)
07 | DCA Amenities & Design Options Re-Certification form (ADO recert)
08 | DCA Approved Architectural Waivers/Optional Amenities |  |  |  |  | (including evidence of DCA approval)
09 | DCA Approved Project Concept Changes |  |  |  | (including evidence of DCA approval)
10 | Other:
OTHER CS SUBMISSIONS
01 | Other:
02 | Other:
DCA#: |  | 0 |  |  |  | Program: | 2021 NHTF 4pct |  |  |  |  | Date: | 0
Note on A13: DEVELOPER CONTACT FOR DCA CONSTRUCTION SERVICES DEPT.
Note on N15: Note: Gross Building "Conditioned" Square Footage
Note on O15: Note: Gross Building "Covered" Square Footage
Note on N24: Note: Gross Building "Conditioned" Square Footage
Note on O24: Note: Gross Building "Covered" Square Footage
Note on O32: Architectural Standards - V. BUILDING INTERIORS DESIGN STANDARDS - B. Unit Sizes: Net Rentable (Leasable) Square Footage: This is the DCA definition for calculating “Residential Unit Square Footage” as it pertains to the Architectural Manual and other documents in Qualified Allocation Plan (QAP). It is calculated for each individual dwelling type. The unit net rentable area is measured from the inside face of each of the unit’s perimeter walls. • Net area included air-conditioned space only. • Measure from the inside (paint) face of all unit perimeter walls. • Do not include any patio, balcony, or breezeway areas. • Do not include any outside storage closets. • Do not deduct any interior walls. • Include non-revenue units in total net rentable living area (Total Residential Unit Square Footage)
Note on M46: Award Notes: Enter hard cost amounts from "awarded" QAP core application Enter data with "60-day" submission.
Note on N46: Due Diligence Notes: Enter hard cost amounts at time of Construction Loan Closing (executed Owner/Contractor agreement, etc.) Enter data with "Commencement" submission.
Note on O46: Final Allocation Notes: Final construction Hard Cost amounts (Change Orders, etc.) that reflect the Final Allocation Application. Enter data with "Construction 8609" submission.
Note on F53: Note: The date for the "AIA G704 Certificate of Substantial Completion"
Note on M57: Award Notes: Enter hard cost amounts from "awarded" QAP core application Enter data with "60-day" submission.
Note on N57: Due Diligence Notes: Enter hard cost amounts at time of Construction Loan Closing (executed Owner/Contractor agreement, etc.) Enter data with "Commencement" submission.
Note on O57: Final Allocation Notes: Final construction Soft Cost amount that reflect the Final Allocation Application. Enter data with "Construction 8609" submission.
Note on B82: Note: Submit copies of DCA approved Project Concept Changes that are related to the Construction Services Dept.
Note on B96: Assumptions & Conditions Status Update Narrative: Provide a narrative that identifies each GHFA Letter of Determination "Assumptions & Conditions" of Funding section and provides a status update of each condition. Restate each "Assumptions & Conditions" verbatim from the Letter of Determination before each response. Note: - Only need to respond to items related to the Construction Services Department requirements
Note on B101: Note: Submit copies of DCA approved Project Concept Changes that are related to the Construction Services Dept.
Note on B116: Note: Submit copies of DCA approved Project Concept Changes that are related to the Construction Services Dept.
Note on B129: Note: Submit copies of DCA approved Project Concept Changes that are related to the Construction Services Dept.

## Formulas (hidden)
Formulas
ResBldgType |  | AccBldgType | ConstType
Elevator-Low Rise |  | Combo Bldg. | New
Elevator-Mid/High Rise |  | Community Bldg. | Rehab
Flat |  | Maintenance Bldg.
Single Family |  | Office Bldg.
Townhome
Walk-up