## Instructions
GA DCA Office of Housing Finance
DCA Construction Document Log - Instructions
(form date: 01.08.25)
| DCA Project #: |  | (2000-###) |  | DCA Submission Type: | (owner rep)
| Project Name: |  |  |  | Form Certif. Date: | (owner rep)
| City: |  |  |  | Certif. Email: | (owner rep)
| Design Firm: |  |  |  | DCA "CD Set" Type: | (arch. rep)
| Rep. Name: |  |  |  | Log Update Date: | (arch. rep)
[5 empty] | Certif. Email: | (arch. rep)
INSTRUCTIONS
Table of Contents
Instructions
Drawings
Project Manual
Addendums
WS Changes
Other Docs
Overview
The DCA Construction Document Log (CD Log) is one of the tools used by DCA Construction Services (CS) Department to assist with expediting the project team's "QAP Construction Compliance" submission requirement process, and to ensure that all parties are working from the same set of construction documents. It is the responsibility of the project team to ensure that DCA is provided with the current set of design and construction documents from the initial submission through project closeout. The CD Log shall contain all project construction documents, including those produced by both the Architect and Engineering firms.
NOTE: The applicable DCA CD Log is used to support each DCA Schedule of Values (DCA SoV) cost column pricing update provided by the Contractor to DCA.
The two "DCA Construction Log "CD Set" Types include:
| • | DCA "Review Set" of CDs
| • | DCA "Contract Set" of CDs
Project Architect
As a requirement of the "QAP Construction Compliance" processes, it is the responsibility of the "Project Architect" to prepare and maintain the "DCA Construction Document Log", and to ensure it's accuracy with project conditions throughout the DCA QAP Construction Compliance submission process. The "Drawings" tab shall reflect the complete set of drawings from the Construction Documents, including drawings that may be outside of the Architect's scope such as Civils and Landscaping drawings.
DCA Construction Log "CD Set" Types
| DCA "Review Set" of CDs |  |  | (DCA "GHFA" funded projects only)
The DCA "Review Set" of Construction Documents (CDs) log is only required for DCA projects that include DCA Georgia Housing Finance Authority (GHFA) managed federal funds (HOME, NHTF,,,), and shall reflect the CDs being submitted by the Ownership during the DCA GHFA Loan Committee "Hard Cost Work Scope" review and approval process.
The DCA "Review Set" of Construction Documents (CDs) log shall include the "Original" issue date of each document, as well as each "Revision" date that occurs prior to the "execution" of the Owner/Contractor Agreement.
The DCA "Review Set" of Construction Documents (CDs) log shall be initially submitted to DCA with the Owner's "DCA Review Submission" package, and updated by the Project Architect during the DCA GHFA Loan Committee "Hard Cost Work Scope" review and approval process.
NOTE: The "final" version" of the DCA "Review Set" of CDs log will be incorporated into the DCA GHFA Loan Committee Construction Hard Cost Clearance approval.
| DCA "Contract Set" of CDs |  |  | (ALL Projects)
The DCA "Contract Set" of CDs is required for ALL projects, and shall reflect the Construction Documents that are referenced in the "executed" Owner/Architect Agreement. This version of the DCA CD Log shall be completed prior to the construction financing loan closing event, and included as an "exhibit" to the Owner/Contractor Agreement that is part of the loan closing documents.
NOTE: For a GHFA funded project, the DCA "Contract Set" of CDs shall incorporate ALL Construction Documents and revisions that were submitted to DCA during the DCA "Review Set" approval process, and that were included with the DCA GHFA Loan Committee Construction Hard Cost Clearance approval.
Addendums |  |  |  | (DCA "GHFA" funded projects only)
During the "DCA GHFA Loan Committee review and approval process", all work scope changes to the DCA "Review Set" of Construction Documents shall be formally documented by the Project Architect through the issuances of "Addendums". These Addendums shall list all work scope changes that occur from the initial CD Log that was submitted with DCA Review Submission package, up to the DCA GHFA Loan Committee "Hard Cost Work Scope" Clearance approval (prior to executing the O/C Agreement). These "Addendums" shall be listed on the updated DCA CD Log and resubmitted to DCA by the Ownership.
Contract Work Scope Changes |  |  |  | (DCA "GHFA" funded projects only)
During the "construction period", all work scope changes to the DCA "Contract Set" of Construction Documents shall be formally documented by the Project Architect through the issuances of AIA Change Order Directives (CCD), Architect's Supplemental Instructions (ASI), Field Orders (FO) or similar type DCA approved document.
NOTE: These documents are a requirement for the DCA GHFA Change Order approval process.
Owner Development Draw |  |  |  | (DCA "GHFA" funded projects only)
In order to track/identify all work scope changes that occur to the DCA "Contract Set" of Construction Documents during the construction period, the Project Architect shall provide an "updated" version of the DCA CD Log for each Owner Development Draw submission to DCA.
Final As-Built CDs |  |  |  | (ALL Projects)
The final "As-Built" DCA "Contract Set" type version of the DCA CD Log will be formally submitted to DCA by the Ownership with both the GHFA Final Draw submission package, and the Construction 8609 Submission package. The Project Architect shall update the CD Log to reflect ALL work scope changes that have occurred to the Construction Documents since the executed date of the Owner/Contractor Agreement ("contract").
DCA GHFA Loan Committee Approval Process Notes
Upon the project team's receipt of the formal DCA "Hard Cost Work Scope" Clearance approval for DCA GHFA Loan Committee, then the DCA received/approved construction documents that occurred during the DCA "Review Set" approval process, shall be incorporated into the DCA "Contract Set" of construction documents. The DCA "Contract Set" version of the DCA CD Log shall be completed, and DCA approved, prior to the GHFA construction financing loan closing event. In addition, the DCA "Contract Set" CD Log shall be included as an "exhibit" to the Owner/Contractor Agreement, and included as part of the GHFA loan closing documents.
CS QAP COMPLIANCE SUBMISSIONS:
DCA Review Submission ("Review Set") Construction Loan Closing Submission ("Contract Set") DCA GHFA Monthly Owner Development Draw Submissions ("Contract Set") DCA GHFA Final Owner Development Draw Submission ("Contract Set")
DCA "Non-GHFA" Funded Projects Notes
For DCA projects that "do not" include DCA GHFA managed federal funds, the DCA "Contract Set" version of the DCA CD Log should be completed prior to the construction financing loan closing event, and included as an "exhibit" to the Owner/Contractor Agreement and included as part of the loan closing documents.
CS QAP COMPLIANCE SUBMISSIONS:
DCA Construction Commencement Submission ("Contract Set") DCA Construction 8609 Submission ("Contract Set")
Detailed instructions for completing this form are included below
The DCA Construction Document Log (CD Log) should be updated during the DCA GHFA Loan Committee pre-construction review/approval process, for the construction financing closing documents, during the construction period DCA GHFA Owner Development Draws and during project closeout.
Form Instructions
• | The "Drawings" tab should reflect all of the current set of drawings in the project set, including drawings that may be outside of the Architect's scope such as Civils and Landscaping drawings.
Cover Sheet
Civil
Landscape
Hardscape
Architectural
Structural
Plumbing
Mechanical
Electrical
• | The "Proj Manual" tab should reflect each section of the current set of specifications and other included documents. The manual/specs shall be detailed, and follow the industry standard Construction Specifications Institute's (CSI) Master Format.
• | The "Addendums" tab should include all of the issued addenda.
• | The "Work Scope Changes" tab should include all of the Architect's issued AIA Change Order Directives (CCD), Architect's Supplemental Instructions (ASI), Field Orders (FO) or similar type DCA approved document..
• | The "Other Docs" should include other issued documents such as supplemental sketches/drawings
• | The CD Log "Revision Date" and "Submittal Type" must be updated with each submission.
• | The CD Log may be modified in order to match the design firm's plan and specification layouts (Note: Do not add additional Excel tabs).
• | An updated CD Log should be included with each related document submission to DCA.
• | Provide one CD Log per project plan set.

## Drawings
GA DCA Office of Housing Finance
DCA Construction Document Log - Drawings
(form date: 01.08.25)
DCA Project #: | 0 | DCA Submission Type: | 0
Project Name: | 0 | Form Certif. Date: | 0
City: | 0 | Certif. Email: | 0
Design Firm: | 0 | DCA "CD Set" Type: | 0
Rep. Name: | 0 | Log Update Date: | 0
|  | Certif. Email: | 0
NOTE: Modify Headings as needed
INDEX OF DRAWINGS |  |  |  |  | NOTE: Instert rows as needed
TITLE/COVER
NUMBER | SHEET NAME |  | ORIGINAL | LATEST REV.
CIVIL
NUMBER | SHEET NAME |  | ORIGINAL | LATEST REV.
LANDSCAPE
NUMBER | SHEET NAME |  | ORIGINAL | LATEST REV.
HARDSCAPE
NUMBER | SHEET NAME |  | ORIGINAL | LATEST REV.
ARCHITECTURAL
NUMBER | SHEET NAME |  | ORIGINAL | LATEST REV.
STRUCTURAL
NUMBER | SHEET NAME |  | ORIGINAL | LATEST REV.
PLUMBING
NUMBER | SHEET NAME |  | ORIGINAL | LATEST REV.
MECHANICAL
NUMBER | SHEET NAME |  | ORIGINAL | LATEST REV.
ELECTRICAL
NUMBER | SHEET NAME |  | ORIGINAL | LATEST REV.
?????
NUMBER | SHEET NAME |  | ORIGINAL | LATEST REV.

## Proj Man
GA DCA Office of Housing Finance
DCA Construction Document Log - Project Manual (specs)
(form date: 01.08.25)
DCA Project #: | 0 | DCA Submission Type: | 0
Project Name: | 0 | Form Certif. Date: | 0
City: | 0 | Certif. Email: | 0
Design Firm: | 0 | DCA "CD Set" Type: | 0
Rep. Name: | 0 | Log Update Date: | 0
|  | Certif. Email: | 0
NOTE: Modify Headings as needed
INDEX OF PROJECT MANUAL (SPECS) |  |  |  |  | NOTE: Instert rows as needed
DIV 01 | GENERAL REQUIREMENTS
NUMBER | SECTION NAME |  | ORIGINAL | LATEST REV.
DIV 02 | SITE WORK
NUMBER | SECTION NAME |  | ORIGINAL | LATEST REV.
DIV 03 | CONCRETE WORK
NUMBER | SECTION NAME |  | ORIGINAL | LATEST REV.
DIV 04 | MASONRY
NUMBER | SECTION NAME |  | ORIGINAL | LATEST REV.
DIV 05 | METALS
NUMBER | SECTION NAME |  | ORIGINAL | LATEST REV.
DIV 06 | CARPENTRY
NUMBER | SECTION NAME |  | ORIGINAL | LATEST REV.
DIV 07 | THERMAL AND MOISTURE PROTECTION
NUMBER | SECTION NAME |  | ORIGINAL | LATEST REV.
DIV 08 | DOORS, WINDOWS AND GLASS
NUMBER | SECTION NAME |  | ORIGINAL | LATEST REV.
DIV 09 | FINISHES
NUMBER | SECTION NAME |  | ORIGINAL | LATEST REV.
DIV 10 | MISCELLANEOUS BUILDING SPECIALTIES
NUMBER | SECTION NAME |  | ORIGINAL | LATEST REV.
DIV 11 | EQUIPMENT
NUMBER | SECTION NAME |  | ORIGINAL | LATEST REV.
DIV 14 | ELEVATOR
NUMBER | SECTION NAME |  | ORIGINAL | LATEST REV.
DIV 15 | MECHANICAL
NUMBER | SECTION NAME |  | ORIGINAL | LATEST REV.
DIV 16 | ELECTRICAL
NUMBER | SECTION NAME |  | ORIGINAL | LATEST REV.
DIV 17 | SPECIAL CONSTRUCTION
NUMBER | SECTION NAME |  | ORIGINAL | LATEST REV.

## Addendums
GA DCA Office of Housing Finance
DCA Construction Document Log - Addendums
(form date: 01.08.25)
DCA Project #: | 0 |  | DCA Submission Type: | 0
Project Name: | 0 |  | Form Certif. Date: | 0
City: | 0 |  | Certif. Email: | 0
Design Firm: | 0 |  | DCA "CD Set" Type: | 0
Rep. Name: | 0 |  | Log Update Date: | 0
|  |  | Certif. Email: | 0
NOTE: Modify Headings as needed
ADDENDUMS | [5 empty] | NOTE: Instert rows as needed
ADDENDUM
NUMBER |  | DESCRIPTION |  | ISSUE DATE | LATEST REV.

## WS Changes
GA DCA Office of Housing Finance
DCA Construction Document Log - WS Changes
(form date: 01.08.25)
DCA Project #: | 0 |  | DCA Submission Type: | 0
Project Name: | 0 |  | Form Certif. Date: | 0
City: | 0 |  | Certif. Email: | 0
Design Firm: | 0 |  | DCA "CD Set" Type: | 0
Rep. Name: | 0 |  | Log Update Date: | 0
|  |  | Certif. Email: | 0
NOTE: Modify Headings as needed
Contract Work Scope Changes (COD, ASI, FO,,,) | [5 empty] | NOTE: Instert rows as needed
AIA Change Order Directives (CCD), Architect's Supplemental Instructions (ASI), Field Orders (FO) or similar type DCA approved document.
NUMBER | TYPE | DESCRIPTION |  | ISSUE DATE | LATEST REV.

## Other Docs
GA DCA Office of Housing Finance
DCA Construction Document Log - Other CDs
(form date: 01.08.25)
DCA Project #: | 0 | DCA Submission Type: | 0
Project Name: | 0 | Form Certif. Date: | 0
City: | 0 | Certif. Email: | 0
Design Firm: | 0 | DCA "CD Set" Type: | 0
Rep. Name: | 0 | Log Update Date: | 0
|  | Certif. Email: | 0
NOTE: Modify Headings as needed
OTHER CONSTRUCTION DOCUMENTS |  |  |  |  | NOTE: Instert rows as needed
SUPPLEMENTAL DRAWINGS/SKETCHES
NUMBER | DESCRIPTION |  | ISSUE DATE | LATEST REV.
OTHER
NUMBER | DESCRIPTION |  | ISSUE DATE | LATEST REV.