## Slide 1
Federal Compliance Overview
The CDBG Compliance Lifecycle
From award through closeout
Brittney Hickom | 2026 CDBG Summit
Notes: Welcome to compliance day! This overview provides a mental map for the compliance sessions that follow. Receiving an award begins the compliance process.

## Slide 2
Georgia Department of Community Affairs
2
The CDBG compliance lifecycle
Each stage creates the record DCA will rely on at monitoring and closeout.
Award &
setup
Planning
Environmental review
& acquisition
Procurement
& contracting
Construction
& implementation
Completion
Monitoring
& closeout
Requirements that continue throughout the lifecycle
National objective Citizen participation Civil rights & Section 504 Financial management Recordkeeping
Notes: Through the life of an award, there are multiple stages of compliance. Some requirements occur at one point, while national objective, citizen participation, civil rights, financial management, and recordkeeping continue throughout the project.

## Slide 3
Georgia Department of Community Affairs
3
Three principles for every CDBG project
1
Know before you act
Identify the requirements triggered by the approved project before committing funds or taking project action.
2
Sequence matters
Complete required reviews and clearances before acquisition, contracting, construction, or another choice limiting action.
3
Document as you go
Maintain a complete grant file that shows what occurred, who approved it, and when each step was completed.
CDBG compliance is easier to manage prospectively than to correct retrospectively.
Notes: These are the three thoughts and/or practices recipients should carry through every session today. Timing and documentation often determine whether an otherwise eligible activity remains eligible.

## Slide 4
Georgia Department of Community Affairs
4
Award and project setup
01
SETUP
The approved application defines the project DCA has agreed to fund.
Confirm the award
Approved scope, activities, and budget
Beneficiaries and national objective
Performance period and key conditions
Build the compliance file
Grant administration and recordkeeping systems
Citizen participation documentation
Section 504 and accessibility responsibilities
First compliance questions
What requirements apply to this project? Who owns each step? What must occur before work begins?
Notes: The first compliance questions you should be asking are: What requirements apply to this project? Who owns each step? What must occur before work begins?
The grant agreement and approved application control the project. It’s important to assign responsibilities early and establish the file structure before activity begins.

## Slide 5
Georgia Department of Community Affairs
5
Before you buy, bid, or build
Five checkpoint questions
1
Environmental review
Has DCA issued environmental clearance?
2
Property
Does acquisition, easement, donation, or displacement trigger URA?
3
Materials
Does Build America, Buy America apply?
4
Procurement
What competitive method and documentation are required?
5
Labor
Will federal labor standards apply to the contract?
STOP
Some actions cannot be corrected after the fact.
The source used to pay for one activity does NOT remove federal requirements when that activity supports the CDBG project.
When in doubt, contact DCA before proceeding.
Notes: This is the key caution slide. Federal requirements are not automatically avoided if you are using local or private funds for a connected activity. Because your project is funding with CDBG monies, all federal requirements apply. Choice limiting actions, acquisition activity, procurement, and construction can create compliance issues when taken too early. These 5 checkpoint questions are a great place to begin.

## Slide 6
Georgia Department of Community Affairs
6
Procurement and contracting
The procurement file must show a fair process and support the final contract.
1
Scope
Clear and complete
2
Method
Correct threshold
3
Solicitation
Open competition
4
Evaluation
Documented basis
5
Contract
Required clauses
6
Notice to proceed
Only after checkpoints
The contract carries federal requirements into construction. Verify clauses, contractor eligibility, and compliance responsibilities before execution.
Notes: The procurement file moves from scope through notice to proceed. The contract must contain the required provisions and clearly assign compliance responsibilities. The upcoming procurement and labor standards sessions will dive into these more today.

## Slide 7
Georgia Department of Community Affairs
7
Construction and implementation
Construction compliance depends on decisions made before work begins.
Federal labor standards
Payroll review, worker interviews, classifications, and restitution when required
Build America, Buy America
Track covered materials, product certifications, and approved exceptions
Environmental conditions
Carry mitigation measures and permit conditions into contracts and field oversight
Contract and draw records
Document inspections, change orders, invoices, approvals, and progress payments
Monitor throughout implementation. Correct issues promptly and preserve the supporting record.
Notes: The four implementation responsibilities seen here will also be presented in more detail during the afternoon sessions. Please remember that strong construction compliance starts with the environmental review, procurement process, and contract documents.

## Slide 8
Georgia Department of Community Affairs
8
Federal and state requirements run in parallel
Recipients must maintain project compliance and remain eligible under State reporting and planning requirements.
FEDERAL PROJECT
COMPLIANCE
Environmental review URA BABA Procurement Labor standards Civil rights National objective
STATE ELIGIBILITY
& REPORTING
Audits GOMI RLGF Service Delivery Strategy Comprehensive Plan Qualified Local Government status
Complete records support both tracks at monitoring and closeout.
Notes: Federal and state requirements run in parallel through the life of your award. Recipients must maintain project compliance and remain eligible under State reporting and planning requirements. A project can face consequences if either track falls out of compliance.

## Slide 9
Georgia Department of Community Affairs
9
A compliant closeout begins on day one
The goal is an eligible project completed in the correct sequence, supported by a record that demonstrates compliance.
Plan
Clear
Procure
Build
Document
Close
Before taking action, ask:
Is the activity eligible? Has the required clearance occurred? Does the file show the decision and timing?
Notes: The goal is an eligible project completed in the correct sequence, supported by a record that demonstrates compliance.
Recipients should be asking themselves these three questions before acting. Then transition directly into Citizen Participation and Section 504.